## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Restoration work for laying of under ground water supply line (400 mm dia) Ch. 0.100 kmp to ch 1.350 on Ukhra Haripur (0-5) road in the district of Pachim Bardhaman |  |  | BILL/00463/2023-2024 | 235/23-24 | 29/08/2023 |  | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 32.64 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Formal work order Distribution Network including FHTC & alied work at Ondal Block of RCFA Part-II (Zone-12A) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000065/2023-2024 | 1764/RCD I | 16/05/2023 | 13/09/2023 | MRITYUNJOY MUKHERJEE & CO. | 610.49 | 195.98 | 32.1 | 50
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Formal work for Construction of 1000 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connetion and cost of pipes,specials at Ondal Block (Zone-12A) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil investigation and chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. in District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000096/2023-2024 | 1847/RCD-I | 31/05/2023 | 25/05/2024 | M/S PIONEER CONSTRUCTION | 203.2 | 152.4 | 75 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Pancgachia (240 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2023-2024 | 3017/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.92 | 2.46 | 50 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Sub Soil Investigation for 1000 cum capacity RCC Over Head Reservoir at (Zone-12A) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000578/2022-2023 | 3366/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Formal work order for distributionn network for RCFA Part-II piped Water Supply Including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-12B)(Segment-1) | Assistant Engineer 2 | Junior Engineer | ORD/000805/2022-2023 | 931/RCDI | 14/03/2023 | 13/05/2023 | ARISTOCON ENGINEER'S CO-OP. SOCIETY LTD. | 157.79 | 98.12 | 62.18 | 82
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 2946/RCD-I | 11/10/2023 |  | Resource Division | 6.78 | 0 | 0 | 0
Total | [13 empty] | 1016.31 | 448.96 | 44.18