## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum work order for Re-connection of FHTC & additional Functional Household Tap Connection (FHTC) for Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC for new pipe line laying under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 6 | ORD/000289/2024-2025 | 2630/RCD-I | 14/11/2024 | 29/03/2025 | SHWET BARANI | 23.56 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Formal order for the work of Laying of 110/90/75 mm dia HDPE pipe line with necessary allied works at Annandapur mouza ICDS to Dompara under Kanksa (Zone-I ) W/s Scheme for upcoming combat draught like situation in Kanksa block under DWSD,PHE Dte (SL-04) |  |  | ORD/000022/2021-2022 | 832/DWSD | 24/05/2021 | 08/06/2021 | M/S KALYANI ENTERPRISE | 5.12 | 0.74 | 14.5 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJM at Radhamohanpur mouza-36 and its adjoining area under command area of Basudha piped W/s Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000046/2022-2023 | 581/DWSD | 21/04/2022 | 28/04/2022 | JOY GURU ENTERPRISE | 4.77 | 4.83 | 101.37 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Providing water supply of office of the deputy inspector General of Police group center at Radhamohanpur under Kanksa and Bonkati GP having with electricity but uncovered by PWSS under DWSD,PHE Dte (SL-03) |  |  | ORD/000047/2022-2023 | 582/DWSD | 21/04/2022 | 28/04/2022 | JOY GURU ENTERPRISE | 2.12 | 2.12 | 100 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000091/2022-2023 | 723/DWSD | 06/05/2022 | 21/05/2022 | BABA LOKENATH ENTERPRISE | 30.27 | 5.38 | 17.78 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Panagarh mouza(JL-85) of Pal para,Hazra bera,Kumar para ,near Tilakchandrpaur Panchayat near Panagarh bypass under DWSD,PHE Dte (SL-12) |  |  | ORD/000092/2021-2022 | 1104/DWSD | 30/07/2021 | 14/08/2021 | GITA CONSTRUCTION | 4.98 | 4.98 | 100 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Jhinuk Garia and Kanksa Hotal para under DWSD,PHE Dte (SL-13) |  |  | ORD/000093/2021-2022 | 1105/DWSD | 30/07/2021 | 14/08/2021 | GITA CONSTRUCTION | 4.82 | 4.82 | 100 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum form order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Duck Bunglow and Kanksa colony para under DWSD,PHE Dte (SL-14) |  |  | ORD/000094/2021-2022 | 1106/DWSD | 30/07/2021 | 14/08/2021 | GITA CONSTRUCTION | 4.98 | 4.98 | 100 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Adibashipara and Kanksa 3 No colony under DWSD,PHE Dte (SL-15) |  |  | ORD/000095/2021-2022 | 1107/DWSD | 30/07/2021 | 14/08/2021 | GITA CONSTRUCTION | 4.89 | 4.89 | 100 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Formal order for the work of Restoration of exiting house hold tap connection (Damaged) and re connection of the same in connection of JJM and changes of defective pipe line of 90/110/125/140/200 mm dia UPVC pipe line at different places of distribution main command area of Basudha Piped W/s Scheme under DWSD,PHE Dte (SL-08) |  |  | ORD/000175/2022-2023 | 1160/DWSD | 01/08/2022 | 11/08/2022 | MD AAMIR KHAN | 5.04 | 4.99 | 99.07 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Replace damaged 250 mtr 150 mm dai AC pipe with the UPVC 160 mm dia pipe line at Panagarh Baruipara ,Ijjatganj OHR cleaning leakage bursting at Ijjatganj and others allied works of Kanksa Zone-II ph-II W/s Scheme under DWSD,PHE Dte (SL_06) |  |  | ORD/000187/2021-2022 | 1408/DWSD | 29/09/2021 | 14/10/2021 | RANJIB GHATAK | 4.2 | 4.2 | 100.2 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Withdrawing of damaged 160 mm dia UPVC pipe and laying of additional length of pipe at Basudha and Ajodhya and repairing of damaged pipe due to newly constructed WBSRDA road and others allied works of Basudha W/s Scheme under DWSD,PHE Dte (SL-08) |  |  | ORD/000202/2022-2023 | 1074/DWSD | 12/07/2022 | 27/07/2022 | MAK CONSTRUCTION CO. | 4.26 | 4.24 | 99.66 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000258/2020-2021 | 1317/DWSD | 09/12/2020 | 23/01/2021 | JOY GURU ENTERPRISE | 25.99 | 3.37 | 12.97 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) |  |  | ORD/000258/2021-2022 | 1676/DWSD | 30/11/2021 | 04/01/2022 | M/S. D. PALIT & CO. | 18.62 | 1.29 | 6.91 | 100
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Z-II)(Ph-II) W/s Scheme to laying branch pipe line in kanksa block for providing FHTC at PanagarhJL_85) at Palpara ,Hazra Para ,Kumanrpara near TC pur Panchayat ,Panagarh bypass under DWSD PHE Dte (Sl-04) |  |  | ORD/000359/2021-2022 | 78/DWSD | 24/01/2022 | 08/02/2022 | GITA CONSTRUCTION | 3.46 | 3.39 | 97.98 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) |  |  | ORD/000392/2020-2021 | 186/DWSD | 04/02/2021 | 21/03/2021 | M/S BADAL GHOSH | 4.92 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-I W/s Scheme to combat draught like situation at in Kaksa Block to providing FHTC at Ijjatganj Mouza (JL-79) under DWSD,PHE Dte..(SL-04) |  |  | ORD/000417/2020-2021 | 273/DWSD | 26/02/2021 | 23/03/2021 | RANJIB GHATAK | 4.97 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Continuation order for the work of providing functional household tap connection (FHTC) in connection with JJM at Kajladihi mouza(JL-26) under command area of Krishnapur Piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte. |  |  | ORD/000427/2021-2022 | 346/DWSD | 17/03/2022 | 01/04/2022 | THE STAR & CO | 2.72 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing restoration of distribution system of Nachan OHR (Part-B) from Nachan More to Dhaboni Lobnapara under Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte.(SL-05) |  |  | ORD/000432/2021-2022 | 412/DWSD | 30/03/2022 | 14/04/2022 | PAYAL CONSTRUCTION | 4.63 | 1.64 | 35.36 | 0
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of laying of distribution pipe line with necessary allied work at Domra and Piariganj mouza under Tilakchandrapur W/s Scheme for FHTC under DWSD, PHE Dte. |  |  | ORD/000443/2021-2022 | 422/DWSD | 30/03/2022 | 09/04/2022 | AMARANJALI CONSTRUCTION | 4.74 | 4.73 | 99.92 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Zone-II) (Phase-II) W/s Scheme to laying branch pipe line in Kanksa block to providing FHTC at Kanksa Mouza (JL-89) at Jhinuk Raia Hotel para ,Duck bungalow colony para under DWSD, PHE Dte.(SL-16) |  |  | ORD/000452/2021-2022 | 431/DWSD | 30/03/2022 | 14/04/2022 | GITA CONSTRUCTION | 4.95 | 4.95 | 100 | 0
Total | [13 empty] | 174 | 65.55 | 37.67