## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Pratabpur high school under Durgapur -Faridpur block covered by Jamgora-Jagannathpur PWSS under DWSD, PHE Dte (SL-20) |  |  | ORD/000377/2021-2022 | 115/DWSD | 01/02/2022 | 21/02/2022 | M/S MONDAL ENTERPRISE | 1.1 | 1.1 | 100 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Ijjatganj Junior high school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte |  |  | ORD/000378/2021-2022 | 116/DWSD | 01/02/2022 | 16/02/2022 | M/S MONDAL ENTERPRISE | 1.1 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Kanksa Poral para F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte |  |  | ORD/000379/2021-2022 | 117/DWSD | 01/02/2022 | 16/02/2022 | BABA LOKENATH ENTERPRISE | 1.1 | 1.1 | 100 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Shibpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS under DWSD, PHE Dte |  |  | ORD/000380/2021-2022 | 118/DWSD | 01/02/2022 | 16/02/2022 | M/S MONDAL ENTERPRISE | 2.12 | 2.03 | 96.06 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Dubrajpur F.P. school under Kanksa block covered by Kanksa (Zone-II) PWSS having Electricity but uncovered by PWSS under DWSD, PHE Dte |  |  | ORD/000381/2021-2022 | 119/DWSD | 01/02/2022 | 21/02/2022 | BASANTI TRADERS | 2.12 | 1.96 | 92.87 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of Providing water supply to Birudiha High school under Kanksa block covered by Kanksa (Zone-II) having electricity but uncovered by PWSS under DWSD, PHE Dte (SL-26) |  |  | ORD/000382/2021-2022 | 120/DWSD | 01/02/2022 | 21/02/2022 | BASANTI TRADERS | 2.11 | 2.06 | 97.45 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | School | Acceptance cum formal order for the work of providing water supply to panagarh bazar high school under Kanksa block covered by Kanksa (Zone-II) PWSS having electricity but uncovered by PWSS under DWSD ,PHE Dte (Sl-24) |  |  | ORD/000404/2021-2022 | 121/DWSD | 20/01/2022 | 04/02/2022 | BABA LOKENATH ENTERPRISE | 2.12 | 1.82 | 86.03 | 0
Total | [13 empty] | 11.77 | 10.08 | 85.68