## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE/CI/DI distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-B) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-13) |  |  | ORD/000027/2023-2024 | 762/DWSD | 22/05/2023 | 26/06/2023 | JOY GURU ENTERPRISE | 94.09 | 65.76 | 69.89 | 85
2 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-C) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) |  |  | ORD/000028/2023-2024 | 759/DWSD | 19/05/2023 | 23/06/2023 | ANWESHA CONSTRUCTION | 98.7 | 49.22 | 49.87 | 65
3 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-E) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman |  |  | ORD/000029/2023-2024 | 761/DWSD | 22/05/2023 | 26/06/2023 | SWATI CORPORATION | 95.42 | 55.3 | 57.95 | 45
4 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-D) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman |  |  | ORD/000030/2023-2024 | 763/DWSD | 22/05/2023 | 26/06/2023 | PRAVAT SARKAR | 98.69 | 16.75 | 16.98 | 40
5 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-F) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman |  |  | ORD/000031/2023-2024 | 811/DWSD | 29/05/2023 | 03/07/2023 | CHATTERJEE CONSTRUCTION | 87.79 | 60.58 | 69 | 75
6 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-A) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-18) |  |  | ORD/000032/2023-2024 | 810/DWSD | 29/05/2023 | 03/07/2023 | BASANTI TRADERS | 99.25 | 73.44 | 73.99 | 70
7 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Drawing design and surveying work for proposed piped W/S Scheme of Tetikhola Piped W/s Scheme under DWSD ,PHE Dte (SL-14) |  |  | ORD/000169/2022-2023 | 1035/DWSD | 04/07/2022 | 19/07/2022 | APEX ENGINEERING | 3.9 | 3.9 | 100 | 0
8 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Sinking of 03 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at TETIKHOLA H/W site & TW-II site of Durgapur-Faridpur Block under TETIKHOLA piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000456/2022-2023 | 309/DWSD | 20/02/2023 | 27/03/2023 | M/S. D. PALIT & CO. | 47.15 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of construction of boundary wall at TETIKHOLA pump house site No-2 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000505/2022-2023 | 321/DWSD | 20/02/2023 | 22/03/2023 | CHATTERJEE CONSTRUCTION | 15.35 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangement at TW No-2 site at Tetikhola H/W site under Tetikhola piped W/S Scheme under DWSD ,PHE Dte |  |  | ORD/000507/2022-2023 | 324/DWSD | 20/02/2023 | 27/03/2023 | MUKHERJEE ENTERPRISE | 13.83 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Construction of boundary wall at Tetikhola H/W site (OHR ) site ,land development ,approach road and others allied works of Augmentation of Tetikhola piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000513/2022-2023 | 330/DWSD | 20/02/2023 | 22/03/2023 | BISHAL ENTERPRISE | 34.05 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at TW No-3 site at Tetikhola under Tetikhola piped W/S Scheme under DWSD ,PHE Dte |  |  | ORD/000518/2022-2023 | 335/DWSD | 20/02/2023 | 17/03/2023 | M/S BANERJEE CONSTRUCTION | 6.88 | 3.44 | 50 | 100
13 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Construction of boundary wall at TETIKHOLA pump house site No-3 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000520/2022-2023 | 322/DWSD | 20/02/2023 | 22/03/2023 | BABA LOKENATH ENTERPRISE | 15.35 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Acceptance cum formal order for the work of Laying ,aligning of DI K9 R/M pipe and interconnection between 3 Nos Tube well with OHR and other allied works of Tetikhola piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000605/2022-2023 | 504/DWSD | 28/03/2023 | 22/04/2023 | BISHAL ENTERPRISE | 48.29 | 0 | 0 | 50
15 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 788/DWSD | 25/05/2023 |  | Resource Division | 63.52 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | New | Supply, delivery & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I,II and III under Tetikhola Piped Water Supply Scheme, Block- Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000039/2023-2024 | 1022/AMD | 19/04/2023 | 18/07/2023 | M/S SWAPAN BANERJEE | 34.29 | 0 | 0 | 0
Total | [13 empty] | 856.56 | 328.39 | 38.34