## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Acceptance cum Work Order for Balance work of distribution pipe line of Kanska Zone-II (Part-B)from OHR to Pathanpara under Augmentation of Birudiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 7 | ORD/001178/2023-2024 | 1019/RCD-I | 16/03/2024 | 30/04/2024 | MD AAMIR KHAN | 35.4 | 17.68 | 49.96 | 80
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 134/RCD-I | 18/01/2024 |  | Resource Division | 130.63 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Acceptance cum formal order for the work of creating a separate zone for BIRUDIHA of Birudiha piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Birudiha, Manikara Mouza under Augmentation of BIRUDIHA piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000109/2023-2024 | 1136/DWSD | 20/07/2023 | 03/09/2023 | M/S K.B.CONSTRUCTION | 98.43 | 35.48 | 36.04 | 90
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Birudiha piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000230/2023-2024 | 1551/DWSD | 19/09/2023 | 18/11/2023 | KHAN ENTERPRISE | 291.36 | 0 | 0 | 90
Total | [13 empty] | 555.82 | 53.16 | 9.56