## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum Work Order for balance work for Construction of site office at Panagarh of RCFA Division-I PHE Dte. under Augmentation of Jatgoria W/S Scheme JJm Fund. | Assistant Engineer 2 |  | ORD/000911/2023-2024 | 211/RCD-I | 29/01/2024 | 29/03/2024 | BASANTI TRADERS | 32.98 | 16.38 | 49.67 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of JATGARIA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -09) |  |  | ORD/000190/2023-2024 | 1192/DWSD | 25/07/2023 | 01/08/2023 | MEASURE LAND | 0.78 | 0.39 | 50 | 100
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Formal order for the work of balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Jatgoria piped W/s Scheme udner DWSD, PHE Dte |  |  | ORD/000232/2023-2024 | 1579/DWSD | 21/09/2023 | 20/11/2023 | SUPER SKILL | 145.14 | 24.89 | 17.15 | 70
Total | [13 empty] | 178.89 | 41.66 | 23.29