## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - DARJEELING
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | DARJEELING | Darjeeling Division | Mirik | 4th (2021-2022) | New | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | TSM/008814 |  | 40036759 | 1 | 430 | 430 | 430 | 170.07 | 170.07 | Yes | 17/11/2021 | GO2122005523PH | SVS | TPH212245633M001 | Administrative Approval Issued | N/A | Yes | 161.42 | Yes | 161.42 | 29/09/2021
2 | DARJEELING | Darjeeling Division | Darjeeling Pulbazar | 4th (2021-2022) | New | RIMBICK WATER SUPPLY SCHEME | SM/09427 | TSM/008813 |  | 40018522 | 1 | 1635 | 1636 | 1636 | 627.68 | 627.68 | Yes | 17/11/2021 | GO2122005523PH | SVS | TPH212245633M002 | Administrative Approval Issued | N/A | Yes | 628.93 | Yes | 628.93 | 29/09/2021
3 | DARJEELING | Darjeeling Division | Darjeeling Pulbazar | 3rd (2022-2023) | New | BHIRGAON DHARGAON PWSS | SM/18714 | TSM/011777 |  |  | 1 | 571 | 149 | 149 | 162.75 | 162.75 | Yes | 07/08/2023 | 2280/PHE/IV/W-621/23 | SVS |  | Administrative Approval Issued | N/A | Yes | 152.77 | Yes | 152.77 | 05/07/2022
4 | DARJEELING | Darjeeling Division | Jorebunglow Sukiapokhri | 5th (2020-2021) | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] | SM/10258 | TSM/007003 | SM/05523 | 7392446 | 2 | 2201 | 1510 | 1560 | 112.63 | 112.63 | Yes | 09/02/2021 | GO2021006679PH | MVS |  | Administrative Approval Issued | N/A | Yes | 72.46 | Yes | 72.46 | 08/01/2021
5 | DARJEELING | Darjeeling Division |  | 5th (2020-2021) | Retrofitting | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | TSM/007001 | SM/05531 | 7392519 | 0 | 0 | 3812 | 3812 | 269.79 | 269.79 | Yes | 09/02/2021 | GO2021006682PH | MVS |  | Administrative Approval Issued | N/A | Yes | 202.06 | Yes | 202.06 | 08/01/2021
6 | DARJEELING | Darjeeling Division | Rangli Rangliot | 5th (2020-2021) | Retrofitting | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | SM/10261 | TSM/006997 | SM/05398 | 7401882 | 1 | 503 | 279 | 328 | 34.5 | 34.5 | Yes | 09/02/2021 | GO2021006683PH | MVS |  | Administrative Approval Issued | N/A | Yes | 19.62 | Yes | 19.62 | 08/01/2021
7 | DARJEELING | Darjeeling Division | Darjeeling Pulbazar | 5th (2021-2022) | New | Hatta Water Supply Scheme | SM/09449 | TSM/008806 |  | 40018692 | 1 | 785 | 310 | 310 | 313.13 | 313.13 | Yes | 19/11/2021 | GO2122005605PH | SVS | PH212245640S000 | Administrative Approval Issued | N/A | Yes | 314.01 | Yes | 314.01 | 08/10/2021
8 | DARJEELING | Darjeeling Division |  | 5th (2020-2021) | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | TSM/007002 | SM/05195 | 40009401 | 0 | 0 | 1005 | 1005 | 80.55 | 80.55 | Yes | 09/02/2021 | GO2021006680PH | MVS |  | Administrative Approval Issued | N/A | Yes | 69.58 | Yes | 69.58 | 08/01/2021
Total | [10 empty] | 7 | 6125 | 9131 | 9230 | 1771.1 | 1771.1 | [8 empty] | 1620.85 |  | 1620.85