## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - MALDAH
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | MALDAH | Malda Division | Ratua - I | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | SM/06855 | TSM/005684 | SM/01530 | 8128312 | 2 | 1316 | 1366 | 1366 | 73.75 | 73.75 | Yes | 07/10/2020 | GO2021001800PH | MVS |  | Administrative Approval Issued | N/A | Yes | 28.28 | Yes | 39.79 | 28/08/2020
2 | MALDAH | Malda Division | Gazole | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme | SM/06860 | TSM/005689 | SM/04470 | 6260105 | 10 | 2046 | 1749 | 1749 | 93.04 | 93.04 | Yes | 07/10/2020 | GO2021001807PH | MVS |  | Administrative Approval Issued | N/A | Yes | 10.57 | Yes | 71.62 | 28/08/2020
3 | MALDAH | Malda Division | Chanchal - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | SM/06861 | TSM/005690 | SM/03892 | 8128320 | 3 | 2041 | 1675 | 1675 | 89.31 | 89.31 | Yes | 07/10/2020 | GO2021001808PH | MVS |  | Administrative Approval Issued | N/A | Yes | 125.61 | Yes | 64.73 | 28/08/2020
4 | MALDAH | Malda Division | Habibpur | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme | SM/06864 | TSM/005693 | SM/03304 | 8128333 | 12 | 1348 | 1186 | 1186 | 64.66 | 64.66 | Yes | 07/10/2020 | GO2021001819PH | MVS |  | Administrative Approval Issued | N/A | Yes | 42.18 | Yes | 54.51 | 28/08/2020
5 | MALDAH | Malda Division | Harischandrapur - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | SM/06872 | TSM/005701 | SM/03071 | 8128353 | 1 | 1905 | 1639 | 1639 | 87.48 | 87.48 | Yes | 08/10/2020 | GO2021001833PH | SVS |  | Administrative Approval Issued | N/A | Yes | 52.27 | Yes | 25.96 | 28/08/2020
6 | MALDAH | Malda Division | Ratua - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme | SM/06869 | TSM/005698 | SM/02517 | 8128348 | 3 | 3231 | 1642 | 1642 | 87.63 | 87.63 | Yes | 08/10/2020 | GO2021001830PH | MVS |  | Administrative Approval Issued | N/A | Yes | 66.89 | Yes | 66.89 | 28/08/2020
7 | MALDAH | Malda Division | Chanchal - I | 1st(2022-2023) | New | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | TSM/011680 |  | 40022690 | 7 | 1808 | 1607 | 1607 | 611.23 | 710.64 | Yes | 12/09/2022 | GO2223007475PH | MVS | PH222355774S000 | Administrative Approval Issued | N/A | Yes | 172.11 | Yes | 420.89 | 25/04/2022
8 | MALDAH | Malda Division | Harischandrapur - II | 11th(2021-2022) | New | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | TSM/011264 |  | 40016192 | 2 | 2596 | 1856 | 2900 | 547.19 | 618.45 | Yes | 22/07/2022 | GO2223005409PH | SVS | PH222358774S000 | Administrative Approval Issued | N/A | Yes | 116.79 | Yes | 541.32 | 30/03/2022
9 | MALDAH | Malda Division | Gazole | 4th (2022-2023) | Augmentation | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | TSM/012797 | SM/03206 | 40026270 | 1 | 1758 | 0 | 0 | 124.51 | 135.51 | Yes | 09/09/2022 | GO2223007370PH | SVS | PH222362123S000 | Administrative Approval Issued | N/A | Yes | 39.69 | Yes | 114.17 | 15/07/2022
10 | MALDAH | Malda Division | Chanchal - I | 3rd (2022-2023) | New | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | TSM/013249 |  | 40027588 | 5 | 3136 | 3192 | 3192 | 686.89 | 761.39 | Yes | 07/09/2022 | GO2223007127PH | MVS | PH222361922S000 | Administrative Approval Issued | N/A | Yes | 165.14 | Yes | 711.41 | 05/07/2022
11 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | TSM/013248 |  | 40022364 | 2 | 901 | 969 | 969 | 312.99 | 346.83 | Yes | 06/09/2022 | GO2223007115PH | MVS | PH222361923S000 | Administrative Approval Issued | N/A | Yes | 72.41 | Yes | 300.6 | 05/07/2022
12 | MALDAH | Malda Division | Habibpur | 3rd (2022-2023) | New | TALPUKUR Piped Water Supply Scheme | SM/12189 | TSM/013199 |  | 40027590 | 11 | 1893 | 2190 | 2190 | 663.8 | 730.06 | Yes | 07/09/2022 | GO2223007228PH | MVS | PH222361952S000 | Administrative Approval Issued | N/A | Yes | 1657.72 | Yes | 678.29 | 05/07/2022
13 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | TSM/013468 |  | 40034633 | 10 | 2909 | 3312 | 3312 | 1315.09 | 1389.03 | Yes | 17/11/2022 | GO2223009853PH | MVS | PH222362551S000 | Administrative Approval Issued | N/A | Yes | 122.7 | Yes | 1325.53 | 22/08/2022
14 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | SULTANNAGAR PWSS | SM/12196 | TSM/012936 |  | 40027597 | 3 | 1415 | 1659 | 1659 | 445.36 | 512.75 | Yes | 07/09/2022 | GO2223007216PH | MVS | PH222361960S000 | Administrative Approval Issued | N/A | Yes | 1228.33 | Yes | 404.99 | 05/07/2022
15 | MALDAH | Malda Division | Maldah (Old) | 5th (2022-2023) | Augmentation | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | TSM/014459 | SM/02831 | 40026214 | 9 | 1968 | 750 | 750 | 353.11 | 369.49 | Yes | 20/09/2022 | GO2223007980PH | MVS | PH222362544S000 | Administrative Approval Issued | N/A | Yes | 175.73 | Yes | 263.21 | 22/08/2022
16 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | SAIDPUR Piped Water Supply Scheme | SM/12766 | TSM/014263 |  | 40027626 | 6 | 2208 | 2570 | 2570 | 798.32 | 846.78 | Yes | 20/09/2022 | GO2223007988PH | MVS | PH222362549S000 | Administrative Approval Issued | N/A | Yes | 88.56 | Yes | 781.65 | 22/08/2022
17 | MALDAH | Malda Division | Ratua - I | 3rd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme | SM/07007 | TSM/006277 | SM/02326 | 8128361 | 3 | 2314 | 1583 | 1583 | 86.07 | 86.07 | Yes | 18/11/2020 | GO2021002539PH | MVS |  | Administrative Approval Issued | N/A | Yes | 71.72 | Yes | 57.81 | 25/09/2020
18 | MALDAH | Malda Division | Gazole | 6th (2022-2023) | New | DAHIL Piped Water Supply Scheme. | SM/18461 | TSM/015609 |  | 40034651 | 24 | 4455 | 4422 | 4422 | 1502.54 | 1594.44 | Yes | 20/07/2023 | 1963/PHE-28011/35/2023-ESTT CELL-Dept. of PHE | MVS | PH222364667S000 | Administrative Approval Issued | N/A | Yes | 139.78 | Yes | 1412.01 | 09/09/2022
19 | MALDAH | Malda Division | Gazole | 9th (2022-2023) | Augmentation | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | TSM/017388 | SM/00067 | 40046393 | 10 | 8526 | 9132 | 9132 | 3085.32 | 3085.32 | Yes | 31/07/2023 | 2140/PHE-28011/115/2023-ESTT CELL-Dept. of PHE | MVS | PH222371217S000 | Administrative Approval Issued | N/A | Yes | 577.4 | Yes | 2369.86 | 16/11/2022
20 | MALDAH | Malda Division | Bamangola | 8th (2021-2022) | Augmentation | Augmentation of Mirzapur Piped Water Supply Scheme | SM/10317 | TSM/009757 | SM/00063 | 40006926 | 7 | 4671 | 4880 | 4880 | 875.13 | 1029.67 | Yes | 04/03/2022 | GO2122010474PH | MVS | PH212249606S000 | Administrative Approval Issued | N/A | Yes | 942.79 | Yes | 940.12 | 27/01/2022
21 | MALDAH | Malda Division | Maldah (Old) | 9th (2022-2023) | New | KALUARI PWSS | SM/18427 | TSM/018421 |  | 40067330 | 9 | 4750 | 4790 | 4894 | 1366.3 | 1380.18 | Yes | 18/07/2023 | 1923/PHE-28011/146/2023-ESTT CELL-Dept. of PHE | MVS | PH222372420S000 | Administrative Approval Issued | N/A | Yes | 357.48 | Yes | 1194.09 | 16/11/2022
22 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | PARAHAR PWSS | SM/18432 | TSM/014116 |  | 40034621 | 22 | 3435 | 2983 | 2983 | 1277.12 | 1356.09 | Yes | 18/07/2023 | 1927/PHE-28011/77/2023-ESTT CELL-Dept. of PHE | MVS | PH222362550S000 | Administrative Approval Issued | N/A | Yes | 107.39 | Yes | 1246.45 | 22/08/2022
23 | MALDAH | Malda Division | Harischandrapur - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme | SM/06862 | TSM/005691 | SM/00828 | 8128323 | 1 | 1027 | 878 | 878 | 49.15 | 49.15 | Yes | 07/10/2020 | GO2021001809PH | SVS |  | Administrative Approval Issued | N/A | Yes | 37.29 | Yes | 37.29 | 28/08/2020
24 | MALDAH | Malda Division | Gazole | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme | SM/06850 | TSM/005681 | SM/03249 | 8128270 | 2 | 1483 | 1268 | 1268 | 68.82 | 68.82 | Yes | 07/10/2020 | GO2021001793PH | MVS |  | Administrative Approval Issued | N/A | Yes | 60.8 | Yes | 64.48 | 28/08/2020
25 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | TSM/012594 |  | 40027599 | 8 | 2557 | 2534 | 2534 | 654.95 | 753.45 | Yes | 07/09/2022 | GO2223007209PH | MVS | PH222363227S000 | Administrative Approval Issued | N/A | Yes | 3104.03 | Yes | 649.63 | 05/07/2022
26 | MALDAH | Malda Division | Gazole | 4th (2022-2023) | Augmentation | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | TSM/012799 | SM/03199 | 40026008 | 3 | 1527 | 0 | 0 | 131.81 | 131.81 | Yes | 09/09/2022 | GO2223007382PH | MVS | PH222362121S000 | Administrative Approval Issued | N/A | Yes | 52.5 | Yes | 111.31 | 15/07/2022
27 | MALDAH | Malda Division | Gazole | 3rd (2022-2023) | New | JIBJALSAR Piped Water Supply Scheme | SM/12182 | TSM/013490 |  | 40025737 | 1 | 134 | 146 | 146 | 69.34 | 73.06 | Yes | 07/09/2022 | GO2223007179PH | SVS | PH222361914S000 | Administrative Approval Issued | N/A | Yes | 80.31 | Yes | 67.21 | 05/07/2022
28 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | BETAHAL Piped Water Supply Scheme | SM/12191 | TSM/013024 |  | 40027592 | 4 | 1375 | 1550 | 1550 | 473.27 | 526.99 | Yes | 07/09/2022 | GO2223007227PH | MVS | PH222361954S000 | Administrative Approval Issued | N/A | Yes | 145.4 | Yes | 454.4 | 05/07/2022
29 | MALDAH | Malda Division | Maldah (Old) | 10th(2021-2022) | Augmentation | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | TSM/010498 | SM/00186 | 40016237 | 1 | 934 | 1133 | 1133 | 390.21 | 390.21 | Yes | 20/09/2022 | GO2223007987PH | SVS | PH222358773S000 | Administrative Approval Issued | N/A | Yes | 32.45 | Yes | 289.44 | 16/03/2022
30 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | PARO PWSS | SM/12195 | TSM/012960 |  | 40027596 | 6 | 2472 | 1995 | 1995 | 442.87 | 510.75 | Yes | 07/09/2022 | GO2223007217PH | MVS | PH222361958S000 | Administrative Approval Issued | N/A | Yes | 222.88 | Yes | 457.8 | 05/07/2022
31 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | MABARAKPUR PWSS | SM/12197 | TSM/012922 |  | 40027598 | 7 | 2061 | 2608 | 2608 | 614.73 | 704.22 | Yes | 07/09/2022 | GO2223007221PH | MVS | PH222361961S000 | Administrative Approval Issued | N/A | Yes | 2079.59 | Yes | 670.62 | 05/07/2022
32 | MALDAH | Malda Division | Ratua - I | 2nd (2022-2023) | Augmentation | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | TSM/011899 | SM/00168 | 40035086 | 11 | 4922 | 5251 | 5251 | 1983.76 | 2200.14 | Yes | 15/12/2022 | GO2223011013PH | MVS | PH222358765S000 | Administrative Approval Issued | N/A | Yes | 117.31 | Yes | 1362.59 | 20/05/2022
33 | MALDAH | Malda Division | Gazole | 8th (2022-2023) | New | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | TSM/013552 |  | 40034892 | 1 | 1084 | 1274 | 1274 | 440.06 | 447.97 | Yes | 20/01/2023 | GO2223012358PH | SVS | PH222366146S000 | Administrative Approval Issued | N/A | Yes | 88.01 | Yes | 389.12 | 30/09/2022
34 | MALDAH | Malda Division | Gazole | 9th (2022-2023) | Augmentation | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | TSM/015614 | SM/03518 | 40046394 | 3 | 3335 | 0 | 1251 | 261.08 | 261.08 | Yes | 04/02/2023 | GO2223013180PH | MVS | PH222371628S000 | Administrative Approval Issued | N/A | Yes | 266.73 | Yes | 228.96 | 16/11/2022
35 | MALDAH | Malda Division | Harischandrapur - I | 9th (2022-2023) | Augmentation | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | TSM/017129 | SM/02843 | 40044929 | 2 | 1746 | 0 | 0 | 102.52 | 102.52 | Yes | 04/02/2023 | GO2223013165PH | MVS | PH222371464S000 | Administrative Approval Issued | N/A | Yes | 173.1 | Yes | 87.86 | 16/11/2022
36 | MALDAH | Malda Division | Chanchal - I | 8th (2022-2023) | New | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | TSM/013453 |  | 40034904 | 8 | 2123 | 2416 | 2416 | 572.13 | 576.55 | Yes | 07/02/2023 | GO2223013452PH | MVS | PH222366147S000 | Administrative Approval Issued | N/A | Yes | 161.08 | Yes | 558.02 | 30/09/2022
37 | MALDAH | Malda Division | Habibpur | 9th (2022-2023) | Augmentation | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | TSM/016720 | SM/02846 | 40044189 | 2 | 1623 | 350 | 350 | 166.09 | 166.09 | Yes | 04/02/2023 | GO2223013168PH | MVS | PH222371376S000 | Administrative Approval Issued | N/A | Yes | 373.59 | Yes | 162.24 | 16/11/2022
38 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15065 | TSM/016724 | SM/03274 | 40044079 | 1 | 2633 | 0 | 0 | 216.09 | 216.09 | Yes | 04/02/2023 | GO2223013149PH | SVS | PH222371209S000 | Administrative Approval Issued | N/A | Yes | 316.1 | Yes | 199.72 | 16/11/2022
39 | MALDAH | Malda Division | Harischandrapur - I | 9th (2022-2023) | Augmentation | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | TSM/017205 | SM/02847 | 40046564 | 11 | 8665 | 0 | 0 | 116.57 | 116.57 | Yes | 04/02/2023 | GO2223013162PH | MVS | PH222371428S000 | Administrative Approval Issued | N/A | Yes | 181.19 | Yes | 93.75 | 16/11/2022
40 | MALDAH | Malda Division | Manikchak | 9th (2022-2023) | Augmentation | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | TSM/019390 | SM/00867 | 40046390 | 2 | 3760 | 420 | 420 | 961.22 | 988.47 | Yes | 06/02/2023 | GO2223013329PH | MVS | PH222371241S000 | Administrative Approval Issued | N/A | Yes | 296.05 | Yes | 780.22 | 16/11/2022
41 | MALDAH | Malda Division | Gazole | 10th(2022-2023) | Augmentation | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | TSM/011890 | SM/00181 | 40060389 | 1 | 554 | 649 | 649 | 355.78 | 355.78 | Yes | 22/02/2023 | GO2223014610PH | SVS | PH222371030S000 | Administrative Approval Issued | N/A | Yes | 590.75 | Yes | 337.34 | 28/12/2022
42 | MALDAH | Malda Division | Ratua - I | 2nd (2022-2023) | New | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | TSM/011274 |  | 40035016 | 5 | 3431 | 3332 | 3524 | 1023.19 | 1143.9 | Yes | 15/12/2022 | GO2223011019PH | MVS | PH222355431S000 | Administrative Approval Issued | N/A | Yes | 88.45 | Yes | 749.77 | 20/05/2022
43 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | Mahil Piped Water Supply Scheme | SM/13733 | TSM/014388 |  | 40034327 | 21 | 4213 | 4761 | 4895 | 1779.92 | 1895.5 | Yes | 17/11/2022 | GO2223009851PH | MVS | PH222362547S000 | Administrative Approval Issued | N/A | Yes | 76.6 | Yes | 1755.22 | 22/08/2022
44 | MALDAH | Malda Division | Maldah (Old) | 1st(2022-2023) | New | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | TSM/011706 |  | 40014620 | 7 | 922 | 749 | 822 | 342.88 | 380.75 | Yes | 12/09/2022 | GO2223007479PH | MVS | PH222355772S000 | Administrative Approval Issued | N/A | Yes | 296.09 | Yes | 300.82 | 25/04/2022
45 | MALDAH | Malda Division | Maldah (Old) | 5th (2022-2023) | Augmentation | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | TSM/014744 | SM/03662 | 40026213 | 8 | 1026 | 0 | 364 | 282.13 | 295.68 | Yes | 20/09/2022 | GO2223007983PH | MVS | PH222362542S000 | Administrative Approval Issued | N/A | Yes | 200.25 | Yes | 265.77 | 22/08/2022
46 | MALDAH | Malda Division | Gazole | 2nd (2022-2023) | New | Alal Zone-I Piped Water Supply Scheme | SM/12075 | TSM/011887 |  | 40028430 | 7 | 4739 | 1971 | 1971 | 732.76 | 732.76 | Yes | 02/09/2022 | GO2223007012PH | MVS | PH222355426S000 | Administrative Approval Issued | N/A | Yes | 158.73 | Yes | 665.72 | 20/05/2022
47 | MALDAH | Malda Division | Maldah (Old) | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | SM/06856 | TSM/005685 | SM/02899 | 8128314 | 2 | 1894 | 1616 | 1616 | 86.33 | 86.33 | Yes | 07/10/2020 | GO2021001801PH | MVS |  | Administrative Approval Issued | N/A | Yes | 27.77 | Yes | 82.36 | 28/08/2020
48 | MALDAH | Malda Division | Chanchal - I | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | SM/06859 | TSM/005688 | SM/03931 | 5344418 | 3 | 1294 | 1321 | 1321 | 71.47 | 71.47 | Yes | 07/10/2020 | GO2021001806PH | MVS |  | Administrative Approval Issued | N/A | Yes | 56.96 | Yes | 69.39 | 28/08/2020
49 | MALDAH | Malda Division | Harischandrapur - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | SM/06868 | TSM/005697 | SM/02844 | 8128345 | 1 | 1312 | 1122 | 1122 | 61.47 | 61.47 | Yes | 08/10/2020 | GO2021001829PH | SVS |  | Administrative Approval Issued | N/A | Yes | 54.58 | Yes | 87.69 | 28/08/2020
50 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | TSM/013445 |  | 40027586 | 1 | 1456 | 781 | 1378 | 273.29 | 291.47 | Yes | 07/09/2022 | GO2223007178PH | SVS | PH222361918S000 | Administrative Approval Issued | N/A | Yes | 63.1 | Yes | 257.41 | 05/07/2022
51 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | Sharanpur Piped Water Supply Scheme | SM/12631 | TSM/013210 |  | 40027622 | 3 | 1831 | 1080 | 1080 | 345.19 | 383.2 | Yes | 19/09/2022 | GO2223007806PH | MVS | PH222361951S000 | Administrative Approval Issued | N/A | Yes | 293.9 | Yes | 365.47 | 05/07/2022
52 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | TSM/012833 |  | 40027621 | 2 | 672 | 698 | 698 | 293.04 | 335.31 | Yes | 19/09/2022 | GO2223007805PH | MVS | PH222361962S000 | Administrative Approval Issued | N/A | Yes | 236.3 | Yes | 291.12 | 05/07/2022
53 | MALDAH | Malda Division | Maldah (Old) | 11th(2021-2022) | New | Sahapur Piped Water Supply Scheme | SM/11968 | TSM/010990 |  | 40016201 | 6 | 6134 | 7669 | 7669 | 1135.04 | 1135.04 | Yes | 26/08/2022 | GO2223006721PH | MVS | PH222358777S000 | Administrative Approval Issued | N/A | Yes | 168.84 | Yes | 1106.94 | 30/03/2022
54 | MALDAH | Malda Division | Harischandrapur - I | 5th (2022-2023) | New | BAIRAT Piped Water Supply Scheme | SM/12743 | TSM/014439 |  | 40027623 | 8 | 2957 | 3235 | 3235 | 884.02 | 939.2 | Yes | 20/09/2022 | GO2223007978PH | MVS | PH222361968S000 | Administrative Approval Issued | N/A | Yes | 80 | Yes | 901.31 | 22/08/2022
55 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | BANGRUA PWSS | SM/12193 | TSM/013018 |  | 40027594 | 1 | 2256 | 900 | 900 | 265.83 | 300.09 | Yes | 07/09/2022 | GO2223007215PH | SVS | PH222361956S000 | Administrative Approval Issued | N/A | Yes | 60.47 | Yes | 239.57 | 05/07/2022
56 | MALDAH | Malda Division | Chanchal - I | 5th (2022-2023) | New | MATIHARPUR Piped Water Supply Scheme | SM/12769 | TSM/013447 |  | 40027629 | 9 | 3554 | 3531 | 3531 | 929.69 | 994.01 | Yes | 20/09/2022 | GO2223007982PH | MVS | PH222362558S000 | Administrative Approval Issued | N/A | Yes | 175.67 | Yes | 844.06 | 22/08/2022
57 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | TSM/014505 |  | 40034171 | 19 | 3393 | 3632 | 3632 | 1386.39 | 1484.54 | Yes | 17/11/2022 | GO2223009855PH | MVS | PH222361967S000 | Administrative Approval Issued | N/A | Yes | 89.31 | Yes | 1368.73 | 22/08/2022
58 | MALDAH | Malda Division | Ratua - I | 2nd (2022-2023) | New | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | TSM/011269 |  | 40035007 | 5 | 5131 | 4488 | 4588 | 1429.91 | 1578.1 | Yes | 15/12/2022 | GO2223011018PH | MVS | PH222355432S000 | Administrative Approval Issued | N/A | Yes | 402.8 | Yes | 1097.34 | 20/05/2022
59 | MALDAH | Malda Division | Ratua - II | 2nd (2022-2023) | New | Pukuria Piped Water Supply Scheme | SM/14100 | TSM/011879 |  | 40035034 | 1 | 5210 | 5771 | 5771 | 1716.45 | 1884.19 | Yes | 15/12/2022 | GO2223011014PH | SVS | PH222358768S000 | Administrative Approval Issued | N/A | Yes | 265.48 | Yes | 1185.03 | 20/05/2022
60 | MALDAH | Malda Division | Gazole | 6th (2022-2023) | New | JIGIN Piped Water Supply Scheme | SM/13430 | TSM/015837 |  | 40033792 | 1 | 406 | 459 | 459 | 213.28 | 234.18 | Yes | 02/11/2022 | GO2223009237PH | SVS | PH222364658S000 | Administrative Approval Issued | N/A | Yes | 65.98 | Yes | 175.41 | 09/09/2022
61 | MALDAH | Malda Division | Ratua - I | 9th (2022-2023) | Augmentation | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15057 | TSM/017203 | SM/01531 | 40046495 | 1 | 1591 | 0 | 0 | 64.27 | 64.27 | Yes | 04/02/2023 | GO2223013145PH | SVS | PH222371091S000 | Administrative Approval Issued | N/A | Yes | 34.98 | Yes | 29.04 | 16/11/2022
62 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | TSM/016722 | SM/02976 | 40044420 | 2 | 1201 | 0 | 0 | 83.83 | 83.83 | Yes | 04/02/2023 | GO2223013183PH | MVS | PH222371297S000 | Administrative Approval Issued | N/A | Yes | 57.97 | Yes | 79.98 | 16/11/2022
63 | MALDAH | Malda Division | Habibpur | 9th (2022-2023) | Augmentation | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | TSM/017676 | SM/00162 | 40046989 | 1 | 1337 | 1413 | 1413 | 398.39 | 398.39 | Yes | 07/02/2023 | GO2223013408PH | SVS | PH222370774S000 | Administrative Approval Issued | N/A | Yes | 460.75 | Yes | 314.97 | 16/11/2022
64 | MALDAH | Malda Division | Bamangola | 9th (2022-2023) | Augmentation | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | SM/15197 | TSM/017379 | SM/02964 | 40046499 | 18 | 5622 | 0 | 0 | 164.65 | 164.65 | Yes | 06/02/2023 | GO2223013325PH | MVS | PH222371449S000 | Administrative Approval Issued | N/A | Yes | 291.45 | Yes | 163.41 | 16/11/2022
65 | MALDAH | Malda Division | Manikchak | 9th (2022-2023) | Augmentation | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | TSM/019387 | SM/00867 | 40046992 | 1 | 5516 | 500 | 500 | 989.61 | 1030.99 | Yes | 28/02/2023 | GO2223015021PH | SVS | PH222370681S000 | Administrative Approval Issued | N/A | Yes | 235.63 | Yes | 903.74 | 16/11/2022
66 | MALDAH | Malda Division | Harischandrapur - I | 10th(2022-2023) | Augmentation | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | TSM/017675 | SM/00184 | 40060438 | 1 | 290 | 733 | 733 | 254.87 | 254.87 | Yes | 22/02/2023 | GO2223014619PH | SVS | PH222370941S000 | Administrative Approval Issued | N/A | Yes | 443.48 | Yes | 237.13 | 28/12/2022
67 | MALDAH | Malda Division | Gazole | 10th(2022-2023) | Augmentation | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | TSM/011889 | SM/00181 | 40060336 | 1 | 554 | 972 | 972 | 543.44 | 543.44 | Yes | 22/02/2023 | GO2223014624PH | SVS | PH222371039S000 | Administrative Approval Issued | N/A | Yes | 62.63 | Yes | 445.5 | 28/12/2022
68 | MALDAH | Malda Division | Ratua - I | 10th(2021-2022) | Augmentation | Augmentation of Samsi PWSS. | SM/18447 | TSM/008164 | SM/00174 | 40016238 | 7 | 6612 | 6805 | 6805 | 2165.6 | 2234.04 | Yes | 20/07/2023 | 1959/PHE-28011/7/2023-ESTT CELL-Dept. of PHE | MVS | PH222359282S000 | Administrative Approval Issued | N/A | Yes | 216.33 | Yes | 1289.87 | 16/03/2022
69 | MALDAH | Malda Division | Gazole | 10th(2022-2023) | New | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | TSM/020336 |  | 40057544 | 8 | 2173 | 2677 | 2677 | 1232.77 | 1232.77 | Yes | 26/07/2023 | 2035/PHE-28011/210/2023-ESTT CELL-Dept. of PHE | MVS | PH222371015S000 | Administrative Approval Issued | N/A | Yes | 309.3 | Yes | 979.94 | 28/12/2022
70 | MALDAH | Malda Division | Gazole | 6th (2022-2023) | New | RAHIMPUR Piped Water Supply Scheme | SM/14174 | TSM/015255 |  | 40034867 | 22 | 2081 | 2638 | 2638 | 1018.51 | 1077.41 | Yes | 09/01/2023 | GO2223011642PH | MVS | PH222364668S000 | Administrative Approval Issued | N/A | Yes | 123.13 | Yes | 1018.54 | 09/09/2022
71 | MALDAH | Malda Division | Gazole | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme | SM/06852 | TSM/005680 | SM/03199 | 8128272 | 4 | 1852 | 1707 | 1707 | 90.94 | 102.95 | Yes | 07/10/2020 | GO2021001797PH | MVS |  | Administrative Approval Issued | N/A | Yes | 60.69 | Yes | 102.74 | 28/08/2020
72 | MALDAH | Malda Division | Chanchal - I | 5th (2022-2023) | New | NABAGRAM Piped Water Supply Scheme | SM/12767 | TSM/013452 |  | 40027627 | 3 | 3526 | 3517 | 3517 | 825.74 | 876.56 | Yes | 20/09/2022 | GO2223007991PH | MVS | PH222362552S000 | Administrative Approval Issued | N/A | Yes | 233.41 | Yes | 826.3 | 22/08/2022
73 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | PARAIL PWSS | SM/18431 | TSM/014391 |  | 40034640 | 15 | 2246 | 3263 | 3263 | 1203.22 | 1276.14 | Yes | 18/07/2023 | 1927/PHE-28011/77/2023-ESTT CELL-Dept. of PHE | MVS | PH222362554S000 | Administrative Approval Issued | N/A | Yes | 154.93 | Yes | 1195.52 | 22/08/2022
74 | MALDAH | Malda Division | Harischandrapur - II | 11th(2022-2023) | Augmentation | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18910 | TSM/020578 | SM/05332 | 40067381 | 6 | 2557 | 0 | 0 | 133.47 | 133.47 | Yes | 09/10/2023 | PHE/IV/3073/W-668/23 | MVS |  | Administrative Approval Issued | N/A | Yes | 294.26 | Yes | 131.79 | 10/03/2023
75 | MALDAH | Malda Division | Manikchak | 9th (2022-2023) | Augmentation | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | TSM/019389 | SM/00867 | 40046995 | 1 | 2520 | 340 | 340 | 853.57 | 879.54 | Yes | 10/02/2023 | GO2223013471PH | SVS | PH222372866S000 | Administrative Approval Issued | N/A | Yes | 124.51 | Yes | 725.45 | 16/11/2022
76 | MALDAH | Malda Division | Habibpur | 4th (2022-2023) | Augmentation | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | TSM/012801 | SM/02901 | 40026210 | 2 | 251 | 0 | 0 | 156.56 | 174.73 | Yes | 09/09/2022 | GO2223007376PH | MVS | PH222362124S000 | Administrative Approval Issued | N/A | Yes | 21.51 | Yes | 155.51 | 15/07/2022
77 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | SM/07973 | TSM/006282 | SM/00067 | 8203350 | 155 | 102673 | 110722 | 110880 | 5777.65 | 5777.65 | Yes | 26/01/2021 | GO2021005524PH | MVS |  | Administrative Approval Issued | N/A | Yes | 6794.89 | Yes | 3316.96 | 25/09/2020
78 | MALDAH | Malda Division | Habibpur | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | SM/06863 | TSM/005692 | SM/02886 | 8128325 | 4 | 784 | 991 | 991 | 54.86 | 54.86 | Yes | 07/10/2020 | GO2021001818PH | MVS |  | Administrative Approval Issued | N/A | Yes | 52.16 | Yes | 36.7 | 28/08/2020
79 | MALDAH | Malda Division | Harischandrapur - II | 7th (2021-2022) | Augmentation | Augmentation of Bhaluka Fatepur Piped water supply scheme | SM/10137 | TSM/009046 | SM/00172 | 40002522 | 2 | 4192 | 4734 | 4734 | 944.43 | 1077.25 | Yes | 08/02/2022 | GO2122009354PH | MVS | PH212248316S000 | Administrative Approval Issued | N/A | Yes | 748.22 | Yes | 1008.21 | 16/12/2021
80 | MALDAH | Malda Division | Gazole | 6th (2021-2022) | Augmentation | Augmentation of Deotala Water Supply Scheme | SM/09986 | TSM/005108 | SM/00163 | 40006366 | 4 | 1172 | 2446 | 2446 | 842.06 | 842.06 | Yes | 16/12/2021 | GO2122006954PH | MVS | PH212246552S000 | Administrative Approval Issued | N/A | Yes | 124.81 | Yes | 607.35 | 22/11/2021
81 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | SAHAPUR Piped Water Supply Scheme | SM/12187 | TSM/013245 |  | 40022366 | 1 | 331 | 397 | 397 | 104.61 | 112.27 | Yes | 06/09/2022 | GO2223007120PH | SVS | PH222361926S000 | Administrative Approval Issued | N/A | Yes | 173.2 | Yes | 121.74 | 05/07/2022
82 | MALDAH | Malda Division | Gazole | 4th (2022-2023) | Augmentation | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | TSM/012798 | SM/03250 | 40027816 | 3 | 2955 | 0 | 1008 | 132.82 | 145.33 | Yes | 09/09/2022 | GO2223007375PH | MVS | PH222362122S000 | Administrative Approval Issued | N/A | Yes | 62.27 | Yes | 113.95 | 15/07/2022
83 | MALDAH | Malda Division | Gazole | 4th (2022-2023) | Augmentation | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | TSM/014339 | SM/03975 | 40026137 | 2 | 1922 | 1275 | 1275 | 268.41 | 281.18 | Yes | 09/09/2022 | GO2223007377PH | MVS | PH222362126S000 | Administrative Approval Issued | N/A | Yes | 147.34 | Yes | 190.62 | 15/07/2022
84 | MALDAH | Malda Division | Habibpur | 3rd (2022-2023) | New | JAMALPUR Piped Water Supply Scheme. | SM/12879 | TSM/013493 |  | 40027632 | 22 | 2759 | 4212 | 4212 | 988.74 | 1047.18 | Yes | 23/09/2022 | GO2223008164PH | MVS | PH222361907S000 | Administrative Approval Issued | N/A | Yes | 204.62 | Yes | 991.3 | 05/07/2022
85 | MALDAH | Malda Division | Habibpur | 4th (2022-2023) | Augmentation | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | TSM/014342 | SM/02848 | 40026037 | 3 | 477 | 1748 | 1748 | 167.81 | 167.81 | Yes | 09/09/2022 | GO2223007381PH | MVS | PH222362125S000 | Administrative Approval Issued | N/A | Yes | 63.89 | Yes | 148.06 | 15/07/2022
86 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | TSM/014431 |  | 40034322 | 7 | 2927 | 2846 | 2846 | 1066.35 | 1128.57 | Yes | 17/11/2022 | GO2223009854PH | MVS | PH222361971S000 | Administrative Approval Issued | N/A | Yes | 104 | Yes | 1006.21 | 22/08/2022
87 | MALDAH | Malda Division | Harischandrapur - I | 6th (2022-2023) | New | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | TSM/014466 |  | 40033760 | 7 | 2921 | 2698 | 2698 | 637.86 | 682.77 | Yes | 02/11/2022 | GO2223009206PH | MVS | PH222364671S000 | Administrative Approval Issued | N/A | Yes | 431.46 | Yes | 657.78 | 09/09/2022
88 | MALDAH | Malda Division | Maldah (Old) | 9th (2022-2023) | Augmentation | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | TSM/016470 | SM/02746 | 40045479 | 3 | 3357 | 0 | 0 | 104.31 | 104.31 | Yes | 04/02/2023 | GO2223013157PH | MVS | PH222371574S000 | Administrative Approval Issued | N/A | Yes | 200.68 | Yes | 89.42 | 16/11/2022
89 | MALDAH | Malda Division | English Bazar | 9th (2022-2023) | Augmentation | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | TSM/016471 | SM/02719 | 40046081 | 2 | 836 | 150 | 150 | 100.43 | 100.43 | Yes | 04/02/2023 | GO2223013190PH | MVS | PH222371594S000 | Administrative Approval Issued | N/A | Yes | 89.32 | Yes | 95.43 | 16/11/2022
90 | MALDAH | Malda Division | Gazole | 6th (2022-2023) | New | FATEPUR Piped Water Supply Scheme | SM/14173 | TSM/015785 |  | 40034658 | 19 | 3913 | 4277 | 4277 | 1472.95 | 1581.73 | Yes | 09/01/2023 | GO2223011641PH | MVS | PH222364661S000 | Administrative Approval Issued | N/A | Yes | 139.11 | Yes | 1488.09 | 09/09/2022
91 | MALDAH | Malda Division | Gazole | 8th (2022-2023) | New | DILALBATI Piped Water Supply Scheme. | SM/15903 | TSM/014129 |  | 40034885 | 1 | 355 | 521 | 521 | 289.35 | 292.15 | Yes | 20/02/2023 | GO2223014285PH | SVS | PH222366145S000 | Administrative Approval Issued | N/A | Yes | 65.35 | Yes | 231.89 | 30/09/2022
92 | MALDAH | Malda Division | Gazole | 10th(2022-2023) | Augmentation | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | TSM/011885 | SM/00169 | 40060303 | 4 | 1008 | 683 | 1052 | 425.25 | 425.25 | Yes | 22/02/2023 | GO2223014608PH | MVS | PH222370997S000 | Administrative Approval Issued | N/A | Yes | 58.71 | Yes | 386.18 | 28/12/2022
93 | MALDAH | Malda Division | Ratua - I | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme | SM/06865 | TSM/005694 | SM/01535 | 8128336 | 1 | 895 | 770 | 770 | 43.73 | 43.73 | Yes | 07/10/2020 | GO2021001820PH | MVS |  | Administrative Approval Issued | N/A | Yes | 28.66 | Yes | 43.58 | 28/08/2020
94 | MALDAH | Malda Division | Chanchal - I | 3rd (2022-2023) | New | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | TSM/013253 |  | 40027587 | 12 | 3116 | 2967 | 2967 | 761.34 | 834.65 | Yes | 07/09/2022 | GO2223007177PH | MVS | PH222361920S000 | Administrative Approval Issued | N/A | Yes | 2473.04 | Yes | 772.52 | 05/07/2022
95 | MALDAH | Malda Division | Harischandrapur - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | SM/06858 | TSM/005687 | SM/02975 | 8128318 | 2 | 1999 | 1084 | 1084 | 59.54 | 59.54 | Yes | 07/10/2020 | GO2021001804PH | MVS |  | Administrative Approval Issued | N/A | Yes | 51.09 | Yes | 81.09 | 28/08/2020
96 | MALDAH | Malda Division | English Bazar | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | SM/06871 | TSM/005700 | SM/02719 | 8128350 | 4 | 1498 | 975 | 975 | 54.06 | 54.06 | Yes | 08/10/2020 | GO2021001832PH | MVS |  | Administrative Approval Issued | N/A | Yes | 54.82 | Yes | 50.94 | 28/08/2020
97 | MALDAH | Malda Division | Bamangola | 7th (2021-2022) | Augmentation | Augmentation of Bamongram piped water supply scheme. | SM/10138 | TSM/008160 | SM/00062 | 40002521 | 9 | 2655 | 3044 | 3481 | 879.05 | 1038.64 | Yes | 08/02/2022 | GO2122009361PH | MVS | PH212248321S000 | Administrative Approval Issued | N/A | Yes | 86.46 | Yes | 887.39 | 16/12/2021
98 | MALDAH | Malda Division | Habibpur | 4th (2022-2023) | New | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | TSM/013454 |  | 40027600 | 29 | 1533 | 1823 | 1823 | 567.57 | 602.34 | Yes | 09/09/2022 | GO2223007384PH | MVS | PH222361965S000 | Administrative Approval Issued | N/A | Yes | 317.46 | Yes | 549.18 | 15/07/2022
99 | MALDAH | Malda Division | Maldah (Old) | 4th (2022-2023) | Augmentation | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | TSM/012800 | SM/03514 | 40026104 | 6 | 857 | 1504 | 1504 | 305.67 | 335.27 | Yes | 09/09/2022 | GO2223007383PH | MVS | PH222362120S000 | Administrative Approval Issued | N/A | Yes | 177.27 | Yes | 313.07 | 15/07/2022
100 | MALDAH | Malda Division | Harischandrapur - I | 11th(2021-2022) | New | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | TSM/011266 |  | 40016191 | 3 | 2527 | 2789 | 2789 | 554.79 | 609.28 | Yes | 22/07/2022 | GO2223005416PH | MVS | PH222358775S000 | Administrative Approval Issued | N/A | Yes | 125.66 | Yes | 393.3 | 30/03/2022
101 | MALDAH | Malda Division | Harischandrapur - I | 2nd (2022-2023) | New | Choupaldanga pipe water Supply Scheme | SM/12076 | TSM/011833 |  | 40022361 | 10 | 2217 | 3482 | 3482 | 790.19 | 902.87 | Yes | 02/09/2022 | GO2223007013PH | MVS | PH222355427S000 | Administrative Approval Issued | N/A | Yes | 208.55 | Yes | 845.45 | 20/05/2022
102 | MALDAH | Malda Division | Habibpur | 4th (2022-2023) | Augmentation | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | TSM/014344 | SM/03201 | 40026113 | 4 | 757 | 1906 | 1906 | 172.5 | 180.45 | Yes | 09/09/2022 | GO2223007380PH | MVS | PH222362545S000 | Administrative Approval Issued | N/A | Yes | 59.31 | Yes | 128.89 | 15/07/2022
103 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | MALIOR PWSS | SM/12192 | TSM/013022 |  | 40027593 | 3 | 2411 | 2789 | 2789 | 651.07 | 718.85 | Yes | 07/09/2022 | GO2223007214PH | MVS | PH222361955S000 | Administrative Approval Issued | N/A | Yes | 1690.07 | Yes | 704.23 | 05/07/2022
104 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | TSM/016549 | SM/03114 | 40046091 | 3 | 1090 | 0 | 0 | 212.37 | 212.37 | Yes | 04/02/2023 | GO2223013153PH | MVS | PH222371582S000 | Administrative Approval Issued | N/A | Yes | 389.03 | Yes | 200.07 | 16/11/2022
105 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15073 | TSM/016694 | SM/02975 | 40044299 | 2 | 1999 | 0 | 0 | 96.31 | 96.31 | Yes | 04/02/2023 | GO2223013144PH | MVS | PH222371262S000 | Administrative Approval Issued | N/A | Yes | 66.69 | Yes | 92.64 | 16/11/2022
106 | MALDAH | Malda Division | Maldah (Old) | 9th (2022-2023) | Augmentation | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | TSM/016719 | SM/02841 | 40044271 | 2 | 1448 | 0 | 0 | 213.72 | 213.72 | Yes | 04/02/2023 | GO2223013171PH | MVS | PH222371391S000 | Administrative Approval Issued | N/A | Yes | 165.27 | Yes | 158.35 | 16/11/2022
107 | MALDAH | Malda Division | Chanchal - II | 11th(2021-2022) | New | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | TSM/011258 |  | 40016168 | 8 | 5842 | 8288 | 8288 | 2175.5 | 2486.52 | Yes | 07/02/2023 | GO2223013361PH | MVS | PH222358776S000 | Administrative Approval Issued | N/A | Yes | 163.84 | Yes | 1783.43 | 30/03/2022
108 | MALDAH | Malda Division | Manikchak | 10th(2022-2023) | Augmentation | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | TSM/019385 | SM/00867 | 40060451 | 1 | 5516 | 125 | 125 | 600.59 | 620.93 | Yes | 22/02/2023 | GO2223014612PH | SVS | PH222372067S000 | Administrative Approval Issued | N/A | Yes | 355.96 | Yes | 463.77 | 28/12/2022
109 | MALDAH | Malda Division | Maldah (Old) | 10th(2022-2023) | New | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | TSM/018437 |  | 40057341 | 7 | 1086 | 1287 | 1287 | 579.04 | 586.08 | Yes | 22/02/2023 | GO2223014615PH | MVS | PH222371058S000 | Administrative Approval Issued | N/A | Yes | 130.3 | Yes | 563.73 | 28/12/2022
110 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | BABUPUR PWSS | SM/18433 | TSM/014434 |  | 40034236 | 27 | 5350 | 5617 | 5617 | 1594.57 | 1697.39 | Yes | 18/07/2023 | 1928/PHE-28011/188/2023-SCHM CELL-Dept. of PHE | MVS | PH222361970S000 | Administrative Approval Issued | N/A | Yes | 105.72 | Yes | 1549.94 | 22/08/2022
111 | MALDAH | Malda Division | Habibpur | 6th (2022-2023) | New | HORGOA Piped Water Supply Scheme | SM/13432 | TSM/015215 |  | 40033798 | 14 | 1571 | 1714 | 1714 | 643.41 | 684.91 | Yes | 02/11/2022 | GO2223009244PH | MVS | PH222364669S000 | Administrative Approval Issued | N/A | Yes | 239.47 | Yes | 678.95 | 09/09/2022
112 | MALDAH | Malda Division | Chanchal - I | 2nd (2022-2023) | New | Hatinda Piped Water Supply Scheme. | SM/12078 | TSM/011729 |  | 40015010 | 7 | 4700 | 4783 | 4783 | 959.77 | 1095.36 | Yes | 02/09/2022 | GO2223007014PH | MVS | PH222358770S000 | Administrative Approval Issued | N/A | Yes | 200.2 | Yes | 962.8 | 20/05/2022
113 | MALDAH | Malda Division | Habibpur | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme | SM/06857 | TSM/005686 | SM/03072 | 8128316 | 8 | 2018 | 1722 | 1722 | 91.69 | 91.69 | Yes | 07/10/2020 | GO2021001802PH | MVS |  | Administrative Approval Issued | N/A | Yes | 6.91 | Yes | 58.57 | 28/08/2020
114 | MALDAH | Malda Division | Habibpur | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | SM/06867 | TSM/005696 | SM/02848 | 8128342 | 10 | 1809 | 1748 | 1748 | 92.99 | 92.99 | Yes | 07/10/2020 | GO2021001822PH | MVS |  | Administrative Approval Issued | N/A | Yes | 9.23 | Yes | 75.72 | 28/08/2020
115 | MALDAH | Malda Division | Chanchal - I | 2nd (2022-2023) | New | GAURIA Piped Water Supply Scheme. | SM/12079 | TSM/011717 |  | 40022291 | 7 | 5822 | 4278 | 4278 | 916.6 | 1006.53 | Yes | 02/09/2022 | GO2223007015PH | MVS | PH222358771S000 | Administrative Approval Issued | N/A | Yes | 172.65 | Yes | 831.08 | 20/05/2022
116 | MALDAH | Malda Division | Harischandrapur - I | 2nd (2022-2023) | New | WARI Piped Water Supply Scheme | SM/12077 | TSM/011955 |  | 40022273 | 11 | 4133 | 3903 | 3903 | 944.1 | 1077.41 | Yes | 02/09/2022 | GO2223007011PH | MVS | PH222358767S000 | Administrative Approval Issued | N/A | Yes | 288.37 | Yes | 1029.77 | 20/05/2022
117 | MALDAH | Malda Division | Habibpur | 6th (2022-2023) | New | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | TSM/013458 |  | 40034839 | 41 | 2238 | 2560 | 2560 | 832.12 | 880.68 | Yes | 17/11/2022 | GO2223009833PH | MVS | PH222364670S000 | Administrative Approval Issued | N/A | Yes | 175.05 | Yes | 869.15 | 09/09/2022
118 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | BHADAR Piped Water Supply Scheme | SM/12768 | TSM/014278 |  | 40027628 | 15 | 2384 | 2064 | 2200 | 621.21 | 660.39 | Yes | 20/09/2022 | GO2223007979PH | MVS | PH222362556S000 | Administrative Approval Issued | N/A | Yes | 234.36 | Yes | 581.76 | 22/08/2022
119 | MALDAH | Malda Division | Harischandrapur - I | 5th (2022-2023) | New | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | TSM/014411 |  | 40027624 | 4 | 3070 | 2782 | 2782 | 656.15 | 703.14 | Yes | 20/09/2022 | GO2223007989PH | MVS | PH222362546S000 | Administrative Approval Issued | N/A | Yes | 219.99 | Yes | 667.02 | 22/08/2022
120 | MALDAH | Malda Division | Gazole | 5th (2022-2023) | New | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | TSM/014266 |  | 40027625 | 5 | 1011 | 919 | 919 | 377.31 | 403.76 | Yes | 20/09/2022 | GO2223007990PH | MVS | PH222362548S000 | Administrative Approval Issued | N/A | Yes | 145.36 | Yes | 373.45 | 22/08/2022
121 | MALDAH | Malda Division | Habibpur | 3rd (2022-2023) | New | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | TSM/013242 |  | 40033946 | 26 | 3171 | 3535 | 3535 | 1147.12 | 1253.79 | Yes | 17/11/2022 | GO2223009859PH | MVS | PH222361946S000 | Administrative Approval Issued | N/A | Yes | 200.54 | Yes | 1183.1 | 05/07/2022
122 | MALDAH | Malda Division | Habibpur | 5th (2022-2023) | Augmentation | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | TSM/014864 | SM/03160 | 40026212 | 4 | 815 | 500 | 736 | 142.91 | 149.78 | Yes | 20/09/2022 | GO2223007977PH | MVS | PH222362543S000 | Administrative Approval Issued | N/A | Yes | 89.23 | Yes | 138.45 | 22/08/2022
123 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | UTTAR BHAKURIA Piped Water Supply Scheme. | SM/12881 | TSM/013230 |  | 40027631 | 1 | 213 | 215 | 215 | 80.18 | 86.24 | Yes | 23/09/2022 | GO2223008163PH | SVS | PH222361948S000 | Administrative Approval Issued | N/A | Yes | 49.99 | Yes | 67.73 | 05/07/2022
124 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | TSM/016501 | SM/03917 | 40046308 | 3 | 999 | 0 | 0 | 84.77 | 84.77 | Yes | 04/02/2023 | GO2223013182PH | MVS | PH222371618S000 | Administrative Approval Issued | N/A | Yes | 69.33 | Yes | 64.66 | 16/11/2022
125 | MALDAH | Malda Division | English Bazar | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | SM/06853 | TSM/005682 | SM/02713 | 8128274 | 2 | 1371 | 1125 | 1125 | 61.62 | 61.62 | Yes | 07/10/2020 | GO2021001798PH | MVS |  | Administrative Approval Issued | N/A | Yes | 56.25 | Yes | 58.95 | 28/08/2020
126 | MALDAH | Malda Division | Chanchal - II | 9th (2022-2023) | Augmentation | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | TSM/016552 | SM/03912 | 40044072 | 1 | 1150 | 0 | 0 | 93.1 | 93.1 | Yes | 04/02/2023 | GO2223013185PH | SVS | PH222371192S000 | Administrative Approval Issued | N/A | Yes | 136.18 | Yes | 62.19 | 16/11/2022
127 | MALDAH | Malda Division | Ratua - I | 9th (2022-2023) | Augmentation | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15083 | TSM/016679 | SM/02326 | 40044393 | 2 | 1739 | 0 | 0 | 75.97 | 75.97 | Yes | 04/02/2023 | GO2223013141PH | MVS | PH222371406S000 | Administrative Approval Issued | N/A | Yes | 18.52 | Yes | 67.72 | 16/11/2022
128 | MALDAH | Malda Division | English Bazar | 10th(2021-2022) | Augmentation | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | TSM/008179 | SM/00180 | 40016240 | 2 | 195 | 1245 | 1245 | 498.84 | 546.57 | Yes | 10/01/2023 | GO2223011796PH | MVS | PH222359281S000 | Administrative Approval Issued | N/A | Yes | 36.84 | Yes | 297.04 | 16/03/2022
129 | MALDAH | Malda Division | Maldah (Old) | 9th (2022-2023) | Augmentation | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | TSM/017802 | SM/00179 | 40046986 | 2 | 1364 | 1464 | 1587 | 328.05 | 328.05 | Yes | 28/02/2023 | GO2223015020PH | SVS | PH222370682S000 | Administrative Approval Issued | N/A | Yes | 701.96 | Yes | 149.39 | 16/11/2022
130 | MALDAH | Malda Division | Chanchal - II | 10th(2022-2023) | New | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | TSM/018373 |  | 40065428 | 235 | 156404 | 56048 | 56048 | 68069.12 | 68069.12 | Yes | 04/08/2023 | 2246/PHE-28011/113/2023-SCHM CELL-Dept. of PHE | MVS | PH222370829S000 | Administrative Approval Issued | N/A | Yes | 21977.53 | Yes | 66060.31 | 28/12/2022
131 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | SM/07972 | TSM/006280 | SM/03160 | 8203410 | 94 | 47749 | 47621 | 47698 | 2518.77 | 2518.77 | Yes | 26/01/2021 | GO2021005525PH | MVS |  | Administrative Approval Issued | N/A | Yes | 1062.58 | Yes | 2326.77 | 25/09/2020
132 | MALDAH | Malda Division | Gazole | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme | SM/06851 | TSM/005679 | SM/03206 | 8128247 | 3 | 3027 | 1811 | 1811 | 96.17 | 96.17 | Yes | 07/10/2020 | GO2021001792PH | MVS |  | Administrative Approval Issued | N/A | Yes | 42.84 | Yes | 93.35 | 28/08/2020
133 | MALDAH | Malda Division | Harischandrapur - II | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | SM/06854 | TSM/005683 | SM/02976 | 8128280 | 5 | 2344 | 1580 | 1580 | 84.53 | 84.53 | Yes | 07/10/2020 | GO2021001799PH | MVS |  | Administrative Approval Issued | N/A | Yes | 24.34 | Yes | 125.95 | 28/08/2020
134 | MALDAH | Malda Division | Habibpur | 5th (2021-2022) | Augmentation | Augmentation of Tilasan Piped water supply scheme | SM/09567 | TSM/009047 | SM/00167 | 40002169 | 3 | 1558 | 1568 | 1568 | 331.85 | 331.85 | Yes | 22/11/2021 | GO2122005685PH | MVS | PH212245452S000 | Administrative Approval Issued | N/A | Yes | 21.04 | Yes | 259.21 | 08/10/2021
135 | MALDAH | Malda Division | Harischandrapur - I | 4th (2021-2022) | Augmentation | Augmentation of Uttar Harishandropur piped water supply scheme. | SM/10291 | TSM/008163 | SM/00066 | 40011171 | 7 | 7010 | 8800 | 8400 | 2014.31 | 2223.72 | Yes | 28/02/2022 | GO2122010177PH | MVS | PH212245148S000 | Administrative Approval Issued | N/A | Yes | 1582.72 | Yes | 1798.68 | 29/09/2021
136 | MALDAH | Malda Division | Harischandrapur - II | 11th(2021-2022) | New | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | TSM/011278 |  | 40016190 | 2 | 2122 | 2912 | 2912 | 798.84 | 904.9 | Yes | 22/07/2022 | GO2223005418PH | MVS | PH222358772S000 | Administrative Approval Issued | N/A | Yes | 201.76 | Yes | 610.16 | 30/03/2022
137 | MALDAH | Malda Division | Habibpur | 4th (2022-2023) | Augmentation | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | TSM/012802 | SM/03303 | 40026030 | 2 | 797 | 0 | 0 | 142.62 | 152.39 | Yes | 09/09/2022 | GO2223007371PH | MVS | PH222361972S000 | Administrative Approval Issued | N/A | Yes | 79.74 | Yes | 108.47 | 15/07/2022
138 | MALDAH | Malda Division | Harischandrapur - I | 3rd (2022-2023) | New | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | TSM/013044 |  | 40027591 | 9 | 2100 | 2326 | 2326 | 605.67 | 672 | Yes | 07/09/2022 | GO2223007223PH | MVS | PH222361953S000 | Administrative Approval Issued | N/A | Yes | 1469.34 | Yes | 616.87 | 05/07/2022
139 | MALDAH | Malda Division | Gazole | 2nd (2022-2023) | New | Alal Zone-II Piped Water Supply Scheme | SM/12877 | TSM/011886 |  | 40028431 | 5 | 2082 | 1413 | 1413 | 596.19 | 596.19 | Yes | 23/09/2022 | GO2223008157PH | MVS | PH222358766S000 | Administrative Approval Issued | N/A | Yes | 129.63 | Yes | 531.1 | 20/05/2022
140 | MALDAH | Malda Division | Bamangola | 5th (2022-2023) | Augmentation | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | TSM/015035 | SM/02900 | 40026215 | 5 | 895 | 0 | 0 | 208.4 | 220.11 | Yes | 20/09/2022 | GO2223007981PH | MVS | PH222362541S000 | Administrative Approval Issued | N/A | Yes | 84.65 | Yes | 141.68 | 22/08/2022
141 | MALDAH | Malda Division | Chanchal - I | 2nd (2022-2023) | Augmentation | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | TSM/011884 | SM/00071 | 40035079 | 6 | 8917 | 11149 | 11149 | 2616.08 | 2992.8 | Yes | 22/11/2022 | GO2223009971PH | MVS | PH222355420S000 | Administrative Approval Issued | N/A | Yes | 255.75 | Yes | 1780.6 | 20/05/2022
142 | MALDAH | Malda Division | Gazole | 9th (2022-2023) | Augmentation | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | TSM/016347 | SM/04446 | 40046531 | 3 | 2440 | 950 | 950 | 196.91 | 196.91 | Yes | 04/02/2023 | GO2223013175PH | MVS | PH222371511S000 | Administrative Approval Issued | N/A | Yes | 208.87 | Yes | 176.52 | 16/11/2022
143 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | TSM/016606 | SM/03580 | 40044131 | 1 | 2063 | 0 | 0 | 103.91 | 103.91 | Yes | 06/02/2023 | GO2223013328PH | SVS | PH222371182S000 | Administrative Approval Issued | N/A | Yes | 229.25 | Yes | 95.49 | 16/11/2022
144 | MALDAH | Malda Division | Habibpur | 9th (2022-2023) | Augmentation | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | TSM/015613 | SM/03072 | 40046545 | 4 | 1442 | 450 | 450 | 196.28 | 196.28 | Yes | 06/02/2023 | GO2223013236PH | MVS | PH222371625S000 | Administrative Approval Issued | N/A | Yes | 282.18 | Yes | 190.21 | 16/11/2022
145 | MALDAH | Malda Division | Maldah (Old) | 9th (2022-2023) | New | MORGRAM PWSS | SM/18557 | TSM/018419 |  | 40046438 | 9 | 3090 | 3767 | 3767 | 1084.68 | 1098.97 | Yes | 31/07/2023 | 2140/PHE-28011/115/2023-ESTT CELL-Dept. of PHE | MVS | PH222371637S000 | Administrative Approval Issued | N/A | Yes | 156.82 | Yes | 962.27 | 16/11/2022
146 | MALDAH | Malda Division | Harischandrapur - I | 11th(2021-2022) | New | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | TSM/011277 |  | 40016199 | 4 | 1205 | 1395 | 1523 | 510.87 | 582.14 | Yes | 22/07/2022 | GO2223005408PH | MVS | PH222358763S000 | Administrative Approval Issued | N/A | Yes | 96.33 | Yes | 398.18 | 30/03/2022
147 | MALDAH | Malda Division | Chanchal - II | 6th (2021-2022) | Augmentation | AUGMENTATION OF MALATIPUR PWSS | SM/09987 | TSM/008173 | SM/00160 | 40006363 | 8 | 2336 | 2301 | 2301 | 588.11 | 699.42 | Yes | 16/12/2021 | GO2122006953PH | MVS | PH212246559S000 | Administrative Approval Issued | N/A | Yes | 484.02 | Yes | 556.57 | 22/11/2021
148 | MALDAH | Malda Division | Habibpur | 8th (2022-2023) | New | PERAPUR PWSS | SM/18420 | TSM/015903 |  | 40034871 | 22 | 2795 | 3213 | 3213 | 1202.32 | 1213.51 | Yes | 18/07/2023 | 1919/PHE-28011/109/2023-SCHM CELL-Dept. of PHE | MVS | PH222366144S000 | Administrative Approval Issued | N/A | Yes | 220.92 | Yes | 1147.01 | 30/09/2022
149 | MALDAH | Malda Division | Chanchal - I | 2nd (2022-2023) | New | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | TSM/011882 |  | 40033932 | 12 | 7481 | 5400 | 5400 | 1072.98 | 1220.74 | Yes | 22/11/2022 | GO2223009962PH | MVS | PH222355425S000 | Administrative Approval Issued | N/A | Yes | 271.16 | Yes | 1057.06 | 20/05/2022
150 | MALDAH | Malda Division | Chanchal - I | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | SM/06866 | TSM/005695 | SM/04308 | 8128339 | 3 | 1615 | 1488 | 1488 | 79.87 | 79.87 | Yes | 07/10/2020 | GO2021001821PH | MVS |  | Administrative Approval Issued | N/A | Yes | 46.95 | Yes | 84.09 | 28/08/2020
151 | MALDAH | Malda Division | Habibpur | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | SM/06870 | TSM/005699 | SM/02901 | 8128349 | 7 | 1735 | 1735 | 1735 | 92.34 | 92.34 | Yes | 08/10/2020 | GO2021001831PH | MVS |  | Administrative Approval Issued | N/A | Yes | 37.02 | Yes | 87.95 | 28/08/2020
152 | MALDAH | Malda Division | Habibpur | 4th (2021-2022) | Augmentation | Augmentation of Bulbulchandi PWSS. | SM/09422 | TSM/008161 | SM/00175 | 40001227 | 5 | 4690 | 4694 | 4929 | 981.06 | 981.06 | Yes | 17/11/2021 | GO2122005478PH | MVS | PH212245152S000 | Administrative Approval Issued | N/A | Yes | 255.44 | Yes | 824.58 | 29/09/2021
153 | MALDAH | Malda Division | Ratua - II | 6th (2021-2022) | Augmentation | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | SM/10181 | TSM/008180 | SM/00069 | 40011166 | 6 | 6494 | 7524 | 7524 | 1896 | 2126.39 | Yes | 17/02/2022 | GO2122009753PH | MVS | PH212246558S000 | Administrative Approval Issued | N/A | Yes | 896.09 | Yes | 1446.28 | 22/11/2021
154 | MALDAH | Malda Division | English Bazar | 1st (2021-2022) | Augmentation | Augmentation of Maheshpur piped water supply scheme | SM/12362 | TSM/005106 | SM/00166 | 40028434 | 9 | 2906 | 0 | 0 | 1414.74 | 1566.03 | Yes | 13/09/2022 | GO2223007584PH | MVS | PH222353483S000 | Administrative Approval Issued | N/A | Yes | 228.77 | Yes | 957.7 | 19/08/2021
155 | MALDAH | Malda Division | Harischandrapur - I | 7th (2021-2022) | Augmentation | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | TSM/008174 | SM/00071 | 40002523 | 7 | 5229 | 4712 | 426 | 1114.1 | 1222.99 | Yes | 31/03/2022 | GO2121011630PH | MVS | PH212248318S000 | Administrative Approval Issued | N/A | Yes | 352.18 | Yes | 1100.96 | 16/12/2021
156 | MALDAH | Malda Division | Harischandrapur - II | 3rd (2022-2023) | New | PUTIA PWSS | SM/12194 | TSM/013011 |  | 40027595 | 1 | 109 | 132 | 132 | 73.96 | 82.16 | Yes | 07/09/2022 | GO2223007222PH | SVS | PH222361957S000 | Administrative Approval Issued | N/A | Yes | 99.44 | Yes | 71.1 | 05/07/2022
157 | MALDAH | Malda Division | Habibpur | 3rd (2022-2023) | New | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | TSM/013215 |  | 40034160 | 21 | 2189 | 2824 | 2824 | 1050.75 | 1149.66 | Yes | 17/11/2022 | GO2223009858PH | MVS | PH222361950S000 | Administrative Approval Issued | N/A | Yes | 76.01 | Yes | 1006.13 | 05/07/2022
158 | MALDAH | Malda Division | Bamangola | 5th (2022-2023) | Augmentation | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | TSM/015034 | SM/02898 | 40062474 | 1 | 521 | 0 | 0 | 164.92 | 172.98 | Yes | 20/01/2023 | GO2223012353PH | SVS | PH222362540S000 | Administrative Approval Issued | N/A | Yes | 119.51 | Yes | 152.03 | 22/08/2022
159 | MALDAH | Malda Division | Habibpur | 9th (2022-2023) | Augmentation | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | TSM/016285 | SM/03304 | 40046240 | 9 | 971 | 750 | 869 | 272.73 | 272.73 | Yes | 04/02/2023 | GO2223013181PH | MVS | PH222371610S000 | Administrative Approval Issued | N/A | Yes | 142.29 | Yes | 188.15 | 16/11/2022
160 | MALDAH | Malda Division | Harischandrapur - II | 9th (2022-2023) | Augmentation | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | TSM/017125 | SM/03823 | 40044160 | 2 | 1062 | 0 | 0 | 84.27 | 84.27 | Yes | 04/02/2023 | GO2223013139PH | MVS | PH222371501S000 | Administrative Approval Issued | N/A | Yes | 69.62 | Yes | 85.26 | 16/11/2022
161 | MALDAH | Malda Division | Chanchal - I | 9th (2022-2023) | Augmentation | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | TSM/016529 | SM/03932 | 40046749 | 3 | 1668 | 980 | 1658 | 149.47 | 149.47 | Yes | 04/02/2023 | GO2223013189PH | MVS | PH222371588S000 | Administrative Approval Issued | N/A | Yes | 61.19 | Yes | 60.95 | 16/11/2022
162 | MALDAH | Malda Division | Bamangola | 9th (2022-2023) | Augmentation | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | TSM/016354 | SM/03516 | 40044964 | 2 | 910 | 130 | 130 | 119.4 | 119.4 | Yes | 04/02/2023 | GO2223013159PH | MVS | PH222371604S000 | Administrative Approval Issued | N/A | Yes | 114.56 | Yes | 69.02 | 16/11/2022
163 | MALDAH | Malda Division | Gazole | 9th (2022-2023) | Augmentation | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | TSM/016220 | SM/03249 | 40044100 | 1 | 1250 | 250 | 250 | 124.6 | 124.6 | Yes | 04/02/2023 | GO2223013186PH | SVS | PH222371199S000 | Administrative Approval Issued | N/A | Yes | 104.58 | Yes | 101.95 | 16/11/2022
164 | MALDAH | Malda Division | Maldah (Old) | 2nd (2022-2023) | New | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | TSM/011828 |  | 40033900 | 28 | 3351 | 4342 | 4342 | 1107.06 | 1264.51 | Yes | 06/02/2023 | GO2223013360PH | MVS | PH222358769S000 | Administrative Approval Issued | N/A | Yes | 169.84 | Yes | 1048.54 | 20/05/2022
165 | MALDAH | Malda Division | Manikchak | 9th (2022-2023) | Augmentation | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | TSM/019388 | SM/00867 | 40046993 | 1 | 2301 | 375 | 375 | 865.47 | 881.16 | Yes | 06/02/2023 | GO2223013330PH | SVS | PH222370736S000 | Administrative Approval Issued | N/A | Yes | 130.17 | Yes | 804.12 | 16/11/2022
166 | MALDAH | Malda Division | Habibpur | 9th (2022-2023) | Augmentation | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | TSM/017677 | SM/00162 | 40046996 | 2 | 2853 | 1345 | 2641 | 390.5 | 390.5 | Yes | 07/02/2023 | GO2223013409PH | SVS | PH222371072S000 | Administrative Approval Issued | N/A | Yes | 518.23 | Yes | 332.42 | 16/11/2022
167 | MALDAH | Malda Division | Ratua - II | 10th(2022-2023) | Augmentation | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | TSM/011880 | SM/00178 | 40060504 | 1 | 1370 | 2049 | 2049 | 868.83 | 868.83 | Yes | 22/02/2023 | GO2223014622PH | SVS | PH222371008S000 | Administrative Approval Issued | N/A | Yes | 278.9 | Yes | 687.04 | 28/12/2022
168 | MALDAH | Malda Division | Maldah (Old) | 10th(2022-2023) | New | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | SM/15960 | TSM/017385 |  | 40066040 | 1 | 73 | 106 | 106 | 49.53 | 49.53 | Yes | 22/02/2023 | GO2223014621PH | SVS | PH222371049S000 | Administrative Approval Issued | N/A | Yes | 78.8 | Yes | 48.78 | 28/12/2022
169 | MALDAH | Malda Division | Gazole | 6th (2022-2023) | New | ALINAGAR Piped Water Supply Scheme | SM/13431 | TSM/015847 |  | 40033888 | 5 | 4719 | 2356 | 2356 | 683.89 | 724.32 | Yes | 02/11/2022 | GO2223009242PH | MVS | PH222364663S000 | Administrative Approval Issued | N/A | Yes | 231.61 | Yes | 678.71 | 09/09/2022
170 | MALDAH | Malda Division | Chanchal - I | 3rd (2022-2023) | New | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | TSM/013216 |  | 40027589 | 3 | 2722 | 2609 | 2609 | 791.25 | 867.35 | Yes | 07/09/2022 | GO2223007226PH | MVS | PH222361949S000 | Administrative Approval Issued | N/A | Yes | 474.17 | Yes | 779.4 | 05/07/2022
171 | MALDAH | Malda Division | Bamangola | 10th(2022-2023) | New | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | TSM/017908 |  | 40057312 | 141 | 38804 | 12384 | 12384 | 15363.32 | 15363.32 | Yes | 04/08/2023 | 2246/PHE-28011/113/2023-SCHM CELL-Dept. of PHE | MVS | PH222371068S000 | Administrative Approval Issued | N/A | Yes | 14440.79 | Yes | 14440.79 | 28/12/2022
Total | [10 empty] | 1675 | 756955 | 563501 | 567674 | 189163.09 | 196141.98 | [8 empty] | 87694.23 |  | 172877.83