## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - DARJEELING
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | TSM/012926 |  | 40045013 | 5 | 1583 | 768 | 768 | 1470.02 | 1470.02 | Yes | 31/07/2023 | 2141/PHE-28011/117/2023-ESTT CELL-Dept. of PHE | MVS | PH222370835S000 | Administrative Approval Issued | N/A | Yes | 1353.52 | Yes | 1353.52 | 30/09/2022
2 | DARJEELING | Kurseong Division |  | 11th(2022-2023) | New | Piped Water supply scheme of Ambotia T.E., Saint Mary's - I, Spring side, Makaibari and Karbia T.E. by pumping water from Balasan river under PHED Kurseong Division, GTA |  | TSM/021464 |  | 40067433 | 5 | 11631 | 3571 | 3571 | 13750 | 13750 | No | N/A | N/A | MVS |  | Awaiting For Administrative Approval | Department | No | N/A | No | N/A | 10/03/2023
3 | DARJEELING | Kurseong Division | Kurseong | 5th (2020-2021) | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] | SM/10262 | TSM/007006 | SM/05195 | 40009404 | 2 | 1955 | 1955 | 817 | 159.17 | 159.17 | Yes | 08/02/2021 | GO2021006578PH | MVS |  | Administrative Approval Issued | N/A | Yes | 123.59 | Yes | 123.59 | 08/01/2021
4 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | SM/18638 | TSM/013420 |  | 40044975 | 2 | 762 | 637 | 637 | 1513.58 | 1513.58 | Yes | 31/07/2023 | 2167/PHE-28011/79/2023-ESTT CELL-Dept. of PHE | MVS | PH222370811S000 | Administrative Approval Issued | N/A | Yes | 1344.48 | Yes | 1344.48 | 30/09/2022
5 | DARJEELING | Kurseong Division | Kurseong | 11th(2022-2023) | Augmentation | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18878 | TSM/020480 | SM/10817 | GOI Issue | 1 | 989 | 161 | 161 | 199.02 | 199.02 | Yes | 05/10/2023 | PHE/IV/3033/W-662/23 | SVS |  | Administrative Approval Issued | N/A | Yes | 157.49 | Yes | 157.49 | 10/03/2023
6 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 8th (2022-2023) | New | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | TSM/014424 |  | 40037351 | 4 | 4668 | 4639 | 4639 | 3828.95 | 3828.95 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | MVS | PH222370770S000 | Administrative Approval Issued | N/A | Yes | 3619 | Yes | 3619 | 30/09/2022
7 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | TSM/013280 |  | 40045005 | 3 | 1963 | 832 | 843 | 1203.19 | 1203.19 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | MVS | PH222370824S000 | Administrative Approval Issued | N/A | Yes | 1171.07 | Yes | 1171.07 | 30/09/2022
8 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 11th(2022-2023) | New | CONSTRUCTION OF SOURCE AND OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SONADA TO ACCOMODATE TWO MOUZAS MAINLY SONADA FOREST & SONADA KHASMAHAL UNDER SUKHIA POKHARI BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, PHED. | SM/19039 | TSM/021463 |  |  | 2 | 3845 | 2100 | 2100 | 2250.46 | 2250.46 | Yes | 17/11/2023 | 3496/PHE-28011/242/2023-SCHM CELL-Dept. of PHE | MVS |  | Administrative Approval Issued | N/A | Yes | 0.99 | Yes | 0.99 | 10/03/2023
9 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Edenvale Tea Garden | SM/18710 | TSM/013285 |  | 40044843 | 1 | 108 | 108 | 108 | 150.23 | 150.23 | Yes | 04/08/2023 | 2259/PHE/IV/W-359/23 | SVS | PH222370685S000 | Administrative Approval Issued | N/A | Yes | 136.43 | Yes | 136.43 | 30/09/2022
10 | DARJEELING | Kurseong Division | Kurseong | 11th(2021-2022) | New | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/19033 | TSM/011217 |  | GOI Issue | 1 | 1495 | 1117 | 1117 | 1424.7 | 1424.7 | Yes | 03/11/2023 | 3371/PHE-28011/145/2022-SCHM CELL-Dept. of PHE | SVS | PH222354861S000 | Administrative Approval Issued | N/A | Yes | 1230.38 | Yes | 1230.38 | 30/03/2022
11 | DARJEELING | Kurseong Division | Kurseong | 10th(2022-2023) | New | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 | TSM/020430 |  | 40059460 | 7 | 3521 | 3420 | 3485 | 2936.38 | 2936.38 | Yes | 14/08/2023 | 2361/PHE-28011/92/2023-ESTT CELL-Dept. of PHE | MVS | PH222372949S000 | Administrative Approval Issued | N/A | Yes | 2446.03 | Yes | 2446.03 | 28/12/2022
12 | DARJEELING | Kurseong Division | Naxalbari | 11th(2022-2023) | Augmentation | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | TSM/020476 | SM/10815 | GOI Issue | 4 | 2126 | 159 | 159 | 194.06 | 194.06 | Yes | 05/10/2023 | PHE/IV/3033/W-662/23 | MVS |  | Administrative Approval Issued | N/A | Yes | 152.53 | Yes | 152.53 | 10/03/2023
13 | DARJEELING | Kurseong Division | Kurseong | 11th(2022-2023) | Augmentation | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME | SM/18879 | TSM/020479 | SM/10790 | GOI Issue | 1 | 294 | 80 | 80 | 93.17 | 93.17 | Yes | 05/10/2023 | PHE/IV/3033/W-662/23 | SVS |  | Administrative Approval Issued | N/A | Yes | 70.82 | Yes | 70.82 | 10/03/2023
14 | DARJEELING | Kurseong Division | Kurseong | 5th (2020-2021) | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | TSM/007004 | SM/05421 | 7363231 | 1 | 2740 | 1463 | 1124 | 108.57 | 108.57 | Yes | 08/02/2021 | GO2021006580PH | MVS |  | Administrative Approval Issued | N/A | Yes | 76.29 | Yes | 76.29 | 08/01/2021
15 | DARJEELING | Kurseong Division | Mirik | 8th (2022-2023) | New | PWS Scheme for Mirik Khasmahal | SM/18650 | TSM/014413 |  | 40046483 | 1 | 1306 | 1306 | 1306 | 1261.17 | 1261.17 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | SVS | PH222370716S000 | Administrative Approval Issued | N/A | Yes | 1238.99 | Yes | 1238.99 | 30/09/2022
16 | DARJEELING | Kurseong Division | Mirik | 8th (2022-2023) | New | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | TSM/014167 |  | 40046486 | 1 | 1552 | 1170 | 1170 | 1262.65 | 1262.65 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | SVS | PH222370717S000 | Administrative Approval Issued | N/A | Yes | 1151.92 | Yes | 1151.92 | 30/09/2022
17 | DARJEELING | Kurseong Division | Kurseong | 11th(2022-2023) | Augmentation | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18880 | TSM/020477 | SM/10818 | GOI Issue | 1 | 684 | 190 | 190 | 197.84 | 197.84 | Yes | 05/10/2023 | PHE/IV/3033/W-662/23 | SVS |  | Administrative Approval Issued | N/A | Yes | 156.31 | Yes | 156.31 | 10/03/2023
18 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 5th (2020-2021) | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | TSM/007005 | SM/05195 | 40009403 | 2 | 1609 | 387 | 312 | 39.28 | 39.28 | Yes | 08/02/2021 | GO2021006579PH | MVS |  | Administrative Approval Issued | N/A | Yes | 37.32 | Yes | 37.32 | 08/01/2021
19 | DARJEELING | Kurseong Division | Mirik | 10th(2022-2023) | New | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | TSM/017734 |  | 40057875 | 1 | 305 | 172 | 172 | 327.7 | 327.7 | Yes | 20/02/2023 | GO2223014268PH | SVS | PH222372789S000 | Administrative Approval Issued | N/A | Yes | 306.55 | Yes | 306.55 | 28/12/2022
20 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 | TSM/013419 |  | 40044761 | 1 | 498 | 229 | 229 | 210.61 | 210.61 | Yes | 17/02/2023 | GO2223014107PH | SVS | PH222370723S000 | Administrative Approval Issued | N/A | Yes | 201.76 | Yes | 201.76 | 30/09/2022
21 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS scheme for St. Mary's & Goethals | SM/15661 | TSM/013415 |  | 40044994 | 2 | 860 | 715 | 675 | 338.76 | 338.76 | Yes | 17/02/2023 | GO2223014108PH | MVS | PH222370818S000 | Administrative Approval Issued | N/A | Yes | 310.41 | Yes | 310.41 | 30/09/2022
22 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 10th(2022-2023) | New | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | SM/18727 | TSM/014164 |  | 40059447 | 2 | 1459 | 1682 | 1682 | 1928.5 | 1928.5 | Yes | 14/08/2023 | 2361/PHE-28011/92/2023-ESTT CELL-Dept. of PHE | MVS | PH222372947S000 | Administrative Approval Issued | N/A | Yes | 1938.1 | Yes | 1938.1 | 28/12/2022
23 | DARJEELING | Kurseong Division | Mirik | 8th (2022-2023) | New | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | TSM/014420 |  | 40045625 | 6 | 2505 | 2100 | 2153 | 3308.68 | 3308.68 | Yes | 31/07/2023 | 2147/PHE-28011/142/2023-ESTT CELL-Dept. of PHE | MVS | PH222370789S000 | Administrative Approval Issued | N/A | Yes | 2589.56 | Yes | 2589.56 | 30/09/2022
24 | DARJEELING | Kurseong Division | Mirik | 8th (2022-2023) | New | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | TSM/014414 |  | 40045635 | 4 | 4510 | 1896 | 1896 | 1969.93 | 1969.93 | Yes | 31/07/2023 | 2167/PHE-28011/79/2023-ESTT CELL-Dept. of PHE | MVS | PH222370798S000 | Administrative Approval Issued | N/A | Yes | 1531.77 | Yes | 1531.77 | 30/09/2022
25 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 | TSM/012921 |  | 40065669 | 2 | 921 | 886 | 886 | 1208.42 | 1208.42 | Yes | 31/07/2023 | 2167/PHE-28011/79/2023-ESTT CELL-Dept. of PHE | MVS | PH222370837S000 | Administrative Approval Issued | N/A | Yes | 1210.86 | Yes | 1210.86 | 30/09/2022
26 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 8th (2022-2023) | New | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | SM/18648 | TSM/014421 |  | 40037351 | 2 | 1967 | 1564 | 1564 | 2338.45 | 2338.45 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | MVS | PH222370777S000 | Administrative Approval Issued | N/A | Yes | 2171.44 | Yes | 2171.44 | 30/09/2022
27 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | SM/18652 | TSM/013418 |  | 40044799 | 1 | 998 | 998 | 998 | 1174.35 | 1174.35 | Yes | 31/07/2023 | 2171/PHE-28011/149/2023-SCHM CELL-Dept. of PHE | SVS | PH222370724S000 | Administrative Approval Issued | N/A | Yes | 964.56 | Yes | 964.56 | 30/09/2022
28 | DARJEELING | Kurseong Division | Rangli Rangliot | 11th(2022-2023) | New | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | SM/19038 | TSM/021459 |  |  | 1 | 3089 | 4193 | 4193 | 6918 | 6918 | Yes | 17/11/2023 | 3496/PHE-28011/242/2023-SCHM CELL-Dept. of PHE | SVS |  | Administrative Approval Issued | N/A | Yes | 5612.47 | Yes | 5612.47 | 10/03/2023
29 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | PWS Scheme for Selim Hill Tea Garden | SM/15652 | TSM/013284 |  | 40044856 | 1 | 492 | 384 | 384 | 967.91 | 967.91 | Yes | 17/02/2023 | GO2223014109PH | SVS | PH222370727S000 | Administrative Approval Issued | N/A | Yes | 914.21 | Yes | 914.21 | 30/09/2022
30 | DARJEELING | Kurseong Division | Jorebunglow Sukiapokhri | 10th(2022-2023) | New | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | TSM/014155 |  | 40059462 | 3 | 2580 | 3257 | 3257 | 3390 | 3390 | Yes | 14/08/2023 | 2361/PHE-28011/92/2023-ESTT CELL-Dept. of PHE | MVS | PH222372948S000 | Administrative Approval Issued | N/A | Yes | 3141.92 | Yes | 3141.92 | 28/12/2022
31 | DARJEELING | Kurseong Division | Kurseong | 11th(2022-2023) | New | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | SM/18917 | TSM/021550 |  |  | 6 | 5304 | 702 | 925 | 947.7 | 947.7 | Yes | 09/10/2023 | PHE/IV/3088/W-671/23 | MVS |  | Administrative Approval Issued | N/A | Yes | 867.29 | Yes | 867.29 | 10/03/2023
32 | DARJEELING | Kurseong Division | Kurseong | 8th (2022-2023) | New | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | TSM/017228 |  | 40044960 | 6 | 11283 | 6130 | 6130 | 3073.44 | 3073.44 | Yes | 26/07/2023 | 2053/PHE-28011/212/2023-ESTT CELL-Dept. of PHE | MVS | PH222370744S000 | Administrative Approval Issued | N/A | Yes | 2675.58 | Yes | 2675.58 | 30/09/2022
Total | [10 empty] | 82 | 79602 | 48971 | 47731 | 60144.89 | 60144.89 | [8 empty] | 38903.64 |  | 38903.64