## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - SOUTH 24 PARGANAS
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | SOUTH 24 PARGANAS | Alipore Division | Namkhana | 4th (2020-2021) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | SM/07411 | TSM/006805 | SM/03793 | 8198353 | 2 | 3806 | 1248 | 2943 | 92.29 | 92.29 | Yes | 29/12/2020 | GO2021003707PH | MVS |  | Administrative Approval Issued | N/A | Yes | 40 | No | N/A | 04/12/2020
2 | SOUTH 24 PARGANAS | Alipore Division | Sagar | 4th (2020-2021) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | TSM/006858 | SM/04847 | 8197426 | 1 | 2150 | 1174 | 1957 | 82.02 | 82.02 | Yes | 29/12/2020 | GO2021003691PH | SVS |  | Administrative Approval Issued | N/A | Yes | 33.2 | No | N/A | 04/12/2020
3 | SOUTH 24 PARGANAS | Alipore Division | Sagar | 4th (2020-2021) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl | SM/07410 | TSM/006803 | SM/04861 | 8198037 | 1 | 1150 | 761 | 880 | 49.5 | 49.5 | Yes | 29/12/2020 | GO2021003704PH | SVS |  | Administrative Approval Issued | N/A | Yes | 5.42 | No | N/A | 04/12/2020
4 | SOUTH 24 PARGANAS | Alipore Division | Falta | 3rd (2020-2021) | Retrofitting | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | TSM/005828 | SM/03906 | 5344170 | 5 | 2194 | 7016 | 1666 | 389.87 | 389.87 | Yes | 19/02/2021 | GO2021007280PH | MVS |  | Administrative Approval Issued | N/A | Yes | 401.94 | No | N/A | 25/09/2020
5 | SOUTH 24 PARGANAS | Alipore Division | Falta | 3rd (2020-2021) | Retrofitting | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08122 | TSM/005829 | SM/03906 | 5344170 | 3 | 1724 | 7016 | 1203 | 357.03 | 357.03 | Yes | 19/02/2021 | GO2021007279PH | MVS |  | Administrative Approval Issued | N/A | Yes | 303.71 | No | N/A | 25/09/2020
6 | SOUTH 24 PARGANAS | Alipore Division | Canning - I | 4th (2020-2021) | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | TSM/006869 | SM/04924 | 8200068 | 4 | 5394 | 5149 | 3199 | 272.76 | 272.76 | Yes | 07/01/2021 | GO2021004171PH | MVS |  | Administrative Approval Issued | N/A | Yes | 41.74 | No | N/A | 04/12/2020
7 | SOUTH 24 PARGANAS | Alipore Division | Kakdwip | 4th (2020-2021) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | SM/07591 | TSM/006863 | SM/03588 | 8200024 | 1 | 4279 | 1075 | 1075 | 66.06 | 66.06 | Yes | 31/12/2020 | GO2021003947PH | SVS |  | Administrative Approval Issued | N/A | Yes | 17.9 | No | N/A | 04/12/2020
8 | SOUTH 24 PARGANAS | Alipore Division | Canning - II | 4th (2020-2021) | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | SM/07592 | TSM/006875 | SM/04923 | 8200028 | 2 | 2701 | 1661 | 1675 | 95.32 | 95.32 | Yes | 31/12/2020 | GO2021003948PH | MVS |  | Administrative Approval Issued | N/A | Yes | 92.65 | No | N/A | 04/12/2020
9 | SOUTH 24 PARGANAS | Alipore Division | Falta | 4th (2021-2022) | Retrofitting | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | TSM/008679 | SM/03906 | 5344170 | 6 | 6636 | 5866 | 5866 | 286.94 | 286.94 | Yes | 17/11/2021 | GO2122005505PH | MVS | PH212245529S000 | Administrative Approval Issued | N/A | Yes | 302.92 | No | N/A | 29/09/2021
10 | SOUTH 24 PARGANAS | Alipore Division | Sagar | 7th (2020-2021) | Retrofitting | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08793 | TSM/007690 | SM/04133 | 40007328 | 1 | 1999 | 877 | 1753 | 66.55 | 66.55 | Yes | 13/09/2021 | GO2122003238PH | MVS |  | Administrative Approval Issued | N/A | Yes | 22.44 | No | N/A | 19/02/2021
11 | SOUTH 24 PARGANAS | Alipore Division | Kakdwip | 7th (2020-2021) | Retrofitting | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | TSM/007688 | SM/00847 | 40007442 | 1 | 7540 | 4210 | 3972 | 208.29 | 208.29 | Yes | 13/09/2021 | GO2122003238PH | MVS |  | Administrative Approval Issued | N/A | Yes | 6.3 | No | N/A | 19/02/2021
12 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - I | 5th (2021-2022) | Retrofitting | Retrofitting of Distribution System of Zone-VIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09555 | TSM/009099 | SM/03906 | 5344170 | 6 | 2512 | 2196 | 2196 | 175.13 | 175.13 | Yes | 19/11/2021 | GO2122005601PH | MVS | TPH212246043M001 | Administrative Approval Issued | N/A | Yes | 22.08 | No | N/A | 08/10/2021
13 | SOUTH 24 PARGANAS | Alipore Division | Namkhana | 1st (2021-2022) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | TSM/008288 | SM/00809 | 40001915 | 4 | 4659 | 4711 | 2421 | 162.44 | 162.44 | Yes | 19/11/2021 | GO2122005584PH | MVS | TPH212243039M010 | Administrative Approval Issued | N/A | Yes | 40.98 | No | N/A | 19/08/2021
14 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - I | 1st (2021-2022) | Retrofitting | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | TSM/008304 | SM/03906 | 5344170 | 4 | 2124 | 1957 | 1957 | 102.7 | 102.7 | Yes | 19/11/2021 | GO2122005579PH | MVS | TPH212245614M002 | Administrative Approval Issued | N/A | Yes | 4.83 | No | N/A | 19/08/2021
15 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - I | 1st (2021-2022) | Retrofitting | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | TSM/008305 | SM/03906 | 5344170 | 2 | 2257 | 1979 | 1573 | 106.53 | 106.53 | Yes | 19/11/2021 | GO2122005579PH | MVS | TPH212245614M003 | Administrative Approval Issued | N/A | Yes | 81.91 | No | N/A | 19/08/2021
16 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - I | 1st (2021-2022) | Retrofitting | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | TSM/008307 | SM/03577 | 5344170 | 3 | 2801 | 2491 | 2491 | 125.82 | 125.82 | Yes | 19/11/2021 | GO2122005579PH | MVS | TPH212245614M005 | Administrative Approval Issued | N/A | Yes | 125.82 | No | N/A | 19/08/2021
17 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - I | 5th (2021-2022) | Retrofitting | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | TSM/009100 | SM/03906 | 5344170 | 1 | 274 | 252 | 252 | 21.75 | 21.75 | Yes | 19/11/2021 | GO2122005601PH | SVS | TPH212246043M002 | Administrative Approval Issued | N/A | Yes | 23.25 | No | N/A | 08/10/2021
18 | SOUTH 24 PARGANAS | Alipore Division | Mathurapur - II | 8th (2021-2022) | Augmentation | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | TSM/009241 | SM/03906 | 5344170 | 1 | 3689 | 1769 | 1769 | 208.5 | 208.5 | Yes | 13/04/2022 | GO2223000224PH | SVS | PH222352641S000 | Administrative Approval Issued | N/A | Yes | 164.7 | No | N/A | 27/01/2022
19 | SOUTH 24 PARGANAS | Alipore Division | Namkhana | 2nd (2021-2022) | Retrofitting | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | SM/09076 | TSM/008428 | SM/05033 | 40001945 | 1 | 2498 | 1169 | 1169 | 120.65 | 120.65 | Yes | 29/10/2021 | GO2122004658PH | SVS | PH212243869M000 | Administrative Approval Issued | N/A | Yes | 123.18 | No | N/A | 08/09/2021
20 | SOUTH 24 PARGANAS | Alipore Division | Canning - II | 2nd (2021-2022) | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | SM/09095 | TSM/008684 | SM/05349 | 40008764 | 4 | 8453 | 4630 | 4630 | 261.46 | 261.46 | Yes | 29/10/2021 | GO2122004657PH | MVS | PH212243869M000 | Administrative Approval Issued | N/A | Yes | 291.28 | No | N/A | 08/09/2021
21 | SOUTH 24 PARGANAS | Alipore Division | Namkhana | 6th (2021-2022) | Augmentation | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | TSM/009237 | SM/00809 | 40009481 | 4 | 4659 | 4770 | 4770 | 1160.08 | 1160.08 | Yes | 01/02/2022 | GO2122009009PH | MVS | PH212246417S000 | Administrative Approval Issued | N/A | Yes | 301.2 | No | N/A | 22/11/2021
22 | SOUTH 24 PARGANAS | Alipore Division | Kulpi | 6th (2021-2022) | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | TSM/009222 | SM/03718 | 5344170 | 12 | 3405 | 2745 | 2745 | 164.33 | 164.33 | Yes | 15/12/2021 | GO2122006875PH | MVS | TPH212246416M002 | Administrative Approval Issued | N/A | Yes | 26.75 | No | N/A | 22/11/2021
23 | SOUTH 24 PARGANAS | Alipore Division | Diamond Harbour - II | 4th (2022-2023) | New | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | TSM/013463 |  | 40060027 | 1 | 40 | 34 | 34 | 38.67 | 38.67 | Yes | 15/09/2022 | GO2223007738PH | SVS | PH222360717M000 | Administrative Approval Issued | N/A | Yes | 26.88 | No | N/A | 15/07/2022
24 | SOUTH 24 PARGANAS | Alipore Division | Sagar | 4th (2021-2022) | Augmentation | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | TSM/008774 | SM/00810 | 40009487 | 2 | 3115 | 1995 | 1995 | 1068.69 | 1068.69 | Yes | 10/02/2022 | GO2122009596PH | MVS | PH212245526S000 | Administrative Approval Issued | N/A | Yes | 123.97 | No | N/A | 29/09/2021
25 | SOUTH 24 PARGANAS | Alipore Division | Canning - II | 2nd (2021-2022) | Augmentation | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | TSM/008768 | SM/03792 | 40009384 | 12 | 4570 | 4871 | 4871 | 867.99 | 867.99 | Yes | 10/12/2021 | GO2122006631PH | MVS | PH212247175S000 | Administrative Approval Issued | N/A | Yes | 940.12 | No | N/A | 08/09/2021
26 | SOUTH 24 PARGANAS | Alipore Division | Basanti | 5th (2022-2023) | Augmentation | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13757 | TSM/015087 | SM/00545 | 40032959 | 1 | 3609 | 3872 | 3872 | 999.02 | 999.02 | Yes | 18/11/2022 | GO2223009880PH | SVS | PH222362290M000 | Administrative Approval Issued | N/A | Yes | 54.15 | No | N/A | 22/08/2022
27 | SOUTH 24 PARGANAS | Alipore Division | Patharpratima | 2nd (2022-2023) | New | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BHAJNA UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/12732 | TSM/011581 |  | 40028492 | 1 | 1965 | 1638 | 1638 | 588.7 | 662.57 | Yes | 20/09/2022 | GO2223007932PH | SVS | PH222355996S000 | Administrative Approval Issued | N/A | Yes | 194.78 | No | N/A | 20/05/2022
Total | [10 empty] | 86 | 90203 | 77132 | 64572 | 8139.09 | 8212.96 | [8 empty] | 3814.1