## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - I | Purbba Basudebpur | null | Pump House | Vested | 133 | 451 | 0 | 0 | Identified | null
2 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Kalinagar | null | WTP | Private | 111 | 2002 | 388 | 11 | Possessed | null
3 | HOWRAH | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah.(TSM/011301,SM/16760) | TSM/011301 | SM/16760 | New | MVS | Bagnan - I | Bangalpur | null | OHR | Private | 43 | 3695 | 2475 | 33 | Identified | null
4 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah.(TSM/011679,SM/11221) | TSM/011679 | SM/11221 | New | MVS | Udaynarayanpur | Chak Baharampur | null | Pump House | Donated | 30 | 8 | 578 | 0 | Identified | null
5 | HOWRAH | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME.(TSM/015233,SM/18747) | TSM/015233 | SM/18747 | New | MVS | Uluberia - II | Brindabanpur | null | OHR | Vested | 90 | 2386 | 2531 | 33 | Identified | null
6 | HOWRAH | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH(TSM/011637,SM/18562) | TSM/011637 | SM/18562 | New | MVS | Amta - I | Anule | Vested | Pump House | Vested | 193 | 1 | 619 | 3 | Identified | IDT proposal sent by BL & LRO
7 | HOWRAH | Augmentation of Ground water PWSS for Islampur(TSM/008589,SM/09428) | TSM/008589 | SM/09428 | Augmentation | MVS | Jagatballavpur | Islampur | null | OHR | Vested | 76 | 0 | 0 | 0 | Possessed | PHE Land
8 | HOWRAH | PANCHLA PIPED WATER SUPPLY SCHEME.(TSM/014879,SM/18563) | TSM/014879 | SM/18563 | New | SVS | Panchla | Panchla (CT) | null | OHR | Donated | 0 | 8585 | 4518 | 33 | Identified | null
9 | HOWRAH | PANCHLA PIPED WATER SUPPLY SCHEME.(TSM/014879,SM/18563) | TSM/014879 | SM/18563 | New | SVS | Panchla | Panchla (CT) | null | Pump House | Vested | 0 | 0 | 0 | 3 | Not Identified | null
10 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara(TSM/008620,SM/09351) | TSM/008620 | SM/09351 | Augmentation | MVS | Jagatballavpur | Bhursit Bamunpara | null | Pump House | Donated | 25 | 797 | 1428 | 0 | Identified | null
11 | HOWRAH | Baniban Zone-III Piped water Supply Scheme(TSM/018485,SM/18564) | TSM/018485 | SM/18564 | New | MVS | Uluberia - II | Basudebpur | null | OHR | Private | 93 | 5182 | 762 | 30 | Identified | null
12 | HOWRAH | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC(TSM/010977,SM/11572) | TSM/010977 | SM/11572 | New | MVS | Udaynarayanpur | Par Radhanagar | Vested(Shali) | Pump House | Vested | 176 | 1 | 218 | 3 | Possessed | IDT pending
13 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme(TSM/005654,SM/06715) | TSM/005654 | SM/06715 | Retrofitting | MVS | Amta - II | Khari Geria | null | OHR | Private | 99 | 234 | 758 | 33 | Identified | null
14 | HOWRAH | Augmentation of Ground water based PWSS Jujarsah(TSM/008639,SM/10146) | TSM/008639 | SM/10146 | Augmentation | MVS | Panchla | Kuldanga | null | Pump House | Vested | 9 | 1 | 5345 | 0 | Identified | null
15 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II)(TSM/006745,SM/07884) | TSM/006745 | SM/07884 | Retrofitting | SVS | Amta - II | Uttar Bhatora | null | OHR | Vested | 78 | 1 | 0 | 33 | Identified | null
16 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block(TSM/006742,SM/07886) | TSM/006742 | SM/07886 | Retrofitting | MVS | Amta - II | Sehagari | null | OHR | Vested | 112 | 22 | 89 | 27 | Identified | null
17 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006743,SM/07887) | TSM/006743 | SM/07887 | Retrofitting | MVS | Udaynarayanpur | Kansona | null | OHR | Vested | 56 | 1 | 340 | 0 | Identified | null
18 | HOWRAH | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME.(TSM/015269,SM/13749) | TSM/015269 | SM/13749 | New | MVS | Panchla | Mallik Bagan | 3rd TW Site | Pump House | Donated | 7 | 0 | 4526 | 0 | Identified | null
19 | HOWRAH | Kamina Piped Water Supply Scheme with provision of FHTC(TSM/011290,SM/16927) | TSM/011290 | SM/16927 | New | MVS | Uluberia - II | Chak.Bhagabatipur | null | OHR | Vested | 2 | 1 | 1342 | 0 | Possessed | IDT proposal sent by BLLRO, Ulu II
20 | HOWRAH | Jaynagar Piped Water Supply Scheme(TSM/018489,SM/14865) | TSM/018489 | SM/14865 | New | MVS | Panchla | Jaynagar | null | Pump House | Vested | 16 | 626 | 2539 | 0 | Identified | null
21 | HOWRAH | Augmentation of Ground water based PWSS Mankur Deulgram(TSM/008627,SM/09349) | TSM/008627 | SM/09349 | Augmentation | MVS | Bagnan - I | Deulgram (CT) | null | OHR | Vested | 4 | 1 | 389 | 33 | Identified | null
22 | HOWRAH | Paschim Panchla Piped Water Supply Scheme.(TSM/014766,SM/13768) | TSM/014766 | SM/13768 | New | SVS | Panchla | Paschim Panchla | Paschim Panchla | Pump House | Vested | 22 | 0 | 0 | 3 | Not Identified | null
23 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah.(TSM/011678,SM/11222) | TSM/011678 | SM/11222 | New | MVS | Amta - II | Saoria | vested | OHR | Vested | 113 | 1 | 1367 | 22 | Possessed | Mutation Done
24 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Ramchandrapur (CT) | null | WTP | Vested | 0 | 1 | 213 | 2 | Possessed | null
25 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1)(TSM/006296,SM/07008) | TSM/006296 | SM/07008 | Retrofitting | SVS | Amta - II | Tajpur | null | OHR | Donated | 131 | 2870 | 1803 | 0 | Identified | null
26 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Domjur | Prasastha | null | OHR | Vested | 29 | 1 | 396 | 0 | Possessed | IDT done, Possession taken by PHED.
27 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II(TSM/006294,SM/07464) | TSM/006294 | SM/07464 | Retrofitting | MVS | Amta - II | Jaypur | vested | OHR | Vested | 105 | 1 | 277 | 76 | Identified | IDT pending
28 | HOWRAH | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block.(TSM/011001,SM/11573) | TSM/011001 | SM/11573 | New | MVS | Udaynarayanpur | Paliara | null | OHR | Vested | 173 | 1 | 1449 | 15 | Identified | null
29 | HOWRAH | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block.(TSM/011001,SM/11573) | TSM/011001 | SM/11573 | New | MVS | Udaynarayanpur | Paliara | Vested | OHR | Vested | 173 | 1 | 1450 | 7 | Possessed | IDT done.
30 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006749,SM/07880) | TSM/006749 | SM/07880 | Retrofitting | MVS | Udaynarayanpur | Kultikari | null | Pump House | Donated | 59 | 635 | 274 | 0 | Identified | null
31 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara(TSM/008620,SM/09351) | TSM/008620 | SM/09351 | Augmentation | MVS | Jagatballavpur | Dhasa | null | Pump House | Vested | 28 | 254 | 760 | 0 | Identified | null
32 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II)(TSM/005644,SM/06784) | TSM/005644 | SM/06784 | Retrofitting | MVS | Amta - I | Balichak | null | OHR | Private | 162 | 1639 | 2162 | 0 | Identified | null
33 | HOWRAH | ICHAPUR PWSS(TSM/012520,SM/13629) | TSM/012520 | SM/13629 | New | MVS | Jagatballavpur | Ichhapur | null | Pump House | Vested | 44 | 1 | 360 | 0 | Identified | null
34 | HOWRAH | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah.(TSM/011760,SM/11711) | TSM/011760 | SM/11711 | New | MVS | Domjur | Bipra Noapara (CT) | null | Pump House | Vested | 0 | 1 | 0 | 0 | Identified | null
35 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme(TSM/005652,SM/06788) | TSM/005652 | SM/06788 | Retrofitting | MVS | Amta - II | Paschim Gazipur | null | Pump House | Private | 115 | 3689 | 0 | 0 | Identified | null
36 | HOWRAH | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah.(TSM/011760,SM/11711) | TSM/011760 | SM/11711 | New | MVS | Domjur | Begari | null | Pump House | Vested | 25 | 116 | 466 | 0 | Identified | null
37 | HOWRAH | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah.(TSM/011760,SM/11711) | TSM/011760 | SM/11711 | New | MVS | Domjur | Begari | null | OHR | Vested | 25 | 0 | 0 | 0 | Possessed | PHE Land
38 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block(TSM/006295,SM/07010) | TSM/006295 | SM/07010 | Retrofitting | MVS | Amta - II | Sirol | (Donated) | Pump House | Donated | 126 | 1769 | 1337 | 0 | Identified | null
39 | HOWRAH | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte.(TSM/008801,SM/09930) | TSM/008801 | SM/09930 | Augmentation | MVS | Amta - I | Mato | Private | Pump House | Private | 184 | 132 | 318 | 1 | Possessed | Old scheme possessed by PHED
40 | HOWRAH | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah.(TSM/011301,SM/16760) | TSM/011301 | SM/16760 | New | MVS | Bagnan - I | Bangalpur | null | Pump House | Vested | 43 | 1 | 0 | 0 | Possessed | IDT Done
41 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006747,SM/07881) | TSM/006747 | SM/07881 | Retrofitting | MVS | Udaynarayanpur | Sonagachhi | (private) Danga | Pump House | Private | 40 | 184 | 131 | 2 | Identified | null
42 | HOWRAH | Patinan Piped Water Supply Scheme(TSM/015627,SM/13848) | TSM/015627 | SM/13848 | New | SVS | Bagnan - I | Patinan | vested | Pump House | Vested | 39 | 1 | 0 | 17 | Possessed | IDT Done and possession handed over to PHE Dte.
43 | HOWRAH | Banharishpur PWSS with FHTC Block Panchla, District-Howrah(TSM/011532,SM/11723) | TSM/011532 | SM/11723 | Augmentation | MVS | Panchla | Ban Harishpur | null | OHR | Vested | 4 | 1 | 2453 | 3 | Possessed | IDT Done
44 | HOWRAH | Augmentation of Ground water based PWSS Mellok Brahman Dakuria(TSM/008640,SM/09347) | TSM/008640 | SM/09347 | Augmentation | MVS | Bagnan - I | Sabsit | null | Pump House | Vested | 38 | 1 | 0 | 0 | Identified | IDT Done
45 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Kajiakhali | null | Intake | Private | 115 | 1478 | 1050 | 0 | Possessed | null
46 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Duaniguzrat | null | OHR | Private | 100 | 1645 | 607 | 0 | Possessed | null
47 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Amardaha | null | OHR | Vested | 35 | 1399 | 440 | 0 | Possessed | IDT done
48 | HOWRAH | Augmentation of Nischintapur piped water supply scheme.(TSM/008092,SM/09720) | TSM/008092 | SM/09720 | Augmentation | MVS | Amta - II | Binalakrishnabati | null | Pump House | Vested | 106 | 1 | 1 | 0 | Possessed | null
49 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Naul | null | OHR | Donated | 9 | 1832 | 1993 | 0 | Possessed | Gift Deed done
50 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Bargram | null | OHR | Vested | 50 | 2741 | 1347 | 0 | Possessed | IDT done
51 | HOWRAH | Bhandardah PWSS with provision of FHTC connection(TSM/010904,SM/14197) | TSM/010904 | SM/14197 | New | MVS | Domjur | Bhandardaha (CT) | Private Land (Danga) (2nd TW Site) | Pump House | Private | 0 | 582 | 837 | 0 | Identified | null
52 | HOWRAH | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS.(TSM/008212,SM/09105) | TSM/008212 | SM/09105 | Retrofitting | MVS | Amta - I | Bhojan | null | OHR | Private | 158 | 1639 | 2162 | 0 | Identified | null
53 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - I | Shyampur | null | OHR | Private | 79 | 547 | 645 | 1 | Identified | null
54 | HOWRAH | Uttar Manasri Piped Water Supply Scheme.(TSM/004182,SM/18914) | TSM/004182 | SM/18914 | New | MVS | Udaynarayanpur | Uttar Manasri | Vested(Shali) | Pump House | Donated | 25 | 1 | 156 | 11 | Possessed | IDT pending
55 | HOWRAH | Augmentation of Keshabpur Water supply scheme(TSM/010465,SM/16947) | TSM/010465 | SM/16947 | Augmentation | SVS | Domjur | Kesabpur (CT) | null | OHR | Vested | 0 | 0 | 0 | 0 | Identified | null
56 | HOWRAH | Uttar Manasri Piped Water Supply Scheme.(TSM/004182,SM/18914) | TSM/004182 | SM/18914 | New | MVS | Udaynarayanpur | Uttar Manasri | Vested (Bastu) | OHR | Vested | 25 | 1 | 106 | 63 | Possessed | IDT pending
57 | HOWRAH | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah.(TSM/011056,SM/11641) | TSM/011056 | SM/11641 | New | MVS | Uluberia - II | Nayachak | null | Pump House | Vested | 57 | 1 | 0 | 0 | Identified | null
58 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015621,SM/13752) | TSM/015621 | SM/13752 | New | SVS | Domjur | Dakshin Jhapardaha (CT) | null | Pump House | Vested | 0 | 1 | 0 | 0 | Identified | null
59 | HOWRAH | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME.(TSM/015277,SM/14154) | TSM/015277 | SM/14154 | Augmentation | MVS | Panchla | Kuldanga | null | OHR | Vested | 9 | 0 | 0 | 0 | Possessed | PHE Land
60 | HOWRAH | Bedhi Chandrapur Piped Water Supply Scheme(TSM/012815,SM/18490) | TSM/012815 | SM/18490 | New | SVS | Udaynarayanpur | Bedhi Chandrapur | Vested (Samshan) | OHR | Vested | 61 | 1 | 1734 | 23 | Possessed | Lat- 22.639380°, Long- 87.957090° (IDT processing ongoing. Sent the documents to District authority.)
61 | HOWRAH | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte.(TSM/011688,SM/11458) | TSM/011688 | SM/11458 | New | MVS | Amta - I | Khardaha | Vested (Samsan) | OHR | Vested | 135 | 1 | 115 | 24 | Identified | IDT proposal sent
62 | HOWRAH | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district(TSM/015623,SM/13747) | TSM/015623 | SM/13747 | New | SVS | Bagnan - I | Hijlak | null | OHR | Vested | 61 | 1 | 1376 | 30 | Identified | null
63 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Uluberia - II | Khalisani (CT) | null | OHR | Vested | 0 | 1 | 608 | 0 | Identified | null
64 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Uluberia - II | Balarampota (CT) | null | OHR | Vested | 0 | 1 | 0 | 0 | Identified | null
65 | HOWRAH | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah.(TSM/011766,SM/11717) | TSM/011766 | SM/11717 | New | SVS | Bagnan - I | Chandrapur | null | Pump House | Private | 58 | 546 | 1301 | 39 | Identified | null
66 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Uluberia - II | Raghudebpur | null | OHR | Vested | 99 | 1 | 3036 | 0 | Identified | null
67 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - I | Rasti | null | OHR | Private | 73 | 5587 | 1440 | 0 | Possessed | null
68 | HOWRAH | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah.(TSM/011761,SM/11718) | TSM/011761 | SM/11718 | New | SVS | Bagnan - I | Ulanpara | null | Pump House | Vested | 57 | 1 | 1411 | 7 | Identified | null
69 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Panchla | Beldubi (CT) | null | OHR | Vested | 0 | 0 | 0 | 0 | Possessed | PHE Land
70 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah.(TSM/011679,SM/11221) | TSM/011679 | SM/11221 | New | MVS | Udaynarayanpur | Naranarayanpur Chak | null | OHR | Donated | 44 | 206 | 459 | 0 | Identified | null
71 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Birpur | null | OHR | Private | 45 | 265 | 0 | 0 | Possessed | Registration done
72 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Dakshin Santoshpur | vested(sali) | OHR | Vested | 56 | 1 | 386 | 45 | Identified | IDT sent
73 | HOWRAH | Makardaha PWSS with provision of FHTC in connection of Domjur Block(TSM/010688,SM/11159) | TSM/010688 | SM/11159 | Augmentation | MVS | Domjur | Makardaha (CT) | null | Pump House | Vested | 0 | 1 | 52 | 0 | Identified | null
74 | HOWRAH | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH(TSM/011637,SM/18562) | TSM/011637 | SM/18562 | New | MVS | Amta - I | Sarpota | null | Pump House | Vested | 196 | 339 | 297 | 3 | Identified | IDT proposal sent by BL & LRO
75 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Mansinhapur (CT) | Vested(Veri) | Pump House | Vested | 0 | 1 | 816 | 1 | Identified | IDT sent
76 | HOWRAH | Baniara PWSS with provision of FHTC connection(TSM/010919,SM/11722) | TSM/010919 | SM/11722 | New | MVS | Domjur | Baniara | null | Pump House | Private | 26 | 696 | 829 | 0 | Identified | null
77 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Patihal | Vested (Pukur) | OHR | Private | 49 | 3417 | 3319 | 46 | Identified | Recorded owner in Zilla Parishad
78 | HOWRAH | Khorda Etarai Piped Water Supply Scheme(TSM/012017,SM/11892) | TSM/012017 | SM/11892 | New | MVS | Udaynarayanpur | Khorda Etarai | Vested (Samshan) | OHR | Vested | 20 | 1 | 364 | 23 | Possessed | IDT pending
79 | HOWRAH | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme(TSM/017891,SM/18567) | TSM/017891 | SM/18567 | Augmentation | MVS | Amta - I | Khasnan | null | OHR | Donated | 139 | 1 | 587 | 39 | Identified | null
80 | HOWRAH | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah.(TSM/011056,SM/11641) | TSM/011056 | SM/11641 | New | MVS | Uluberia - II | Nayachak | null | Pump House | Vested | 57 | 1 | 76 | 0 | Identified | null
81 | HOWRAH | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1)(TSM/006301,SM/07074) | TSM/006301 | SM/07074 | Retrofitting | SVS | Panchla | Ranihati | null | Pump House | Vested | 17 | 0 | 0 | 3 | Not Identified | null
82 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block(TSM/006292,SM/07396) | TSM/006292 | SM/07396 | Retrofitting | MVS | Amta - I | Chandrapur | Private | Pump House | Private | 208 | 1 | 260 | 0 | Identified | null
83 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Jala Dhulagiri | null | OHR | Vested | 2 | 1 | 377 | 0 | Possessed | IDT done, Possession taken by PHED.
84 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block(TSM/006300,SM/07465) | TSM/006300 | SM/07465 | Retrofitting | MVS | Amta - II | Khariop | vested | OHR | Vested | 120 | 1 | 0 | 41 | Identified
85 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015622,SM/14155) | TSM/015622 | SM/14155 | New | SVS | Domjur | Domjur (CT) | null | OHR | Vested | 0 | 0 | 0 | 0 | Possessed | IDT done
86 | HOWRAH | BARRAMNAGAR PIPED WATER SUPPLY SCHEME.(TSM/015228,SM/13750) | TSM/015228 | SM/13750 | New | SVS | Uluberia - II | Barramnagar | null | Pump House | Vested | 97 | 1 | 1246 | 0 | Identified | null
87 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Mugkalyan | null | OHR | Vested | 89 | 1818 | 2788 | 1 | Identified | null
88 | HOWRAH | ICHAPUR PWSS(TSM/012520,SM/13629) | TSM/012520 | SM/13629 | New | MVS | Jagatballavpur | Ichhapur | Private | Pump House | Donated | 44 | 884 | 621 | 3 | Identified | null
89 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Halyan | null | OHR | Vested | 96 | 1 | 498 | 0 | Identified | null
90 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Ratanpur | null | OHR | Vested | 33 | 1 | 153 | 0 | Identified | IDT done
91 | HOWRAH | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah.(TSM/011909,SM/17175) | TSM/011909 | SM/17175 | New | MVS | Domjur | Uttar Jhapardaha | null | OHR | Vested | 9 | 1 | 803 | 0 | Possessed | IDT done
92 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block(TSM/006748,SM/07882) | TSM/006748 | SM/07882 | Retrofitting | MVS | Amta - I | Panpur | null | Pump House | Vested | 214 | 1 | 60 | 0 | Identified | null
93 | HOWRAH | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah.(TSM/011909,SM/17175) | TSM/011909 | SM/17175 | New | MVS | Domjur | Uttar Jhapardaha | null | Pump House | Vested | 9 | 238 | 415 | 1 | Identified | null
94 | HOWRAH | Ghuteghari Piped Water Supply Scheme(TSM/018482,SM/17198) | TSM/018482 | SM/17198 | New | SVS | Amta - I | Ghuteghari | null | OHR | Vested | 182 | 1 | 462 | 15 | Identified | null
95 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block(TSM/006748,SM/07882) | TSM/006748 | SM/07882 | Retrofitting | MVS | Amta - I | Panpur | vested | OHR | Vested | 214 | 1 | 0 | 0 | Identified | null
96 | HOWRAH | Makardaha PWSS with provision of FHTC in connection of Domjur Block(TSM/010688,SM/11159) | TSM/010688 | SM/11159 | Augmentation | MVS | Domjur | Makardaha (CT) | null | Pump House | Private | 0 | 585 | 2079 | 0 | Identified | null
97 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block(TSM/006746,SM/07883) | TSM/006746 | SM/07883 | Retrofitting | MVS | Amta - II | Jhamtia | null | OHR | Private | 98 | 102 | 615 | 10 | Possessed | PHE Land
98 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I)(TSM/006744,SM/07885) | TSM/006744 | SM/07885 | Retrofitting | MVS | Amta - II | Dakshin Bhatora | Private (Samsan) Rayat | OHR | Private | 79 | 3361 | 2561 | 33 | Identified | null
99 | HOWRAH | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district(TSM/015623,SM/13747) | TSM/015623 | SM/13747 | New | SVS | Bagnan - I | Hijlak | null | Pump House | Vested | 61 | 0 | 0 | 3 | Not Identified | null
100 | HOWRAH | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme(TSM/010806,SM/18398) | TSM/010806 | SM/18398 | Augmentation | MVS | Udaynarayanpur | Sibanipur | null | OHR | Vested | 35 | 1 | 293 | 0 | Identified | null
101 | HOWRAH | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC.(TSM/008354,SM/10020) | TSM/008354 | SM/10020 | Augmentation | MVS | Bagnan - I | Paschim Bainan (CT) | null | Pump House | Donated | 9 | 3112 | 4306 | 0 | Identified | null
102 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Kanyamani | null | OHR | Vested | 16 | 1 | 631 | 0 | Identified | null
103 | HOWRAH | Augmentation of Kanpur Piped water supply scheme (Zone-II)(TSM/008513,SM/10021) | TSM/008513 | SM/10021 | Augmentation | MVS | Amta - I | Basantapur (CT) | Vested(Bhagar) | Pump House | Vested | 189 | 1 | 1199 | 18 | Identified | IDT proposal pending
104 | HOWRAH | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah.(TSM/011301,SM/16760) | TSM/011301 | SM/16760 | New | MVS | Bagnan - I | Bangalpur | null | Pump House | Vested | 43 | 1 | 2096 | 0 | Possessed | IDT Done and possession handed over to PHE Dte.
105 | HOWRAH | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah.(TSM/011548,SM/11793) | TSM/011548 | SM/11793 | New | MVS | Amta - II | Jayanti | null | Pump House | Vested | 123 | 1 | 508 | 2 | Identified | null
106 | HOWRAH | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah.(TSM/011548,SM/11793) | TSM/011548 | SM/11793 | New | MVS | Amta - II | Jayanti | null | OHR | Vested | 123 | 1 | 316 | 33 | Possessed | null
107 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block(TSM/006293,SM/07395) | TSM/006293 | SM/07395 | Retrofitting | MVS | Amta - II | Beral | Vested, (Samsan) | OHR | Vested | 82 | 1 | 590 | 45 | Identified | IDT Proposal to be formed
108 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II(TSM/006294,SM/07464) | TSM/006294 | SM/07464 | Retrofitting | MVS | Amta - II | Jaypur | vested | Pump House | Vested | 105 | 1 | 3424 | 3 | Identified | IDT pending
109 | HOWRAH | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah.(TSM/011584,SM/12562) | TSM/011584 | SM/12562 | New | MVS | Panchla | Jala Bishwanathpur | null | OHR | Vested | 5 | 0 | 0 | 0 | Possessed | PHE land
110 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Ichhanagari | Vested(Sali) | OHR | Vested | 1 | 1 | 2395 | 45 | Identified | IDT sent
111 | HOWRAH | Augmentation of Nischintapur piped water supply scheme.(TSM/008092,SM/09720) | TSM/008092 | SM/09720 | Augmentation | MVS | Amta - II | Hanidaha | null | OHR | Vested | 108 | 1 | 1 | 28 | Possessed | null
112 | HOWRAH | Sonatala Piped Water Supply Scheme(TSM/015612,SM/14949) | TSM/015612 | SM/14949 | New | MVS | Udaynarayanpur | Sonatala | Vested | Pump House | Vested | 52 | 1 | 575 | 3 | Possessed | IDT pending
113 | HOWRAH | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah.(TSM/011056,SM/11641) | TSM/011056 | SM/11641 | New | MVS | Uluberia - II | Nayachak | Vested (Danga) | OHR | Vested | 57 | 1 | 62 | 35 | Identified | null
114 | HOWRAH | Augmentation of Ground water based PWSS Mellok Brahman Dakuria(TSM/008640,SM/09347) | TSM/008640 | SM/09347 | Augmentation | MVS | Bagnan - I | Sabsit | null | OHR | Vested | 38 | 1 | 1447 | 33 | Possessed | IDT done
115 | HOWRAH | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah.(TSM/015619,SM/18748) | TSM/015619 | SM/18748 | New | MVS | Uluberia - II | Kantaberia | null | Pump House | Private | 91 | 0 | 0 | 3 | Identified | null
116 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1)(TSM/006296,SM/07008) | TSM/006296 | SM/07008 | Retrofitting | SVS | Amta - II | Tajpur | null | Pump House | Private | 131 | 3277 | 1123 | 0 | Identified | null
117 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015621,SM/13752) | TSM/015621 | SM/13752 | New | SVS | Domjur | Dakshin Jhapardaha (CT) | null | Pump House | Vested | 0 | 1 | 0 | 0 | Identified | null
118 | HOWRAH | Augmentation of Ground water based PWSS Jujarsah(TSM/008639,SM/10146) | TSM/008639 | SM/10146 | Augmentation | MVS | Panchla | Shuvararah (CT) | null | Pump House | Donated | 6 | 0 | 5144 | 0 | Identified | null
119 | HOWRAH | Rejuvenation of Amta Piped water supply scheme.(TSM/005366,SM/08966) | TSM/005366 | SM/08966 | Augmentation | MVS | Amta - I | Madaria | null | Pump House | Vested | 145 | 1 | 1064 | 0 | Identified | null
120 | HOWRAH | Augmentation of Ground water based PWSS Kanupat.(TSM/008622,SM/09350) | TSM/008622 | SM/09350 | Augmentation | MVS | Udaynarayanpur | Dakshin Singti | PHE Land | OHR | Vested | 28 | 1 | 539 | 0 | Possessed | null
121 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara(TSM/008620,SM/09351) | TSM/008620 | SM/09351 | Augmentation | MVS | Jagatballavpur | Bhursit Bamunpara | null | Pump House | Vested | 25 | 1161 | 1005 | 0 | Possessed | PHE land
122 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme (TSM/005658,SM/06718) | TSM/005658 | SM/06718 | Retrofitting | SVS | Uluberia - II | Uttar Pirpur (CT) | Private (Danga) | Pump House | Private | 0 | 1751 | 633 | 3 | Identified | null
123 | HOWRAH | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur(TSM/011932,SM/11894) | TSM/011932 | SM/11894 | New | MVS | Domjur | Nonakundu | null | Pump House | Vested | 5 | 977 | 1699 | 0 | Identified | null
124 | HOWRAH | Sankhali Piped Water Supply Scheme(TSM/015853,SM/15289) | TSM/015853 | SM/15289 | New | SVS | Panchla | Sankhali | null | OHR | Vested | 19 | 1 | 1101 | 0 | Identified | null
125 | HOWRAH | Sonatala Piped Water Supply Scheme(TSM/015612,SM/14949) | TSM/015612 | SM/14949 | New | MVS | Udaynarayanpur | Sonatala | null | Pump House | Vested | 52 | 1 | 610 | 8 | Identified | null
126 | HOWRAH | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur(TSM/011932,SM/11894) | TSM/011932 | SM/11894 | New | MVS | Domjur | Mahishnala | null | OHR | Donated | 4 | 362 | 186 | 1 | Identified | null
127 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block(TSM/006295,SM/07010) | TSM/006295 | SM/07010 | Retrofitting | MVS | Amta - II | Narit | vested | OHR | Vested | 125 | 1 | 97 | 0 | Identified
128 | HOWRAH | Sonatala Piped Water Supply Scheme(TSM/015612,SM/14949) | TSM/015612 | SM/14949 | New | MVS | Udaynarayanpur | Sonatala | Vested (Danga) | OHR | Vested | 52 | 1 | 1907 | 24 | Possessed | IDT pending
129 | HOWRAH | Rudrapur PWSS with provision of FHTC connection.(TSM/010920,SM/11515) | TSM/010920 | SM/11515 | New | MVS | Domjur | Rudrapur | null | OHR | Vested | 16 | 1 | 695 | 0 | Possessed | IDT Done
130 | HOWRAH | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah.(TSM/011909,SM/17175) | TSM/011909 | SM/17175 | New | MVS | Domjur | Uttar Jhapardaha | null | Pump House | Vested | 9 | 238 | 756 | 1 | Identified | null
131 | HOWRAH | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME.(TSM/015269,SM/13749) | TSM/015269 | SM/13749 | New | MVS | Panchla | Gabberia (CT) | 4th TW Site | Pump House | Donated | 0 | 0 | 614 | 0 | Identified | null
132 | HOWRAH | Matinala Piped Water Supply Scheme(TSM/016162,SM/15285) | TSM/016162 | SM/15285 | New | MVS | Bagnan - II | Mellak | null | Pump House | Vested | 20 | 1 | 939 | 3 | Identified
133 | HOWRAH | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah.(TSM/015619,SM/18748) | TSM/015619 | SM/18748 | New | MVS | Uluberia - II | Kantaberia | null | OHR | Private | 91 | 0 | 0 | 25 | Identified | null
134 | HOWRAH | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah.(TSM/011491,SM/11853) | TSM/011491 | SM/11853 | New | MVS | Udaynarayanpur | Sultanpur | null | OHR | Vested | 8 | 1 | 271 | 0 | Identified | null
135 | HOWRAH | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme(TSM/010806,SM/18398) | TSM/010806 | SM/18398 | Augmentation | MVS | Udaynarayanpur | Sibanipur | null | OHR | Vested | 35 | 1 | 260 | 0 | Possessed | IDT Done
136 | HOWRAH | Augmentation of Ground Water Based PWSS for Shekrahati(TSM/008595,SM/09586) | TSM/008595 | SM/09586 | Augmentation | MVS | Jagatballavpur | Krishnanandapur | null | OHR | Vested | 20 | 0 | 0 | 0 | Possessed | PHE LAND
137 | HOWRAH | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah.(TSM/011491,SM/11853) | TSM/011491 | SM/11853 | New | MVS | Udaynarayanpur | Sitapur | null | OHR | Vested | 9 | 1 | 279 | 0 | Possessed | null
138 | HOWRAH | Ground Water Based Raspur PWSS(TSM/017956,SM/18719) | TSM/017956 | SM/18719 | New | MVS | Amta - I | Sameshwar | Vested | OHR | Vested | 151 | 1 | 412 | 33 | Identified | Requision sent for IDT to IR & WD Dept. WB
139 | HOWRAH | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah.(TSM/011795,SM/11790) | TSM/011795 | SM/11790 | New | SVS | Jagatballavpur | Shyampur | vested | OHR | Vested | 30 | 1 | 15 | 87 | Identified | null
140 | HOWRAH | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah.(TSM/011760,SM/11711) | TSM/011760 | SM/11711 | New | MVS | Domjur | Bipra Noapara (CT) | null | Pump House | Vested | 0 | 1 | 459 | 0 | Identified | null
141 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015610,SM/13751) | TSM/015610 | SM/13751 | New | MVS | Domjur | Dakshin Jhapardaha (CT) | null | Pump House | Vested | 0 | 0 | 0 | 3 | Not Identified | null
142 | HOWRAH | Matinala Piped Water Supply Scheme(TSM/016162,SM/15285) | TSM/016162 | SM/15285 | New | MVS | Bagnan - II | Mellak | null | OHR | Donated | 20 | 1188 | 1586 | 0 | Identified | null
143 | HOWRAH | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah.(TSM/011584,SM/12562) | TSM/011584 | SM/12562 | New | MVS | Panchla | Jala Bishwanathpur | null | Pump House | Donated | 5 | 1892 | 1367 | 0 | Identified | null
144 | HOWRAH | Ground Water Based Raspur PWSS(TSM/017956,SM/18719) | TSM/017956 | SM/18719 | New | MVS | Amta - I | Sameshwar | vested | Pump House | Vested | 151 | 1 | 490 | 3 | Identified | Requision sent for IDT to IR & WD Dept. WB
145 | HOWRAH | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah.(TSM/011600,SM/11000) | TSM/011600 | SM/11000 | New | MVS | Bagnan - I | Hature Kandarpapur | Vested (Samsan) | OHR | Vested | 49 | 1 | 593 | 36 | Possessed | null
146 | HOWRAH | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME.(TSM/014806,SM/18560) | TSM/014806 | SM/18560 | Augmentation | MVS | Panchla | Jayrampur | null | OHR | Vested | 14 | 0 | 0 | 0 | Possessed | PHE Land
147 | HOWRAH | Ground Water Based Water Supply Scheme for Ajangachhi PWSS(TSM/017917,SM/18561) | TSM/017917 | SM/18561 | New | MVS | Amta - II | Dhanyaghari | null | Pump House | Vested | 90 | 131 | 1808 | 0 | Identified | null
148 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015610,SM/13751) | TSM/015610 | SM/13751 | New | MVS | Domjur | Khantora (CT) | null | Pump House | Donated | 0 | 3962 | 1663 | 0 | Possessed | Gift Deed done
149 | HOWRAH | Baniban Zone-I Piped Water Supply Scheme(TSM/017947,SM/18566) | TSM/017947 | SM/18566 | New | MVS | Uluberia - II | Baniban Jagadishpur | null | Pump House | Private | 62 | 0 | 0 | 3 | Identified | null
150 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah(TSM/015621,SM/13752) | TSM/015621 | SM/13752 | New | SVS | Domjur | Dakshin Jhapardaha (CT) | null | Pump House | Vested | 0 | 1 | 0 | 0 | Identified | null
151 | HOWRAH | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur(TSM/011933,SM/11893) | TSM/011933 | SM/11893 | New | MVS | Domjur | Rajapur | null | Pump House | Vested | 11 | 1 | 280 | 0 | Identified | null
152 | HOWRAH | Khadinan Piped Water Supply Scheme(TSM/015626,SM/13847) | TSM/015626 | SM/13847 | New | SVS | Bagnan - I | Khadinan | null | Pump House | Vested | 59 | 1 | 1107 | 1 | Possessed | PHE Land
153 | HOWRAH | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur.(TSM/011009,SM/12270) | TSM/011009 | SM/12270 | New | MVS | Udaynarayanpur | Narikel Beria | null | Pump House | Vested | 170 | 1 | 1304 | 3 | Possessed | null
154 | HOWRAH | Augmentation of Maju piped water supply scheme.(TSM/008091,SM/10035) | TSM/008091 | SM/10035 | Augmentation | MVS | Jagatballavpur | Madhya Maju | 2nd TW Site | Pump House | Vested | 33 | 0 | 0 | 0 | Possessed | PHE Land
155 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Pratappur Krishnabati | Private (Samsan) | OHR | Vested | 23 | 18 | 81 | 11 | Identified | NOC Of Raiyat is collected by B.D.O, J.B pur
156 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Bamunpara | Vested(Danga P.Patit) | OHR | Vested | 16 | 1 | 718 | 56 | Identified | IDT sent
157 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Mugkalyan | null | Pump House | Private | 89 | 5717 | 2862 | 1 | Possessed | null
158 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - I | Alipur | null | OHR | Donated | 143 | 547 | 964 | 0 | Identified | null
159 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Tiorpara | null | OHR | Private | 119 | 4 | 734 | 0 | Possessed | Registration done
160 | HOWRAH | BARRAMNAGAR PIPED WATER SUPPLY SCHEME.(TSM/015228,SM/13750) | TSM/015228 | SM/13750 | New | SVS | Uluberia - II | Barramnagar | null | OHR | Vested | 97 | 1 | 1349 | 1 | Identified | null
161 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Manikpur | null | OHR | Vested | 21 | 1 | 106 | 0 | Identified | null
162 | HOWRAH | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah.(TSM/011600,SM/11000) | TSM/011600 | SM/11000 | New | MVS | Bagnan - I | Hature Kandarpapur | null | Pump House | Vested | 49 | 1 | 0 | 0 | Identified | null
163 | HOWRAH | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah.(TSM/011761,SM/11718) | TSM/011761 | SM/11718 | New | SVS | Bagnan - I | Ulanpara | null | OHR | Private | 57 | 2898 | 1783 | 17 | Identified | null
164 | HOWRAH | Bhandardah PWSS with provision of FHTC connection(TSM/010904,SM/14197) | TSM/010904 | SM/14197 | New | MVS | Domjur | Makardaha (CT) | null | Pump House | Vested | 0 | 0 | 0 | 3 | Identified | PHE land
165 | HOWRAH | Makardaha PWSS with provision of FHTC in connection of Domjur Block(TSM/010688,SM/11159) | TSM/010688 | SM/11159 | Augmentation | MVS | Domjur | Makardaha (CT) | null | Pump House | Vested | 0 | 1 | 354 | 0 | Identified | null
166 | HOWRAH | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME.(TSM/014806,SM/18560) | TSM/014806 | SM/18560 | Augmentation | MVS | Panchla | Deulpur | Vested Land(Danga Puratan Patit) | Pump House | Vested | 12 | 1 | 1998 | 0 | Identified | null
167 | HOWRAH | Bhandardah PWSS with provision of FHTC connection(TSM/010904,SM/14197) | TSM/010904 | SM/14197 | New | MVS | Domjur | Bhandardaha (CT) | null | Pump House | Vested | 0 | 0 | 0 | 3 | Not Identified | null
168 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Domjur | Prasastha | null | OHR | Vested | 29 | 1 | 395 | 1 | Identified | null
169 | HOWRAH | PANCHLA PIPED WATER SUPPLY SCHEME.(TSM/014879,SM/18563) | TSM/014879 | SM/18563 | New | SVS | Panchla | Panchla (CT) | null | Pump House | Vested | 0 | 0 | 0 | 3 | Not Identified | null
170 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Barunda | null | OHR | Private | 32 | 0 | 1815 | 0 | Identified | null
171 | HOWRAH | PANCHLA PIPED WATER SUPPLY SCHEME.(TSM/014879,SM/18563) | TSM/014879 | SM/18563 | New | SVS | Panchla | Panchla (CT) | Panchla | OHR | Donated | 0 | 8172 | 5038 | 33 | Identified | null
172 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Mukundapur | null | OHR | Vested | 18 | 1390 | 125 | 0 | Possessed | null
173 | HOWRAH | Khorda Etarai Piped Water Supply Scheme(TSM/012017,SM/11892) | TSM/012017 | SM/11892 | New | MVS | Udaynarayanpur | Etarai | Vested (Puratan Patit) | Pump House | Vested | 19 | 1 | 90 | 7 | Possessed | IDT pending
174 | HOWRAH | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME.(TSM/014806,SM/18560) | TSM/014806 | SM/18560 | Augmentation | MVS | Panchla | Kusadanga | null | Pump House | Vested | 13 | 0 | 0 | 0 | Possessed | PHE Land
175 | HOWRAH | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME.(TSM/015277,SM/14154) | TSM/015277 | SM/14154 | Augmentation | MVS | Panchla | Gondalpara | null | Pump House | Vested | 10 | 1 | 1354 | 0 | Possessed | IDT Done
176 | HOWRAH | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme(TSM/017891,SM/18567) | TSM/017891 | SM/18567 | Augmentation | MVS | Amta - I | Purba Gazipur | null | Pump House | Vested | 140 | 0 | 0 | 3 | Not Identified | null
177 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Kalinagar | null | OHR | Vested | 111 | 1 | 381 | 9 | Possessed | IDT done
178 | HOWRAH | Ground Water Based Water Supply Scheme for Ajangachhi PWSS(TSM/017917,SM/18561) | TSM/017917 | SM/18561 | New | MVS | Amta - II | Takipara | null | Pump House | Vested | 87 | 1 | 0 | 0 | Identified | null
179 | HOWRAH | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah.(TSM/011570,SM/11719) | TSM/011570 | SM/11719 | New | MVS | Amta - II | Jhikhira | null | OHR | Private | 65 | 2086 | 1066 | 18 | Identified | null
180 | HOWRAH | Ground Water Based Water Supply Scheme for Ajangachhi PWSS(TSM/017917,SM/18561) | TSM/017917 | SM/18561 | New | MVS | Amta - II | Takipara | null | OHR | Vested | 87 | 1 | 1132 | 0 | Identified | null
181 | HOWRAH | Baniban Zone-I Piped Water Supply Scheme(TSM/017947,SM/18566) | TSM/017947 | SM/18566 | New | MVS | Uluberia - II | Baniban Jagadishpur | null | OHR | Private | 62 | 0 | 0 | 23 | Identified | null
182 | HOWRAH | Gopalpur Piped Water Supply Scheme(TSM/015625,SM/13748) | TSM/015625 | SM/13748 | New | MVS | Bagnan - I | Gopalpur | null | OHR | Private | 41 | 0 | 32 | 0 | Identified | null
183 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Ichhanagari | null | Pump House | Vested | 1 | 0 | 0 | 3 | Not Identified | null
184 | HOWRAH | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah.(TSM/011550,SM/11720) | TSM/011550 | SM/11720 | New | MVS | Amta - II | Kulia | Vested (Samsan) | Pump House | Vested | 85 | 1 | 345 | 2 | Possessed | Mutation Done
185 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme(TSM/005649,SM/06716) | TSM/005649 | SM/06716 | Retrofitting | MVS | Amta - I | Kotalpara | null | Pump House | Private | 149 | 639 | 704 | 0 | Identified | null
186 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Ramchandrapur (CT) | null | WTP | Vested | 0 | 1 | 0 | 0 | Possessed | null
187 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Kamalapur | Private(Puratan Patit) | Pump House | Private | 53 | 337 | 1869 | 9 | Identified | NOC Of Raiyat is collected by B.D.O, J.B pur
188 | HOWRAH | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah.(TSM/011550,SM/11720) | TSM/011550 | SM/11720 | New | MVS | Amta - II | Ghoraberia | vested | OHR | Vested | 80 | 1 | 504 | 33 | Possessed | Mutation Done
189 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Ramchandrapur (CT) | null | WTP | Vested | 0 | 1 | 197 | 2 | Possessed | null
190 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Godaria | Private(Doba ) | OHR | Private | 6 | 185 | 195 | 24 | Identified | NOC Of Raiyat is collected by B.D.O, J.B pur
191 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Panchla | Sahapur (CT) | null | OHR | Private | 0 | 0 | 0 | 0 | Possessed | PHE land
192 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Jagatballavpur | Vested(Pukur Par) | OHR | Vested | 4 | 1 | 1900 | 33 | Identified | IDT sent
193 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara(TSM/008620,SM/09351) | TSM/008620 | SM/09351 | Augmentation | MVS | Jagatballavpur | Dhasa | null | OHR | Vested | 28 | 1 | 963 | 1 | Possessed | PHE land
194 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme(TSM/005652,SM/06788) | TSM/005652 | SM/06788 | Retrofitting | MVS | Amta - II | Paschim Gazipur | null | OHR | Private | 115 | 1844 | 2481 | 0 | Identified | null
195 | HOWRAH | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah.(TSM/011584,SM/12562) | TSM/011584 | SM/12562 | New | MVS | Panchla | Jala Bishwanathpur | null | Pump House | Donated | 5 | 1216 | 1367 | 0 | Identified | null
196 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme (TSM/005658,SM/06718) | TSM/005658 | SM/06718 | Retrofitting | SVS | Uluberia - II | Uttar Pirpur (CT) | Private (Danga) | OHR | Private | 0 | 1789 | 1020 | 20 | Possessed | Registration done
197 | HOWRAH | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah.(TSM/011584,SM/12562) | TSM/011584 | SM/12562 | New | MVS | Panchla | Jala Bishwanathpur | null | Pump House | Vested | 5 | 1 | 1264 | 2 | Identified | null
198 | HOWRAH | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh(TSM/011062,SM/15186) | TSM/011062 | SM/15186 | New | MVS | Uluberia - II | Jagarampur | Vested (Danga, Puratan patit) | OHR | Vested | 59 | 1 | 888 | 54 | Identified | null
199 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block(TSM/006746,SM/07883) | TSM/006746 | SM/07883 | Retrofitting | MVS | Amta - II | Jhamtia | null | Pump House | Vested | 98 | 1 | 416 | 4 | Possessed | PHE Land
200 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I)(TSM/006744,SM/07885) | TSM/006744 | SM/07885 | Retrofitting | MVS | Amta - II | Dakshin Bhatora | Private | Pump House | Private | 79 | 2131 | 2456 | 3 | Identified | null
201 | HOWRAH | Sherpur Piped Water Supply Scheme(TSM/018486,SM/18426) | TSM/018486 | SM/18426 | New | MVS | Amta - I | Madhyakul | Vested (Samshan) | Pump House | Vested | 217 | 1 | 760 | 3 | Identified | IDT proposal sent
202 | HOWRAH | Augmentation of Ground water based PWSS Mankur Deulgram(TSM/008627,SM/09349) | TSM/008627 | SM/09349 | Augmentation | MVS | Bagnan - I | Deulgram (CT) | null | OHR | Vested | 4 | 0 | 0 | 3 | Not Identified | null
203 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block(TSM/006293,SM/07395) | TSM/006293 | SM/07395 | Retrofitting | MVS | Amta - II | Beral | private | Pump House | Private | 82 | 602 | 1381 | 6 | Identified | null
204 | HOWRAH | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah.(TSM/011795,SM/11790) | TSM/011795 | SM/11790 | New | SVS | Jagatballavpur | Shyampur | private | OHR | Private | 30 | 18 | 333 | 32 | Identified | null
205 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara(TSM/008620,SM/09351) | TSM/008620 | SM/09351 | Augmentation | MVS | Jagatballavpur | Ghanashyambati | null | Pump House | Donated | 26 | 80 | 273 | 0 | Identified | null
206 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Jagatballavpur | Vested (Shali) | OHR | Vested | 4 | 1 | 158 | 33 | Identified | IDT sent
207 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006747,SM/07881) | TSM/006747 | SM/07881 | Retrofitting | MVS | Udaynarayanpur | Sonagachhi | null | Pump House | Private | 40 | 285 | 95 | 3 | Identified | null
208 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006747,SM/07881) | TSM/006747 | SM/07881 | Retrofitting | MVS | Udaynarayanpur | Sonagachhi | (Private) Bastu | Pump House | Private | 40 | 186 | 140 | 5 | Identified | null
209 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006747,SM/07881) | TSM/006747 | SM/07881 | Retrofitting | MVS | Udaynarayanpur | Sonagachhi | (Private) Danga | OHR | Private | 40 | 186 | 138 | 13 | Identified | Cabinet Approval Send.
210 | HOWRAH | Augmentation of Nischintapur piped water supply scheme.(TSM/008092,SM/09720) | TSM/008092 | SM/09720 | Augmentation | MVS | Amta - II | Binalakrishnabati | null | Pump House | Vested | 106 | 1 | 1 | 3 | Possessed | null
211 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II)(TSM/006745,SM/07884) | TSM/006745 | SM/07884 | Retrofitting | SVS | Amta - II | Uttar Bhatora | null | OHR | Vested | 78 | 1 | 0 | 3 | Identified | null
212 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II)(TSM/006745,SM/07884) | TSM/006745 | SM/07884 | Retrofitting | SVS | Amta - II | Uttar Bhatora | null | OHR | Vested | 78 | 1 | 0 | 3 | Identified | null
213 | HOWRAH | Rudrapur PWSS with provision of FHTC connection.(TSM/010920,SM/11515) | TSM/010920 | SM/11515 | New | MVS | Domjur | Rudrapur | null | Pump House | Donated | 16 | 844 | 1313 | 0 | Identified | null
214 | HOWRAH | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC(TSM/010977,SM/11572) | TSM/010977 | SM/11572 | New | MVS | Udaynarayanpur | Par Radhanagar | Vested(Shali) | OHR | Vested | 176 | 1 | 458 | 40 | Possessed | IDT pending
215 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block(TSM/006742,SM/07886) | TSM/006742 | SM/07886 | Retrofitting | MVS | Amta - II | Sehagari | null | Pump House | Vested | 112 | 1 | 120 | 2 | Identified | IDT Pending
216 | HOWRAH | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme(TSM/010806,SM/18398) | TSM/010806 | SM/18398 | Augmentation | MVS | Udaynarayanpur | Jangalpara Belgram | null | Pump House | Vested | 36 | 1 | 1465 | 0 | Identified | null
217 | HOWRAH | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME.(TSM/015269,SM/13749) | TSM/015269 | SM/13749 | New | MVS | Panchla | Mallik Bagan | null | OHR | Vested | 7 | 5219 | 3110 | 77 | Possessed | Already recorded in favour of PHE in
218 | HOWRAH | Rudrapur PWSS with provision of FHTC connection.(TSM/010920,SM/11515) | TSM/010920 | SM/11515 | New | MVS | Domjur | Oadipur | null | Pump House | Donated | 17 | 605 | 657 | 0 | Identified | null
219 | HOWRAH | Shibgachhia Piped Water Supply Scheme(TSM/018487,SM/18193) | TSM/018487 | SM/18193 | New | SVS | Amta - II | Shibgachhia | null | Pump House | Vested | 76 | 1 | 1 | 8 | Identified | null
220 | HOWRAH | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah.(TSM/012056,SM/13770) | TSM/012056 | SM/13770 | New | MVS | Jagatballavpur | Marghurali | vested | OHR | Vested | 41 | 1 | 232 | 33 | Identified | null
221 | HOWRAH | Dakshin Panchla Piped Water Supply Scheme(TSM/018488,SM/17196) | TSM/018488 | SM/17196 | New | SVS | Panchla | Dakshin Panchla | Private (Shali) | OHR | Private | 23 | 195 | 302 | 25 | Possessed | Consent letter for sell from Rayati.
222 | HOWRAH | Jaynagar Piped Water Supply Scheme(TSM/018489,SM/14865) | TSM/018489 | SM/14865 | New | MVS | Panchla | Jaynagar | null | Pump House | Vested | 16 | 0 | 0 | 6 | Not Identified | JL-15
223 | HOWRAH | Rejuvenation of Amta Piped water supply scheme.(TSM/005366,SM/08966) | TSM/005366 | SM/08966 | Augmentation | MVS | Amta - I | Ranapara | null | OHR | Vested | 141 | 756 | 968 | 0 | Possessed | null
224 | HOWRAH | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME.(TSM/015269,SM/13749) | TSM/015269 | SM/13749 | New | MVS | Panchla | Mallik Bagan | null | Pump House | Vested | 7 | 5219 | 3158 | 0 | Possessed | Already recorded in favour of PHE in
225 | HOWRAH | Bedhi Chandrapur Piped Water Supply Scheme(TSM/012815,SM/18490) | TSM/012815 | SM/18490 | New | SVS | Udaynarayanpur | Bedhi Chandrapur | Vested | OHR | Vested | 61 | 1 | 345 | 7 | Possessed | Lat-22.637638° , Long-87.957243°(IDT processing ongoing. Sent the documents to District authority.)
226 | HOWRAH | Sankhali Piped Water Supply Scheme(TSM/015853,SM/15289) | TSM/015853 | SM/15289 | New | SVS | Panchla | Sankhali | Sankhali | Pump House | Vested | 19 | 1 | 1114 | 0 | Identified | null
227 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme(TSM/005649,SM/06716) | TSM/005649 | SM/06716 | Retrofitting | MVS | Amta - I | Khosalpur | null | Pump House | Private | 202 | 1102 | 21 | 0 | Identified | null
228 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme(TSM/005649,SM/06716) | TSM/005649 | SM/06716 | Retrofitting | MVS | Amta - I | Khosalpur | null | OHR | Private | 202 | 2089 | 1760 | 0 | Identified | null
229 | HOWRAH | Paschim Panchla Piped Water Supply Scheme.(TSM/014766,SM/13768) | TSM/014766 | SM/13768 | New | SVS | Panchla | Paschim Panchla | null | OHR | Donated | 22 | 0 | 1378 | 25 | Identified | null
230 | HOWRAH | Augmentation of Ground Water Based PWSS for Shekrahati(TSM/008595,SM/09586) | TSM/008595 | SM/09586 | Augmentation | MVS | Jagatballavpur | Narendrapur | null | Pump House | Vested | 29 | 0 | 0 | 0 | Possessed | PHE LAND
231 | HOWRAH | Sibpur Piped Water Supply Scheme.(TSM/014685,SM/13769) | TSM/014685 | SM/13769 | New | SVS | Udaynarayanpur | Sibpur | Vested (Danga) | OHR | Vested | 18 | 1 | 6462 | 34 | Possessed | IDT pending
232 | HOWRAH | Augmentation of Ground Water Based PWSS for Shekrahati(TSM/008595,SM/09586) | TSM/008595 | SM/09586 | Augmentation | MVS | Jagatballavpur | Sekrahati | null | Pump House | Vested | 21 | 1 | 588 | 0 | Identified | null
233 | HOWRAH | Augmentation of Maju piped water supply scheme.(TSM/008091,SM/10035) | TSM/008091 | SM/10035 | Augmentation | MVS | Jagatballavpur | Madhya Maju | 3rd TW Site | Pump House | Vested | 33 | 0 | 0 | 0 | Possessed | PHE Land
234 | HOWRAH | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah.(TSM/012056,SM/13770) | TSM/012056 | SM/13770 | New | MVS | Jagatballavpur | Nimabalia | null | Pump House | Vested | 42 | 1 | 129 | 0 | Identified | null
235 | HOWRAH | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS.(TSM/008212,SM/09105) | TSM/008212 | SM/09105 | Retrofitting | MVS | Amta - I | Bhojan | null | Pump House | Donated | 158 | 1059 | 286 | 0 | Identified | null
236 | HOWRAH | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block.(TSM/011001,SM/11573) | TSM/011001 | SM/11573 | New | MVS | Udaynarayanpur | Paliara | Vested | Pump House | Vested | 173 | 1 | 1448 | 3 | Possessed | IDT done.
237 | HOWRAH | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block.(TSM/011001,SM/11573) | TSM/011001 | SM/11573 | New | MVS | Udaynarayanpur | Gauranga Chak | Vested | Pump House | Vested | 172 | 1 | 204 | 3 | Possessed | IDT done.
238 | HOWRAH | Augmentation of Keshabpur Water supply scheme(TSM/010465,SM/16947) | TSM/010465 | SM/16947 | Augmentation | SVS | Domjur | Kesabpur (CT) | null | Pump House | Vested | 0 | 1 | 2205 | 0 | Identified | null
239 | HOWRAH | Rejuvenation of Amta Piped water supply scheme.(TSM/005366,SM/08966) | TSM/005366 | SM/08966 | Augmentation | MVS | Amta - I | Guzarpur | null | Pump House | Vested | 207 | 1517 | 29 | 0 | Identified | null
240 | HOWRAH | Banharishpur PWSS with FHTC Block Panchla, District-Howrah(TSM/011532,SM/11723) | TSM/011532 | SM/11723 | Augmentation | MVS | Panchla | Ban Harishpur | null | Pump House | Donated | 4 | 485 | 1954 | 0 | Identified | null
241 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I)(TSM/005647,SM/06785) | TSM/005647 | SM/06785 | Retrofitting | MVS | Amta - I | Kasra | private(sali,bastu) | Pump House | Private | 203 | 1102 | 21 | 4 | Identified | Proposal sent for cabinet approval
242 | HOWRAH | Rejuvenation of Amta Piped water supply scheme.(TSM/005366,SM/08966) | TSM/005366 | SM/08966 | Augmentation | MVS | Amta - I | Madaria | null | OHR | Vested | 145 | 1 | 1013 | 0 | Identified | null
243 | HOWRAH | Augmentation of Ground water based PWSS Pulgustia(TSM/008637,SM/10143) | TSM/008637 | SM/10143 | Augmentation | MVS | Jagatballavpur | Dwipa | null | Pump House | Vested | 71 | 0 | 0 | 0 | Possessed | PHE Land
244 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Chak Kamala | null | OHR | Vested | 23 | 1 | 1509 | 0 | Identified | null
245 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - I | Ichhapur | null | OHR | Vested | 127 | 1 | 539 | 0 | Possessed | IDT done
246 | HOWRAH | Paschim Panchla Piped Water Supply Scheme.(TSM/014766,SM/13768) | TSM/014766 | SM/13768 | New | SVS | Panchla | Paschim Panchla | null | Pump House | Donated | 22 | 1139 | 1784 | 0 | Identified | null
247 | HOWRAH | Chakur water supply scheme.(TSM/008182,SM/08987) | TSM/008182 | SM/08987 | New | SVS | Bagnan - I | Chakur | null | Pump House | Vested | 11 | 1 | 1077 | 1 | Possessed | IDT Done and possession handed over to PHE Dte.
248 | HOWRAH | Sibpur Piped Water Supply Scheme.(TSM/014685,SM/13769) | TSM/014685 | SM/13769 | New | SVS | Udaynarayanpur | Sibpur | Vested (Danga) | Pump House | Vested | 18 | 1 | 6400 | 3 | Possessed | IDT pending
249 | HOWRAH | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah.(TSM/011600,SM/11000) | TSM/011600 | SM/11000 | New | MVS | Bagnan - I | Natibpur | null | Pump House | Vested | 52 | 1 | 0 | 0 | Identified | null
250 | HOWRAH | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah.(TSM/011909,SM/17175) | TSM/011909 | SM/17175 | New | MVS | Domjur | Uttar Jhapardaha | null | Pump House | Donated | 9 | 2690 | 3762 | 0 | Identified | null
251 | HOWRAH | Sealdanga Piped Water Supply Scheme(TSM/018484,SM/14866) | TSM/018484 | SM/14866 | New | MVS | Jagatballavpur | Sial Danga | null | Pump House | Private | 59 | 1087 | 2605 | 0 | Identified | null
252 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block(TSM/006749,SM/07880) | TSM/006749 | SM/07880 | Retrofitting | MVS | Udaynarayanpur | Chitrasenpur | Private(Shali) | OHR | Vested | 55 | 1792 | 2749 | 15 | Identified | null
253 | HOWRAH | Sealdanga Piped Water Supply Scheme(TSM/018484,SM/14866) | TSM/018484 | SM/14866 | New | MVS | Jagatballavpur | Sial Danga | null | OHR | Private | 59 | 160 | 2803 | 33 | Identified | null
254 | HOWRAH | Augmentation of Ground water based PWSS Pulgustia(TSM/008637,SM/10143) | TSM/008637 | SM/10143 | Augmentation | MVS | Jagatballavpur | Nalda | Vested (Bastu) | Pump House | Vested | 69 | 1 | 1511 | 5 | Identified | null
255 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Ramchandrapur (CT) | null | WTP | Vested | 0 | 1 | 216 | 1 | Possessed | null
256 | HOWRAH | Augmentation of Maju piped water supply scheme.(TSM/008091,SM/10035) | TSM/008091 | SM/10035 | Augmentation | MVS | Jagatballavpur | Madhya Maju | null | OHR | Vested | 33 | 0 | 0 | 0 | Possessed | PHE Land
257 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Masila | null | OHR | Vested | 24 | 0 | 0 | 0 | Possessed | null
258 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah.(TSM/011679,SM/11221) | TSM/011679 | SM/11221 | New | MVS | Udaynarayanpur | Naranarayanpur Chak | null | Pump House | Vested | 44 | 1 | 433 | 0 | Possessed | IDT Done
259 | HOWRAH | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme(TSM/010806,SM/18398) | TSM/010806 | SM/18398 | Augmentation | MVS | Udaynarayanpur | Sibanipur | null | Pump House | Vested | 35 | 1 | 159 | 0 | Possessed | IDT Done
260 | HOWRAH | Augmentation of Bamunhati Water Supply Scheme(TSM/012517,SM/12874) | TSM/012517 | SM/12874 | Augmentation | MVS | Uluberia - II | Bamunhati | null | Pump House | Private | 11 | 448 | 236 | 0 | Identified | Cabinet approval not yet received.
261 | HOWRAH | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah.(TSM/011420,SM/11007) | TSM/011420 | SM/11007 | New | MVS | Bagnan - I | Murgaberia | Murgaberia | Pump House | Donated | 55 | 0 | 0 | 3 | Possessed | null
262 | HOWRAH | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH(TSM/011637,SM/18562) | TSM/011637 | SM/18562 | New | MVS | Amta - I | Baneshwarpur | null | OHR | Vested | 194 | 507 | 89 | 25 | Identified | IDT proposal sent by BL & LRO
263 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Chatur Bhujkathi | null | OHR | Vested | 23 | 1 | 189 | 0 | Identified | null
264 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah.(TSM/011679,SM/11221) | TSM/011679 | SM/11221 | New | MVS | Udaynarayanpur | Chak Baharampur | null | Pump House | Donated | 30 | 1245 | 579 | 0 | Possessed | Registration and gift deed done
265 | HOWRAH | Shibgachhia Piped Water Supply Scheme(TSM/018487,SM/18193) | TSM/018487 | SM/18193 | New | SVS | Amta - II | Shibgachhia | null | OHR | Vested | 76 | 1 | 1616 | 33 | Identified | null
266 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah.(TSM/011678,SM/11222) | TSM/011678 | SM/11222 | New | MVS | Amta - II | Saoria | vested | Pump House | Vested | 113 | 1 | 1384 | 11 | Possessed | Mutation Done
267 | HOWRAH | Baniara PWSS with provision of FHTC connection(TSM/010919,SM/11722) | TSM/010919 | SM/11722 | New | MVS | Domjur | Baniara | Vested (Path) (OHR Site) | OHR | Vested | 26 | 634 | 1238 | 0 | Identified | null
268 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Anantabati | private | OHR | Private | 58 | 1648 | 159 | 14 | Identified | NOC Of Raiyat is collected by B.D.O, J.B pur
269 | HOWRAH | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC.(TSM/008354,SM/10020) | TSM/008354 | SM/10020 | Augmentation | MVS | Bagnan - I | Paschim Bainan (CT) | null | Pump House | Donated | 9 | 602 | 806 | 13 | Identified | null
270 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Bargachhia | vested(samsan) | Pump House | Vested | 51 | 1 | 1398 | 1 | Identified | IDT sent
271 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Bagnan - II | Kamardaha | null | OHR | Private | 28 | 971 | 355 | 0 | Identified | null
272 | HOWRAH | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur(TSM/011933,SM/11893) | TSM/011933 | SM/11893 | New | MVS | Domjur | Khas Mara | vested (Sali) | OHR | Vested | 13 | 1 | 1096 | 35 | Possessed | null
273 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Tripurapur | null | OHR | Vested | 59 | 1058 | 2 | 0 | Possessed | IDT done
274 | HOWRAH | Augmentation of Keshabpur Water supply scheme(TSM/010465,SM/16947) | TSM/010465 | SM/16947 | Augmentation | SVS | Domjur | Kesabpur (CT) | null | Pump House | Vested | 0 | 1 | 1 | 0 | Identified | null
275 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - II | Sadashibpur | null | OHR | Vested | 61 | 1 | 24 | 0 | Identified | null
276 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Shyampur - I | Bar Kalia | null | OHR | Vested | 140 | 1 | 560 | 0 | Identified | null
277 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (TSM/019280,SM/19186) | TSM/019280 | SM/19186 | Augmentation | MVS | Uluberia - I | Mongrajpur | null | OHR | Private | 31 | 4 | 881 | 0 | Possessed | Registration done
278 | HOWRAH | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME.(TSM/015277,SM/14154) | TSM/015277 | SM/14154 | Augmentation | MVS | Panchla | Gondalpara | Vested (2nd Tubewell) | Pump House | Vested | 10 | 1 | 1404 | 0 | Possessed | IDT Done
279 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Kamalapur | Vested(Samsan) | OHR | Vested | 53 | 1 | 1005 | 49 | Identified | IDT sent
280 | HOWRAH | Kamina Piped Water Supply Scheme with provision of FHTC(TSM/011290,SM/16927) | TSM/011290 | SM/16927 | New | MVS | Uluberia - II | Kamina | null | Pump House | Vested | 3 | 1 | 475 | 0 | Possessed | null
281 | HOWRAH | Augmentation of Ground water PWSS for Islampur(TSM/008589,SM/09428) | TSM/008589 | SM/09428 | Augmentation | MVS | Jagatballavpur | Islampur | null | Pump House | Vested | 76 | 0 | 0 | 0 | Possessed | PHE Land
282 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Shibnandabati | null | Pump House | Vested | 9 | 0 | 0 | 3 | Not Identified | null
283 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division(TSM/010279,SM/14095) | TSM/010279 | SM/14095 | Augmentation | MVS | Jagatballavpur | Naikuli | Vested(Nayanjuli ), Zilla Parishad Land | Pump House | Vested | 11 | 1 | 93 | 2 | Identified | null
284 | HOWRAH | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte.(TSM/008801,SM/09930) | TSM/008801 | SM/09930 | Augmentation | MVS | Amta - I | Barue | (Private) Puratan Danga | Pump House | Private | 185 | 946 | 533 | 1 | Possessed | Old scheme possessed by PHED
285 | HOWRAH | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah.(TSM/011420,SM/11007) | TSM/011420 | SM/11007 | New | MVS | Bagnan - I | Murgaberia | Murgaberia | OHR | Vested | 55 | 1 | 555 | 26 | Possessed | null
286 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Panchla | Paniara (CT) | null | OHR | Vested | 0 | 1 | 0 | 0 | Possessed | null
287 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme(TSM/019257,SM/19187) | TSM/019257 | SM/19187 | Augmentation | MVS | Sankrail | Ramchandrapur (CT) | null | OHR | Vested | 0 | 1 | 349 | 0 | Possessed | null