## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 | Office of the CE,Head Quarter | 0 | 0 | 12
2 | Alipore Division | 427 | 5 | 18
3 | Barasat Division | 213 | 1 | 26
4 | Nadia Division | 0 | 2 | 2
5 | Murshidabad Division | 390 | 17 | 22
6 | North 24 Pgs W/S Division I | 73 | 0 | 9
7 | Midnapore Division | 89 | 11 | 40
8 | Tamluk Division | 73 | 1 | 20
9 | Bankura Division | 289 | 82 | 33
10 | RCFA Division I | 35 | 0 | 9
11 | Nadia Arsenic Division I | 29 | 9 | 10
12 | Durgapur W/S Division | 57 | 5 | 3
13 | Purulia Division | 88 | 1 | 8
14 | Howrah Division | 1 | 3 | 4
15 | Hooghly Division | 328 | 6 | 11
16 | Burdwan Division | 98 | 5 | 14
17 | Birbhum Division | 182 | 5 | 14
18 | Raiganj Division | 100 | 5 | 21
19 | Jalpaiguri Division | 104 | 0 | 22
20 | Coochbehar Division | 259 | 0 | 12
21 | Siliguri W/S Division | 56 | 0 | 4
22 | Neorakhola W/S Mnt. Division | 244 | 21 | 73
23 | Darjeeling Division | 6 | 0 | 1
24 | Kalimpong Division | 23 | 1 | 0
25 | Malda Division | 171 | 0 | 8
26 | Malda Arsenic Area W/S Division | 61 | 0 | 4
27 | Balurghat Division | 211 | 4 | 8
28 | Electrical Division | 4 | 0 | 1
29 | South 24 Pgs Mechanical Division | 15 | 0 | 5
30 | Central Mechanical Division | 2 | 0 | 1
31 | Asansol Mechanical Division | 3 | 0 | 4
32 | Purulia Mechanical Division | 2 | 0 | 2
33 | Bolpur Mechanical Division | 1 | 0 | 2
34 | Midnapore Mechanical Division | 34 | 7 | 244
35 | Bankura Mechanical Division | 12 | 0 | 5
36 | Resources Division | 1 | 0 | 63
37 | Eastern Mechanical Division | 19 | 1 | 316
38 | Malda Mechanical Division | 9 | 0 | 35
39 | Northern Mechanical Division | 0 | 19 | 1
40 | Special Investigation Division | 0 | 0 | 0
41 | Survey Division | 0 | 0 | 0
42 | Investigation Unit | 0 | 1 | 6
43 | Planning and Design Division IV | 0 | 0 | 7
44 | South 24 Pgs. W/S Division - I | 330 | 1 | 15
45 | Barasat Arsenic Division | 21 | 0 | 7
46 | Nadia Arsenic Civil Division II | 60 | 0 | 0
47 | Berhampur Division I | 46 | 2 | 1
48 | Berhampur M/E Division | 24 | 0 | 93
49 | WSSO | 0 | 0 | 0
50 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
51 | Alipurduar Division | 192 | 7 | 3
52 | Kurseong Division | 11 | 0 | 1
53 | Northern Mechanical Division II | 15 | 0 | 27
54 | Project Implementation Unit,Purba Midnapur(ADB) | 0 | 0 | 0
55 | Jhargram Division | 27 | 6 | 24
56 | Jhargram Mechanical Division | 95 | 0 | 126
Total |  | 4530 | 228 | 1398