## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | TSM/006854 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 01/01/2021 | 31/10/2023 | 12/06/2023 | 0 | 1016 | inf | nan | 96 | 0
2 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | TSM/006857 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 20/02/2021 | 30/06/2023 | 12/06/2023 | 0 | 1557 | inf | nan | 91 | 0
3 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme includ | SM/07400 | TSM/006856 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 20/02/2021 | 30/06/2023 | 12/06/2023 | 0 | 1774 | inf | nan | 91 | 0
4 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | TSM/006847 | Retrofitting |  |  |  | 29/12/2020 | 02/03/2023 | 31/03/2023 | 12/06/2023 | 0 | 1280 | inf | nan | 100 | 0
5 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | SM/07402 | TSM/006800 | Retrofitting |  |  |  | 29/12/2020 | 08/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 1276 | inf | nan | 100 | 0
6 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | TSM/006812 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 02/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1536 | inf | nan | 92 | 0
7 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | SM/07404 | TSM/006851 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 04/01/2021 | 31/03/2024 | 12/06/2023 | 0 | 1263 | inf | nan | 82 | 0
8 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07405 | TSM/006813 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 01/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1536 | inf | nan | 91 | 0
9 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme includin | SM/07406 | TSM/006852 | Retrofitting |  |  |  | 29/12/2020 | 24/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 1328 | inf | nan | 100 | 0
10 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme including | SM/07407 | TSM/006853 | Retrofitting |  |  |  | 29/12/2020 | 24/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 1328 | inf | nan | 100 | 0
11 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | TSM/006855 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 01/01/2021 | 01/07/2023 | 12/06/2023 | 0 | 1158 | inf | nan | 96 | 0
12 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | TSM/006849 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 05/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 927 | inf | nan | 89 | 0
13 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl | SM/07410 | TSM/006803 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 29/12/2020 | 04/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 880 | inf | nan | 82 | 0
14 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | SM/07411 | TSM/006805 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 15/03/2021 | 31/12/2023 | 12/06/2023 | 0 | 2943 | inf | nan | 91 | 0
15 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | SM/07412 | TSM/006806 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 15/03/2021 | 31/12/2023 | 12/06/2023 | 0 | 4374 | inf | nan | 95 | 0
16 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | TSM/006858 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 02/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1957 | inf | nan | 95 | 0
17 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07416 | TSM/006804 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 29/12/2020 | 04/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1957 | inf | nan | 91 | 0
18 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | TSM/006799 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 31/12/2020 | 05/01/2021 | 31/12/2023 | 12/06/2023 | 0 | 1104 | inf | nan | 91 | 0
19 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | TSM/006844 | Retrofitting | Raidighi Sub-Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | 31/12/2020 | 02/03/2023 | 30/04/2023 | 12/06/2023 | 0 | 870 | inf | nan | 81 | 0
20 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | TSM/006842 | Retrofitting |  |  |  | 31/12/2020 | 30/07/2022 | 31/07/2022 | 12/06/2023 | 0 | 1351 | inf | nan | 100 | 0
21 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Koaberia W/S Scheme including | SM/07579 | TSM/006837 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 31/12/2020 | 25/02/2021 | 30/06/2023 | 12/06/2023 | 0 | 1071 | inf | nan | 93 | 0
22 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | TSM/006814 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 31/12/2020 | 01/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 2076 | inf | nan | 91 | 0
23 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | TSM/006859 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 31/12/2020 | 02/01/2021 | 31/12/2023 | 12/06/2023 | 0 | 1386 | inf | nan | 86 | 0
24 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07583 | TSM/006815 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 31/12/2020 | 05/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 889 | inf | nan | 91 | 0
25 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07584 | TSM/006838 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 31/12/2020 | 01/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1613 | inf | nan | 97 | 0
26 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07587 | TSM/006839 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 31/12/2020 | 22/10/2022 | 30/06/2023 | 12/06/2023 | 0 | 1074 | inf | nan | 96 | 0
27 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includi | SM/07588 | TSM/006840 | Retrofitting |  |  |  | 31/12/2020 | 08/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 780 | inf | nan | 100 | 0
28 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | TSM/006861 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | 31/12/2020 | 05/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1160 | inf | nan | 96 | 0
29 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including | SM/07590 | TSM/006862 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 31/12/2020 | 01/03/2021 | 31/12/2023 | 12/06/2023 | 0 | 2329 | inf | nan | 81 | 0
30 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | SM/07591 | TSM/006863 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | 31/12/2020 | 01/03/2021 | 31/12/2023 | 12/06/2023 | 0 | 1075 | inf | nan | 81 | 0
31 | Alipore Division | SOUTH 24 PARAGANAS | Canning - II | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | SM/07592 | TSM/006875 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 31/12/2020 | 18/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 1675 | inf | nan | 88 | 0
32 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ananda Abad Water Supply S | SM/07593 | TSM/006865 | Retrofitting |  |  |  | 31/12/2020 | 19/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 1195 | inf | nan | 100 | 0
33 | Alipore Division | SOUTH 24 PARAGANAS | Canning - II | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Singheswar Water Supply S | SM/07594 | TSM/006910 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 31/12/2020 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 1349 | inf | nan | 87 | 0
34 | Alipore Division | SOUTH 24 PARAGANAS | Canning - I | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bhaleya Water Supply Sch | SM/07598 | TSM/006877 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 31/12/2020 | 04/01/2022 | 31/12/2023 | 07/07/2023 | 0 | 1641 | inf | nan | 82 | 0
35 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sridharnagar W/S Scheme includ | SM/07625 | TSM/006860 | Retrofitting |  |  |  | 07/01/2021 | 09/07/2024 | 31/03/2022 | 12/06/2023 | 0 | 1493 | inf | nan | 100 | 0
36 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in | SM/07626 | TSM/006864 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 07/01/2021 | 04/03/2021 | 31/03/2025 | 19/11/2024 | 0 | 3074 | inf | nan | 86 | 0
37 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | SM/07627 | TSM/006872 | Retrofitting |  |  |  | 07/01/2021 | 08/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 3820 | inf | nan | 100 | 0
38 | Alipore Division | SOUTH 24 PARAGANAS | Canning - I | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat | SM/07634 | TSM/006866 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 07/01/2021 | 08/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 3369 | inf | nan | 85 | 0
39 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i | SM/07636 | TSM/006911 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | 07/01/2021 | 01/04/2022 | 31/12/2023 | 12/06/2023 | 0 | 3898 | inf | nan | 81 | 0
40 | Alipore Division | SOUTH 24 PARAGANAS | Canning - I | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Uttar Angadberia Water | SM/07637 | TSM/006913 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 07/01/2021 | 18/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 2101 | inf | nan | 85 | 0
41 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | TSM/006878 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 07/01/2021 | 10/02/2021 | 31/12/2023 | 07/07/2023 | 0 | 2122 | inf | nan | 98 | 0
42 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jyotishpur Water Supply S | SM/07643 | TSM/006899 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 07/01/2021 | 01/10/2021 | 31/12/2023 | 12/06/2023 | 0 | 2153 | inf | nan | 88 | 0
43 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | TSM/006811 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 08/01/2021 | 31/01/2021 | 30/06/2023 | 12/06/2023 | 0 | 1178 | inf | nan | 96 | 0
44 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | TSM/006848 | Retrofitting |  |  |  | 08/01/2021 | 30/07/2022 | 31/07/2022 | 12/06/2023 | 0 | 1827 | inf | nan | 100 | 0
45 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | TSM/006843 | Retrofitting |  |  |  | 08/01/2021 | 30/07/2022 | 31/07/2022 | 12/06/2023 | 0 | 2151 | inf | nan | 100 | 0
46 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-VIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07753 | TSM/006846 | Retrofitting | Raidighi Sub-Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | 08/01/2021 | 25/02/2023 | 31/07/2023 | 12/06/2023 | 0 | 2520 | inf | nan | 81 | 0
47 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | TSM/006802 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 08/01/2021 | 27/02/2021 | 30/06/2023 | 12/06/2023 | 0 | 1417 | inf | nan | 95 | 0
48 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | TSM/006845 | Retrofitting | Raidighi Sub-Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | 08/01/2021 | 31/01/2023 | 31/07/2023 | 12/06/2023 | 0 | 2091 | inf | nan | 91 | 0
49 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | SM/07757 | TSM/006810 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | 08/01/2021 | 25/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 1447 | inf | nan | 99 | 0
50 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includin | SM/07758 | TSM/006801 | Retrofitting |  |  |  | 08/01/2021 |  | 31/03/2022 | 12/06/2023 | 0 | 1224 | inf | nan | 100 | 0
51 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | TSM/006850 | Retrofitting |  |  |  | 08/01/2021 | 07/07/2021 | 31/03/2022 | 12/06/2023 | 0 | 987 | inf | nan | 100 | 0
52 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | TSM/006893 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 08/01/2021 | 26/02/2021 | 31/12/2025 | 19/11/2024 | 0 | 2937 | inf | nan | 85 | 0
53 | Alipore Division | SOUTH 24 PARAGANAS | Gosaba | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | TSM/006879 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | 08/01/2021 | 18/02/2021 | 31/12/2023 | 12/06/2023 | 0 | 4308 | inf | nan | 87 | 0
54 | Alipore Division | SOUTH 24 PARAGANAS | Gosaba | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | TSM/006905 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | 08/01/2021 | 08/01/2021 | 31/03/2023 | 12/06/2023 | 0 | 1745 | inf | nan | 97 | 0
55 | Alipore Division | SOUTH 24 PARAGANAS | Falta | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | TSM/005826 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | 19/02/2021 | 22/02/2021 | 31/07/2022 | 05/09/2023 | 0 | 3835 | inf | nan | 100 | 0
56 | Alipore Division | SOUTH 24 PARAGANAS | Falta | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | TSM/005827 | Retrofitting |  |  |  | 19/02/2021 | 26/02/2021 | 31/07/2022 | 12/06/2023 | 0 | 1329 | inf | nan | 100 | 0
57 | Alipore Division | SOUTH 24 PARAGANAS | Falta | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | TSM/005828 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | 19/02/2021 | 24/05/2021 | 31/03/2024 | 05/09/2023 | 0 | 1666 | inf | nan | 95 | 0
58 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | TSM/005830 | Retrofitting |  |  |  | 19/02/2021 | 24/02/2021 | 30/11/2022 | 12/06/2023 | 0 | 4362 | inf | nan | 100 | 0
59 | Alipore Division | SOUTH 24 PARAGANAS | Falta | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08122 | TSM/005829 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | 19/02/2021 | 24/02/2021 | 31/03/2024 | 05/09/2023 | 0 | 1203 | inf | nan | 95 | 0
60 | Alipore Division | SOUTH 24 PARAGANAS | Falta | Retrofitting of Distribution system of Zone IX Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08123 | TSM/005831 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | 19/02/2021 | 24/02/2021 | 31/07/2022 | 05/09/2023 | 0 | 624 | inf | nan | 100 | 0
61 | Alipore Division | SOUTH 24 PARAGANAS | Diamond Harbour - II | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | TSM/005832 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | 19/02/2021 | 24/02/2021 | 31/12/2023 | 04/07/2023 | 0 | 4642 | inf | nan | 99 | 0
62 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | TSM/007241 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | 31/05/2021 | 01/12/2021 | 31/12/2023 | 12/06/2023 | 0 | 1845 | inf | nan | 83 | 0
63 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on | SM/08630 | TSM/007243 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 31/05/2021 | 16/06/2022 | 31/12/2023 | 11/06/2024 | 0 | 2079 | inf | nan | 100 | 0
64 | Alipore Division | SOUTH 24 PARAGANAS | Gosaba | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sambhunagar WS Scheme includin | SM/08633 | TSM/007250 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | 27/05/2021 | 29/10/2021 | 31/12/2023 | 12/06/2023 | 0 | 2581 | inf | nan | 81 | 0
65 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | SM/08636 | TSM/007268 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 31/05/2021 | 27/07/2021 | 31/12/2023 | 12/06/2023 | 0 | 1350 | inf | nan | 87 | 0
66 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | TSM/007245 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 31/05/2021 | 05/06/2021 | 30/09/2023 | 12/06/2023 | 0 | 1221 | inf | nan | 93 | 0
67 | Alipore Division | SOUTH 24 PARAGANAS | Gosaba | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Amlamethi Water Supply Scheme including one y | SM/09008 | TSM/007253 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | 26/05/2021 | 22/11/2021 | 31/12/2023 | 12/06/2023 | 0 | 3313 | inf | nan | 81 | 0
68 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hiranmoypur Water Supply Scheme including one | SM/09013 | TSM/007270 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 26/05/2021 | 22/11/2021 | 31/12/2023 | 12/06/2023 | 0 | 3602 | inf | nan | 84 | 0
69 | Alipore Division | SOUTH 24 PARAGANAS | Canning - I | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayangarh Water Supply Scheme including one | SM/09015 | TSM/007273 | Retrofitting |  |  |  | 26/05/2021 | 02/11/2021 |  | 12/06/2023 | 0 | 2385 | inf | nan | 100 | 0
70 | Alipore Division | SOUTH 24 PARAGANAS | Basanti | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S | SM/09016 | TSM/007274 | Retrofitting | Canning Sub-division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 26/05/2021 | 02/11/2021 | 31/12/2023 | 12/06/2023 | 0 | 1592 | inf | nan | 100 | 0
71 | Alipore Division | SOUTH 24 PARAGANAS | Namkhana | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | SM/09076 | TSM/008428 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 29/10/2021 | 01/04/2022 | 30/04/2025 | 19/11/2024 | 0 | 1169 | inf | nan | 81 | 0
72 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | TSM/008429 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 29/10/2021 | 02/02/2022 | 30/06/2023 | 12/06/2023 | 0 | 1508 | inf | nan | 95 | 0
73 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | TSM/008690 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 12/11/2021 | 25/04/2022 | 31/12/2023 | 12/06/2023 | 0 | 1655 | inf | nan | 95 | 0
74 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | TSM/008693 | Retrofitting | Kakdwip Sub-Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 17/11/2021 | 31/01/2022 | 30/06/2023 | 12/06/2023 | 0 | 1623 | inf | nan | 86 | 0
75 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | TSM/008666 | Retrofitting | Raidighi Sub-Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | 17/11/2021 | 20/11/2022 | 31/07/2023 | 12/06/2023 | 0 | 1692 | inf | nan | 81 | 0
76 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - II | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09399 | TSM/008670 | Retrofitting | Raidighi Sub-Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | 17/11/2021 | 31/01/2023 | 31/07/2023 | 12/06/2023 | 0 | 4243 | inf | nan | 81 | 0
77 | Alipore Division | SOUTH 24 PARAGANAS | Kakdwip | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | TSM/008786 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | 18/11/2021 | 04/12/2022 | 30/06/2023 | 12/06/2023 | 0 | 680 | inf | nan | 85 | 0
78 | Alipore Division | SOUTH 24 PARAGANAS | Diamond Harbour - II | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09505 | TSM/008279 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | 19/11/2021 | 15/02/2022 | 31/08/2022 | 12/06/2023 | 0 | 4562 | inf | nan | 90 | 0
79 | Alipore Division | SOUTH 24 PARAGANAS | Diamond Harbour - II | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone VI including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09506 | TSM/008280 | Retrofitting | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | 19/11/2021 | 22/11/2021 | 31/08/2022 | 12/06/2023 | 0 | 1833 | inf | nan | 99 | 0
80 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | TSM/008304 | Retrofitting |  |  |  | 19/11/2021 | 30/09/2022 | 30/09/2023 | 12/06/2023 | 0 | 1957 | inf | nan | 100 | 0
81 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | TSM/008305 | Retrofitting |  |  |  | 19/11/2021 | 10/03/2023 | 30/09/2023 | 12/06/2023 | 0 | 1573 | inf | nan | 100 | 0
82 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & | SM/09514 | TSM/008306 | Retrofitting |  |  |  | 19/11/2021 | 05/02/2023 | 30/09/2023 | 12/06/2023 | 0 | 1840 | inf | nan | 100 | 0
83 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | TSM/008307 | Retrofitting |  |  |  | 19/11/2021 | 12/01/2023 | 30/09/2023 | 12/06/2023 | 0 | 2491 | inf | nan | 100 | 0
84 | Alipore Division | SOUTH 24 PARAGANAS | Mathurapur - I | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | TSM/009100 | Retrofitting |  |  |  | 19/11/2021 | 30/01/2023 | 31/07/2022 | 12/06/2023 | 0 | 252 | inf | nan | 100 | 0
85 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | AUGMENTATION OF GROUND WATER BASED MRITYUNJAYNAGAR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11698 | TSM/011494 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 29/07/2022 | 01/09/2022 | 31/03/2024 | 01/07/2024 | 0 | 632 | inf | nan | 96 | 0
86 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | TSM/011331 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 03/08/2022 | 12/09/2022 | 31/12/2024 | 12/08/2024 | 0 | 1690 | inf | nan | 94 | 0
87 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | TSM/011470 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 09/11/2022 | 01/12/2022 | 31/12/2025 | 12/08/2024 | 0 | 1735 | inf | nan | 85 | 0
88 | Alipore Division | SOUTH 24 PARAGANAS | Canning - II | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-X) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13572 | TSM/014674 | Augmentation | Canning Sub-division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | 09/11/2022 | 30/11/2022 | 31/12/2025 | 14/08/2024 | 0 | 198 | inf | nan | 86 | 0
89 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KRISHNADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13871 | TSM/011605 | New | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 25/11/2022 | 06/12/2022 | 31/12/2024 | 15/03/2024 | 0 | 936 | inf | nan | 90 | 0
90 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | TSM/011505 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | 25/11/2022 | 02/12/2022 |  | 12/06/2023 | 0 | 1623 | inf | nan | 90 | 0
91 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | TSM/011629 | New | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 01/12/2022 | 30/12/2022 | 31/12/2024 | 12/08/2024 | 0 | 1486 | inf | nan | 83 | 0
92 | Alipore Division | SOUTH 24 PARAGANAS | Patharpratima | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | TSM/011500 | Augmentation | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | 02/01/2023 | 24/03/2023 | 31/03/2024 | 12/06/2023 | 0 | 1049 | inf | nan | 90 | 0
93 | Alipore Division | SOUTH 24 PARAGANAS | Sagar | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | TSM/017110 | New | Kakdwip Sub-Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | 04/02/2023 | 05/02/2023 | 31/03/2024 | 01/07/2024 | 0 | 1517 | inf | nan | 91 | 0
94 | Alipore Division | SOUTH 24 PARAGANAS | Budge Budge - I | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) | SM/18868 | TSM/020615 | Augmentation | Diamond Harbour Sub-Division | Assistant Engineer, Diamond Harbour sub division |  | 05/10/2023 | 07/10/2023 | 05/04/2024 | 13/10/2023 | 0 | 1484 | inf | nan | 90 | 0
Total | [14 empty] | 0 | 173647 | 0 | 0 |  | NAN