## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Murshidabad Division | MURSHIDABAD | Bharatpur - II | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs | SM/07509 | TSM/006547 | Retrofitting | Kandi Sub-Division | ASSISTANT ENGINEER |  | 29/12/2020 | 02/01/2021 | 31/03/2024 | 12/06/2023 | 2 | 1276 | inf | inf | 99 | 3
2 | Murshidabad Division | MURSHIDABAD | Domkal | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07911 | TSM/006570 | Retrofitting |  |  |  | 19/01/2021 | 28/05/2021 | 31/03/2024 | 12/06/2023 | 2 | 2146 | inf | nan | 100 | 0
3 | Murshidabad Division | MURSHIDABAD | Raninagar - II | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida | SM/08100 | TSM/006574 | Retrofitting |  |  |  | 08/02/2021 | 09/08/2021 |  | 12/06/2023 | 4 | 5365 | inf | nan | 100 | 0
4 | Murshidabad Division | MURSHIDABAD | Samserganj | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan | SM/09737 | TSM/007515 | Retrofitting |  |  |  | 29/11/2021 | 05/01/2022 | 31/03/2024 | 12/06/2023 | 5 | 7358 | inf | inf | 100 | 9
5 | Murshidabad Division | MURSHIDABAD | Farakka | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad | SM/09743 | TSM/007541 | Retrofitting |  |  |  | 30/11/2021 | 03/12/2021 | 31/03/2024 | 12/06/2023 | 7 | 2145 | inf | inf | 100 | 7
6 | Murshidabad Division | MURSHIDABAD | Raghunathganj - I | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B | SM/09750 | TSM/007514 | Retrofitting |  |  |  | 29/11/2021 | 22/12/2021 |  | 12/06/2023 | 3 | 3979 | inf | inf | 100 | 1
7 | Murshidabad Division | MURSHIDABAD | Suti - I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD | SM/10812 | TSM/008643 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER-II | Junior engineer-III | 25/05/2022 | 25/06/2022 | 31/03/2024 | 12/06/2023 | 4 | 3873 | inf | inf | 100 | 1
8 | Murshidabad Division | MURSHIDABAD | Beldanga - II | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. | SM/11161 | TSM/008737 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER-I | Junior engineer-III | 02/06/2022 | 07/06/2022 | 31/03/2024 | 12/06/2023 | 3 | 268 | inf | nan | 100 | 0
9 | Murshidabad Division | MURSHIDABAD | Berhampore | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio | SM/11163 | TSM/008735 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER-I | Junior engineer-II | 02/06/2022 | 06/06/2022 | 31/03/2024 | 12/06/2023 | 2 | 319 | inf | inf | 100 | 5
10 | Murshidabad Division | MURSHIDABAD | Raghunathganj - II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II | SM/11198 | TSM/008642 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | 03/06/2022 | 06/06/2022 | 31/03/2024 | 12/06/2023 | 6 | 1544 | inf | inf | 100 | 3
11 | Murshidabad Division | MURSHIDABAD | Raghunathganj - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I | SM/11220 | TSM/008647 | Augmentation | Jangipur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | 15/06/2022 | 18/06/2022 | 31/03/2024 | 12/06/2023 | 2 | 3301 | inf | inf | 100 | 2
12 | Murshidabad Division | MURSHIDABAD | Beldanga - II | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11563 | TSM/010759 | Augmentation | Berhampur Sub-Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | 22/07/2022 | 24/08/2022 | 31/03/2024 | 12/06/2023 | 8 | 1657 | inf | inf | 100 | 2
13 | Murshidabad Division | MURSHIDABAD | Nawda | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | TSM/010706 | Augmentation | Berhampur Sub-Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | 22/07/2022 | 23/08/2022 | 31/03/2024 | 06/03/2024 | 9 | 364 | inf | inf | 98 | 8
14 | Murshidabad Division | MURSHIDABAD | Nawda | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11567 | TSM/010769 | Augmentation | Berhampur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | 22/07/2022 | 25/08/2022 | 31/03/2024 | 12/06/2023 | 7 | 105 | inf | inf | 100 | 7
15 | Murshidabad Division | MURSHIDABAD | Raghunathganj - II | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | TSM/011576 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | 03/08/2022 | 03/09/2022 | 31/03/2024 | 22/02/2024 | 7 | 2376 | inf | inf | 99 | 2
16 | Murshidabad Division | MURSHIDABAD | Samserganj | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | TSM/011687 | Augmentation | Berhampur M/E Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | 03/08/2022 | 05/09/2022 | 31/03/2024 | 12/06/2023 | 9 | 9386 | inf | inf | 100 | 1
17 | Murshidabad Division | MURSHIDABAD | Samserganj | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | TSM/017469 | New | Berhampur M/E Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | 04/02/2023 | 10/02/2023 | 31/12/2024 | 22/05/2024 | 8 | 817 | inf | inf | 98 | 5
Total | [14 empty] | 88 | 46279 | 0 | 0 |  | NAN