## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07599 | TSM/006919 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 11/01/2021 | 31/03/2024 | 28/06/2023 | 3 | 1096 | inf | inf | 98 | 94
2 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07600 | TSM/006920 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 11/01/2021 | 31/03/2024 | 28/06/2023 | 3 | 1761 | inf | inf | 98 | 46
3 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07601 | TSM/006918 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 3 | 1371 | inf | inf | 98 | 65
4 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07602 | TSM/006915 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 4 | 1615 | inf | inf | 98 | 49
5 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07603 | TSM/006917 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 1 | 1068 | inf | inf | 98 | 91
6 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07604 | TSM/006916 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 04/02/2021 | 31/03/2024 | 28/06/2023 | 2 | 889 | inf | inf | 98 | 89
7 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | SM/07605 | TSM/006914 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 3 | 1477 | inf | inf | 98 | 79
8 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07606 | TSM/006921 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 1 | 467 | inf | inf | 98 | 74
9 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07607 | TSM/006922 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 04/02/2021 | 31/03/2024 | 28/06/2023 | 2 | 962 | inf | inf | 98 | 47
10 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07608 | TSM/006923 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 1 | 1927 | inf | inf | 98 | 44
11 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07609 | TSM/006924 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 05/01/2021 | 22/01/2021 | 31/03/2024 | 28/06/2023 | 1 | 1443 | inf | inf | 90 | 73
12 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) | SM/08039 | TSM/007047 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 17/05/2021 | 31/03/2024 | 28/06/2023 | 1 | 4288 | inf | inf | 98 | 41
13 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North | SM/08040 | TSM/007090 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 03/06/2021 | 31/03/2024 | 28/06/2023 | 2 | 1337 | inf | inf | 98 | 78
14 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). | SM/08041 | TSM/007086 | Retrofitting | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | 01/02/2021 | 03/06/2021 | 31/03/2024 | 28/06/2023 | 6 | 185 | inf | inf | 98 | 49
15 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chandpur Water Supply Scheme at Bagdah Block under (Phase-I) | SM/08042 | TSM/007085 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 02/07/2021 | 31/03/2024 | 28/06/2023 | 1 | 1125 | inf | inf | 98 | 80
16 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). | SM/08043 | TSM/007082 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 03/06/2021 | 31/03/2024 | 28/06/2023 | 2 | 1242 | inf | inf | 98 | 30
17 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bangangram (Zone-I) Water Supply Scheme at Bongaon Block (Phase-II) | SM/08044 | TSM/007084 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 31/05/2021 | 31/03/2024 | 28/06/2023 | 1 | 611 | inf | inf | 98 | 46
18 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Amdanga | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N | SM/08045 | TSM/007089 | Retrofitting | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 31/05/2021 | 31/03/2024 | 28/06/2023 | 2 | 1452 | inf | inf | 98 | 23
19 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 | SM/08046 | TSM/007088 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 31/05/2021 | 31/03/2024 | 28/06/2023 | 1 | 1351 | inf | inf | 98 | 33
20 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Palla Water Supply Scheme at Bongaon Block (Phase-I) | SM/08047 | TSM/007048 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 14/06/2021 | 31/03/2024 | 28/06/2023 | 1 | 1048 | inf | inf | 98 | 45
21 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dighari Water Supply Scheme at Bongaon Block (Phase-II). | SM/08048 | TSM/007083 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 01/02/2021 | 03/06/2021 | 31/03/2024 | 28/06/2023 | 1 | 1164 | inf | inf | 98 | 46
22 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). | SM/08234 | TSM/007277 | Retrofitting | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 2 | 1431 | inf | inf | 98 | 41
23 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-II WaterSupply Scheme at Bongaon Block (Phase-I). | SM/08235 | TSM/007279 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 1 | 1040 | inf | inf | 98 | 39
24 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-I WaterSupply Scheme at Bongaon Block (Phase-II). | SM/08236 | TSM/007285 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 1 | 1303 | inf | inf | 98 | 41
25 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Bangangram (Zone-II) Water SupplyScheme at Bongaon Block (Phase-II). | SM/08237 | TSM/007283 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 16/11/2021 | 31/03/2024 | 28/06/2023 | 1 | 1085 | inf | inf | 98 | 32
26 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). | SM/08238 | TSM/007281 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 1 | 1202 | inf | inf | 98 | 31
27 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | TSM/007278 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 4 | 1496 | inf | inf | 98 | 41
28 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at Bongaon Block (Phase-II). | SM/08240 | TSM/007287 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 28/10/2021 | 31/03/2024 | 28/06/2023 | 1 | 1040 | inf | inf | 98 | 69
29 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Amdanga | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | TSM/007436 | Retrofitting | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | 22/02/2021 | 26/11/2021 | 31/03/2024 | 28/06/2023 | 6 | 2780 | inf | inf | 95 | 81
30 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block | SM/08242 | TSM/007434 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 12/10/2021 | 31/03/2024 | 28/06/2023 | 1 | 1179 | inf | inf | 98 | 42
31 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | SM/08243 | TSM/007435 | Retrofitting | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 24/12/2021 | 31/03/2024 | 28/06/2023 | 3 | 1919 | inf | inf | 90 | 15
32 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Amdanga | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | SM/08244 | TSM/007437 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/02/2021 | 24/12/2021 | 31/03/2024 | 28/06/2023 | 3 | 1464 | inf | inf | 88 | 13
33 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gainpur Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. | SM/08730 | TSM/007651 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 09/09/2021 | 29/12/2021 | 31/03/2024 | 28/06/2023 | 1 | 464 | inf | inf | 98 | 90
34 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). | SM/08731 | TSM/007652 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 09/09/2021 | 29/12/2021 | 31/03/2024 | 28/06/2023 | 1 | 802 | inf | inf | 98 | 44
35 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). | SM/08732 | TSM/007650 | Retrofitting | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 09/09/2021 | 29/12/2021 | 31/03/2024 | 28/06/2023 | 5 | 1768 | inf | inf | 98 | 97
36 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | TSM/009448 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 30/05/2022 | 31/03/2024 | 28/06/2023 | 5 | 5274 | inf | inf | 78 | 51
37 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | TSM/009519 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) |  | 02/02/2022 | 30/05/2022 | 31/03/2024 | 28/06/2023 | 9 | 8990 | inf | inf | 55 | 50
38 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | TSM/009520 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 28/04/2022 | 31/03/2024 | 28/06/2023 | 6 | 1810 | inf | inf | 78 | 61
39 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | TSM/009323 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 23/05/2022 | 31/03/2024 | 28/06/2023 | 7 | 4118 | inf | inf | 88 | 38
40 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | TSM/009270 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 19/05/2022 | 31/03/2024 | 28/06/2023 | 9 | 2759 | inf | inf | 84 | 56
41 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | TSM/009496 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) |  | 02/02/2022 | 10/06/2022 | 31/03/2024 | 28/06/2023 | 8 | 8163 | inf | inf | 75 | 69
42 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | TSM/009515 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) |  | 02/02/2022 | 27/05/2022 | 31/03/2024 | 28/06/2023 | 8 | 5976 | inf | inf | 85 | 71
43 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | TSM/009271 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 02/05/2022 | 31/03/2024 | 28/06/2023 | 6 | 3893 | inf | inf | 86 | 68
44 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | TSM/009219 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/02/2022 | 10/06/2022 | 31/03/2024 | 28/06/2023 | 10 | 3767 | inf | inf | 88 | 48
45 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10153 | TSM/009497 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) |  | 11/02/2022 | 10/06/2022 | 31/03/2024 | 28/06/2023 | 7 | 7823 | inf | inf | 55 | 42
46 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | TSM/009123 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 02/03/2022 | 13/05/2022 | 31/03/2024 | 28/06/2023 | 8 | 2699 | inf | inf | 68 | 51
47 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | TSM/010391 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 08/04/2022 | 30/05/2022 | 31/10/2024 | 18/06/2024 | 9 | 1449 | inf | inf | 43 | 31
48 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | TSM/010388 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 08/04/2022 | 25/07/2022 | 31/03/2024 | 28/06/2023 | 6 | 1799 | inf | inf | 69 | 60
49 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | TSM/010666 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 18/04/2022 | 19/04/2022 | 31/03/2024 | 04/10/2023 | 7 | 3466 | inf | inf | 5 | 0
50 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | TSM/010599 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) |  | 18/04/2022 | 19/04/2022 | 31/03/2024 | 27/02/2024 | 14 | 5789 | inf | inf | 5 | 12
51 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | TSM/009939 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 18/04/2022 | 16/08/2022 | 31/03/2024 | 28/06/2023 | 11 | 2628 | inf | inf | 67 | 70
52 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bagda | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | TSM/010664 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 18/04/2022 | 01/07/2023 | 30/04/2024 | 07/03/2024 | 6 | 1205 | inf | inf | 10 | 12
53 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | TSM/010275 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 18/04/2022 | 30/11/2022 | 31/03/2024 | 23/11/2023 | 11 | 2829 | inf | inf | 52 | 41
54 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | TSM/010566 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 19/04/2022 | 01/07/2023 | 30/04/2024 | 22/03/2024 | 6 | 3671 | inf | inf | 7 | 1
55 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | TSM/010276 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 21/04/2022 | 10/11/2022 | 31/08/2024 | 24/04/2024 | 8 | 1886 | inf | inf | 70 | 57
56 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | TSM/010573 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 23/05/2022 | 01/08/2023 | 31/03/2024 | 04/10/2023 | 6 | 3750 | inf | inf | 2 | 0
57 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | TSM/009938 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 25/05/2022 | 05/09/2022 | 31/03/2024 | 28/06/2023 | 10 | 4201 | inf | inf | 52 | 71
58 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/11212 | TSM/010262 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | 09/06/2022 | 14/10/2022 | 31/05/2024 | 20/03/2024 | 9 | 3611 | inf | inf | 43 | 29
59 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | TSM/009082 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 13/06/2022 | 25/07/2022 | 31/03/2024 | 28/06/2023 | 12 | 4258 | inf | inf | 59 | 53
60 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Bongaon | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/11555 | TSM/011010 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/07/2022 | 01/08/2023 | 30/04/2024 | 22/03/2024 | 6 | 2114 | inf | inf | 44 | 1
61 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | TSM/011191 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 22/07/2022 | 21/11/2022 | 31/08/2024 | 18/03/2024 | 15 | 705 | inf | inf | 17 | 9
62 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12383 | TSM/014883 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 13/09/2022 | 17/11/2022 | 31/05/2024 | 04/03/2024 | 9 | 2150 | inf | inf | 11 | 12
63 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barrackpur - II | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15817 | TSM/014836 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | 20/02/2023 | 04/07/2023 | 31/03/2024 | 04/10/2023 | 6 | 1169 | inf | inf | 1 | 0
64 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | TSM/014881 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 20/02/2023 | 11/07/2023 | 31/05/2024 | 23/02/2024 | 8 | 2939 | inf | inf | 12 | 9
65 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | TSM/014790 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 20/02/2023 | 11/07/2023 | 30/04/2024 | 07/03/2024 | 7 | 3667 | inf | inf | 19 | 27
66 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15821 | TSM/014754 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 20/02/2023 | 11/07/2023 | 31/07/2024 | 07/03/2024 | 7 | 2537 | inf | inf | 6 | 20
67 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | TSM/014788 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 20/02/2023 | 11/07/2023 | 31/05/2024 | 07/03/2024 | 7 | 3593 | inf | inf | 6 | 27
68 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Barasat - I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18258 | TSM/013336 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 21/06/2023 | 11/07/2023 | 31/03/2024 | 04/10/2023 | 2 | 6162 | inf | inf | 1 | 0
69 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | TSM/015251 | Augmentation | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 21/06/2023 | 03/07/2023 | 30/06/2024 | 12/03/2024 | 7 | 2526 | inf | inf | 24 | 11
70 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18261 | TSM/015092 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 21/06/2023 | 03/07/2023 | 30/06/2024 | 23/02/2024 | 8 | 3740 | inf | inf | 5 | 5
71 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | TSM/015472 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 21/06/2023 | 03/07/2023 | 30/04/2024 | 07/03/2024 | 6 | 2191 | inf | inf | 5 | 0
72 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18263 | TSM/015074 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 21/06/2023 | 03/07/2023 | 31/07/2024 | 07/03/2024 | 5 | 2648 | inf | inf | 6 | 0
73 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS | Deganga | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18264 | TSM/015086 | Augmentation | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | 21/06/2023 | 03/07/2023 | 31/03/2024 | 03/08/2023 | 3 | 2796 | inf | inf | 1 | 0
Total | [14 empty] | 367 | 181603 | 0 | 0 |  | NAN