## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. | SM/06633 | TSM/005400 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | 05/02/2020 |  |  | 30/04/2021 | 2 | 0 | inf | inf | 0 | 60
2 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Engagement of Laboratory personnel to operate Atomic Absorption Spectrophotometer, Chemist for testing of bottling plant samples (PRANDHARA) & Data entry operator for BIS Documentation works as per IS 14543-2016 protocol including supply, delivery, instal | SM/10734 | TSM/009557 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | 19/05/2022 |  |  | 19/05/2022 | 1 | 0 | inf | inf | 0 | 37
3 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | TSM/009330 | Disaster | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 23/05/2022 |  |  | 23/05/2022 | 16 | 0 | inf | inf | 0 | 95
4 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for the office premises of North 24 Parganas W/S Division-I, Public Health Engineering Directorate, Govt. of West Be | SM/11648 | TSM/011465 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | 27/07/2022 |  |  | 29/07/2022 | 1 | 0 | inf | inf | 0 | 57
5 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/12048 | TSM/012595 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | 01/09/2022 |  |  | 05/09/2022 | 2 | 0 | inf | inf | 0 | 89
6 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/13407 | TSM/015393 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | 02/11/2022 |  |  | 04/11/2022 | 6 | 0 | inf | inf | 0 | 72
7 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/13849 | TSM/016622 | Support | North 24 Pgs W/S Division I | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | 25/11/2022 | 15/09/2023 |  | 26/11/2022 | 9 | 0 | inf | inf | 0 | 89
8 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Supply, Installation, Commissioning & Monitoring of INTELLIGENT Disinfection Systems for the complete, desired. Continuous, constant & external power free disinfection of drinking water (via the national JJM approved green technology) supplied through (PW | SM/14516 | TSM/016087 | Support | Sub-Division I under North 24 pgs W/S Division I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | 20/01/2023 |  |  | 29/01/2023 | 1 | 0 | inf | inf | 0 | 60
9 | North 24 Pgs W/S Division I | NORTH 24 PARAGANAS |  | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. | SM/19088 | TSM/021811 | Support |  |  |  | 05/12/2023 | 05/08/2024 |  | 05/12/2023 | 4 | 0 | inf | inf | 0 | 7
Total | [14 empty] | 42 | 0 | 0 | 0 |  | NAN