## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Midnapore Division | PASCHIM MEDINIPUR | Midnapore | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS | SM/06921 | TSM/005715 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/10/2020 | 26/11/2020 | 31/07/2022 | 12/06/2023 | 2 | 1246 | inf | inf | 100 | 6
2 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. | SM/08213 | TSM/007153 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/02/2021 | 24/02/2021 |  | 12/06/2023 | 3 | 120 | inf | inf | 100 | 5
3 | Midnapore Division | PASCHIM MEDINIPUR | Midnapore | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District | SM/09703 | TSM/008268 | Retrofitting | RWS Midnapur Sub-Division | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | 26/11/2021 | 10/05/2022 | 31/03/2024 | 28/09/2023 | 2 | 1265 | inf | inf | 85 | 4
4 | Midnapore Division | PASCHIM MEDINIPUR | Ghatal | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | TSM/018372 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 04/02/2023 | 27/03/2023 |  | 12/06/2023 | 5 | 502 | inf | inf | 100 | 1
5 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | TSM/018377 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 8 | 325 | inf | inf | 88 | 4
6 | Midnapore Division | PASCHIM MEDINIPUR | Ghatal | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | TSM/018343 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 5 | 317 | inf | inf | 100 | 8
7 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | TSM/018349 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 7 | 280 | inf | inf | 100 | 4
8 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15576 | TSM/018213 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division | JE1 Ghatal Sub-division | 15/02/2023 |  |  | 12/06/2023 | 1 | 264 | inf | nan | 100 | 0
9 | Midnapore Division | PASCHIM MEDINIPUR | Ghatal | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15578 | TSM/018368 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 01/07/2024 | 31/12/2025 | 09/08/2024 | 5 | 342 | inf | inf | 86 | 1
10 | Midnapore Division | PASCHIM MEDINIPUR | Dantan - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | TSM/018179 | Augmentation | Midnapur Mechanical Sub Division-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 16/03/2023 | 25/04/2023 | 16/09/2023 | 12/06/2023 | 3 | 75 | inf | nan | 83 | 0
11 | Midnapore Division | PASCHIM MEDINIPUR | Keshpur | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/17395 | TSM/018218 | Augmentation | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | 15/03/2023 | 31/07/2023 |  | 12/06/2023 | 3 | 70 | inf | inf | 100 | 1
Total | [14 empty] | 44 | 4806 | 0 | 0 |  | NAN