## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Midnapore Division | PASCHIM MEDINIPUR |  | Procurement of Chemical & Consumables, Glassware, Plasticware etc. required for smooth running of the Laboratories. | SM/06619 | TSM/005384 | Support |  |  |  | 05/02/2020 |  |  | 31/07/2020 | 12 | 0 | inf | inf | 100 | 97
2 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | SM/08206 | TSM/007155 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/02/2021 | 17/02/2022 |  | 12/06/2023 | 4 | 363 | inf | inf | 100 | 57
3 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur | SM/08207 | TSM/007143 | Retrofitting | Ghatal Subdivision | AE Ghatal Sub-division |  | 09/02/2021 | 26/02/2021 |  | 12/06/2023 | 2 | 2031 | inf | inf | 100 | 96
4 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. | SM/08208 | TSM/007157 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/02/2021 | 01/02/2022 |  | 12/06/2023 | 3 | 84 | inf | inf | 100 | 41
5 | Midnapore Division | PASCHIM MEDINIPUR | Pingla | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur | SM/08210 | TSM/007140 | Retrofitting | Kharagpur Sub-Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | 09/02/2021 | 26/02/2021 |  | 12/06/2023 | 2 | 1457 | inf | inf | 100 | 96
6 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. | SM/08213 | TSM/007153 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/02/2021 | 24/02/2021 |  | 12/06/2023 | 3 | 120 | inf | inf | 100 | 5
7 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. | SM/08215 | TSM/007152 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 09/02/2021 | 28/12/2021 |  | 12/06/2023 | 3 | 253 | inf | inf | 100 | 49
8 | Midnapore Division | PASCHIM MEDINIPUR | Keshpur | Retrofitting to accomodate FHTC under JJM in Mugbasan PWSS | SM/08218 | TSM/007150 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | 09/02/2021 | 02/07/2021 |  | 12/06/2023 | 1 | 1445 | inf | inf | 100 | 96
9 | Midnapore Division | PASCHIM MEDINIPUR | Sabang | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08696 | TSM/007431 | Retrofitting | Ghatal Subdivision | AE Ghatal Sub-division |  | 01/09/2021 | 03/09/2021 |  | 12/06/2023 | 4 | 5208 | inf | inf | 100 | 95
10 | Midnapore Division | PASCHIM MEDINIPUR |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Medinipur District. | SM/08999 | TSM/008139 | Support |  |  |  | 29/10/2021 |  |  | 31/10/2021 | 0 | 0 | inf | inf | 0 | 86
11 | Midnapore Division | JHARGRAM |  | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | TSM/008124 | Support |  |  |  | 29/10/2021 | 07/12/2023 |  | 31/10/2021 | 5 | 0 | inf | inf | 0 | 57
12 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | Retrofitting to accommodate FHTC under JJM in Nabin Mahespur PWSS, Block - Daspur-I, District - Paschim Medinipur. | SM/09081 | TSM/008467 | Retrofitting | Ghatal Subdivision | AE Ghatal Sub-division |  | 28/10/2021 | 04/04/2022 |  | 12/06/2023 | 1 | 1204 | inf | inf | 100 | 80
13 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Ground Water Based Keudi Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09417 | TSM/008542 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 17/11/2021 | 17/12/2021 |  | 12/06/2023 | 2 | 41 | inf | inf | 100 | 66
14 | Midnapore Division | PASCHIM MEDINIPUR | Keshpur | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09418 | TSM/008483 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | 17/11/2021 | 17/12/2021 |  | 12/06/2023 | 2 | 374 | inf | inf | 100 | 71
15 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | Retrofitting of Ground Water Based Kalshibhanga Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09419 | TSM/008546 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 17/11/2021 | 04/03/2022 |  | 12/06/2023 | 2 | 57 | inf | inf | 100 | 27
16 | Midnapore Division | PASCHIM MEDINIPUR | Garbeta - II | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | TSM/008482 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | 17/11/2021 | 03/06/2022 |  | 12/06/2023 | 10 | 3130 | inf | inf | 100 | 32
17 | Midnapore Division | PASCHIM MEDINIPUR | Sabang | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | TSM/008487 | New | Kharagpur Sub-Division | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 24/11/2021 | 30/11/2021 |  | 12/06/2023 | 14 | 237 | inf | inf | 100 | 77
18 | Midnapore Division | PASCHIM MEDINIPUR | Sabang | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | TSM/008479 | New | Kharagpur Sub-Division | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 24/11/2021 | 30/11/2021 |  | 12/06/2023 | 8 | 252 | inf | inf | 100 | 88
19 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | TSM/008256 | Retrofitting | Ghatal Subdivision | AE Ghatal Sub-division | JE1 Ghatal Sub-division | 26/11/2021 | 17/12/2021 |  | 12/06/2023 | 5 | 1394 | inf | inf | 100 | 79
20 | Midnapore Division | PASCHIM MEDINIPUR | Mohanpur | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09723 | TSM/008257 | Retrofitting | RWS Midnapur Sub-Division | AE/RWS Midnapore Sub Division | JE RWS Midnapur Sub-Division(Mohanpur) | 26/11/2021 | 07/01/2022 |  | 12/06/2023 | 3 | 593 | inf | inf | 100 | 68
21 | Midnapore Division | PASCHIM MEDINIPUR |  | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. | SM/12378 | TSM/012741 | Support |  |  |  | 13/09/2022 |  |  | 14/09/2022 | 12 | 0 | inf | inf | 0 | 93
22 | Midnapore Division | PASCHIM MEDINIPUR |  | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission under Midnapore Division, PHE Dte. | SM/12633 | TSM/012033 | Support |  |  |  | 19/09/2022 |  |  | 20/09/2022 | 1 | 0 | inf | inf | 0 | 32
23 | Midnapore Division | PASCHIM MEDINIPUR |  | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. | SM/14086 | TSM/016458 | Support |  |  |  | 12/12/2022 |  |  | 15/12/2022 | 53 | 0 | inf | inf | 0 | 92
24 | Midnapore Division | PASCHIM MEDINIPUR |  | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | TSM/014343 | Support |  |  |  | 21/12/2022 |  |  | 21/12/2022 | 44 | 0 | inf | inf | 0 | 97
25 | Midnapore Division | JHARGRAM |  | PROCUREMENT OF CHEMICALS & CONSUMABLES ,GLASSWARE ETC.REQUIRED FOR SMOOTH RUNNING OF THE DIFFERENT LABORATORIES UNDER MIDNAPORE DIVISION,PHE DTE. | SM/14108 | TSM/016305 | Support |  |  |  | 21/12/2022 | 07/03/2024 |  | 21/12/2022 | 5 | 0 | inf | inf | 0 | 50
26 | Midnapore Division | PASCHIM MEDINIPUR | Ghatal | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | TSM/018372 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 04/02/2023 | 27/03/2023 |  | 21/11/2024 | 5 | 502 | inf | inf | 90 | 1
27 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | TSM/018377 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 8 | 325 | inf | inf | 88 | 4
28 | Midnapore Division | PASCHIM MEDINIPUR | Ghatal | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | TSM/018343 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 5 | 317 | inf | inf | 100 | 8
29 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | TSM/018349 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | 15/02/2023 | 27/03/2023 |  | 12/06/2023 | 7 | 280 | inf | inf | 100 | 4
30 | Midnapore Division | PASCHIM MEDINIPUR | Daspur - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15576 | TSM/018213 | Augmentation | Ghatal Subdivision | AE Ghatal Sub-division | JE1 Ghatal Sub-division | 15/02/2023 |  |  | 12/06/2023 | 1 | 264 | inf | nan | 100 | 0
31 | Midnapore Division | PASCHIM MEDINIPUR | Salbani | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. | SM/16949 | TSM/018430 | Retrofitting | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE2 Sadar Sub-division | 16/03/2023 | 17/07/2023 |  | 12/06/2023 | 2 | 150 | inf | inf | 100 | 50
32 | Midnapore Division | PASCHIM MEDINIPUR | Keshpur | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/17395 | TSM/018218 | Augmentation | Midnapur Sadar Sub-Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | 15/03/2023 | 31/07/2023 |  | 12/06/2023 | 3 | 70 | inf | inf | 100 | 1
33 | Midnapore Division | PASCHIM MEDINIPUR |  | Regular Upkeep of Drinking Water Testing Laboratory in Paschim Medinipur Under Midnapore Division, PHE dte. Related to Water Quality Monitoring and Surveillance Support Activities under Jal Jeevan Mission. | SM/18277 | TSM/020800 | Support |  |  |  | 23/06/2023 |  |  | 27/06/2023 | 0 | 0 | inf | nan | 0 | 0
34 | Midnapore Division | PASCHIM MEDINIPUR |  | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | TSM/022033 | Support |  |  |  | 24/11/2023 | 27/09/2023 |  | 30/11/2023 | 36 | 0 | inf | inf | 0 | 39
35 | Midnapore Division | PASCHIM MEDINIPUR |  | Collection,Testing & Uploading charges of Drinking Water Samples through Field Test Kits(FTKs) in Paschim Medinipur District(Phase-II) related to Water Quality Monitoring & Surveillance Program Under Jal Jeevan Mission. | SM/19089 | TSM/022289 | Support |  |  |  | 05/12/2023 |  |  | 05/12/2023 | 1 | 0 | inf | inf | 0 | 37
36 | Midnapore Division | PASCHIM MEDINIPUR |  | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues and WASH issues under Jal Jeevan Mission (JJM) Support Activities at Paschim Medinipur District. | SM/19172 | TSM/021314 | Support |  |  |  | 08/02/2024 |  |  | 15/02/2024 | 0 | 0 | inf | nan | 0 | 0
37 | Midnapore Division | PASCHIM MEDINIPUR |  | Drinking Water sample collection and testing through Field Test Kit(FTKs) and uploading charges for the same related to water quality monitoring and surveillance programme under Jal Jeevan Mission. | SM/19214 | TSM/011204 | Support |  |  |  | 19/06/2024 |  |  | 25/06/2024 | 1 | 0 | inf | nan | 0 | 0
38 | Midnapore Division | PASCHIM MEDINIPUR |  | Estimate for procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Laboratories for the year 2024- 2025 in the District of Paschim Medinipur Under Midnapore Division P.H.E. Dte. | SM/19270 | TSM/023239 | Support |  |  |  | 10/09/2024 |  |  | 11/09/2024 | 0 | 0 | inf | nan | 0 | 0
39 | Midnapore Division | PASCHIM MEDINIPUR |  | Regular Upkeepment of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents. accessories and safety | SM/19282 | TSM/023237 | Support |  |  |  | 30/10/2024 |  |  | 12/11/2024 | 0 | 0 | inf | nan | 0 | 0
40 | Midnapore Division | PASCHIM MEDINIPUR |  | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | TSM/023235 | Support |  |  |  | 30/10/2024 |  |  | 12/11/2024 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 270 | 20151 | 0 | 0 |  | NAN