## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Tamluk Division | PURBA MEDINIPUR |  | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division | SM/08683 | TSM/007240 | Support | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 23/08/2021 | 24/08/2021 | 31/12/2023 | 22/05/2023 | 0 | 0 | inf | nan | 60 | 0
2 | Tamluk Division | PURBA MEDINIPUR |  | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/09021 | TSM/008131 | Support |  |  |  | 30/10/2021 | 25/11/2022 | 31/12/2023 | 05/10/2023 | 0 | 0 | inf | nan | 30 | 0
3 | Tamluk Division | PURBA MEDINIPUR |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | TSM/008140 | Support |  |  |  | 30/10/2021 | 03/08/2023 | 31/03/2024 | 05/10/2023 | 0 | 0 | inf | nan | 15 | 0
4 | Tamluk Division | PURBA MEDINIPUR | Mahisadal | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | TSM/008368 | Augmentation | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 03/11/2021 | 08/03/2022 | 31/12/2023 | 05/10/2023 | 0 | 2920 | inf | nan | 90 | 0
5 | Tamluk Division | PURBA MEDINIPUR | Mahisadal | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | TSM/008435 | Augmentation | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 03/11/2021 | 11/02/2022 | 31/12/2023 | 12/06/2023 | 0 | 3478 | inf | nan | 50 | 0
6 | Tamluk Division | PURBA MEDINIPUR | Panskura | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | TSM/008436 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/11/2021 | 23/02/2022 | 31/12/2023 | 06/11/2023 | 0 | 4335 | inf | nan | 96 | 0
7 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - I | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. | SM/09800 | TSM/009108 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 01/12/2021 | 19/01/2022 | 31/12/2023 | 12/06/2023 | 0 | 2550 | inf | nan | 95 | 0
8 | Tamluk Division | PURBA MEDINIPUR | Moyna | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. | SM/09803 | TSM/009116 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 01/12/2021 | 19/01/2022 | 31/12/2023 | 12/06/2023 | 0 | 2633 | inf | nan | 90 | 0
9 | Tamluk Division | PURBA MEDINIPUR | Egra - I | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | SM/09804 | TSM/009110 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 01/12/2021 | 19/01/2022 | 31/03/2024 | 12/06/2023 | 0 | 2783 | inf | nan | 80 | 0
10 | Tamluk Division | PURBA MEDINIPUR | Chandipur | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | TSM/008357 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 10/12/2021 | 05/04/2022 | 31/03/2024 | 03/11/2023 | 0 | 4407 | inf | nan | 96 | 0
11 | Tamluk Division | PURBA MEDINIPUR | Deshopran | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | TSM/009590 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 12/07/2022 | 31/12/2023 | 12/06/2023 | 0 | 1833 | inf | nan | 50 | 0
12 | Tamluk Division | PURBA MEDINIPUR | Contai - III | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | SM/10345 | TSM/009922 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 16/03/2022 | 28/03/2022 | 31/12/2023 | 12/06/2023 | 0 | 13 | inf | nan | 90 | 0
13 | Tamluk Division | PURBA MEDINIPUR | Haldia | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | TSM/009767 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 29/03/2022 | 03/03/2023 | 31/03/2024 | 06/11/2023 | 0 | 2729 | inf | nan | 51 | 0
14 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - I | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block | SM/10432 | TSM/010126 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 12/04/2022 | 25/04/2022 | 31/03/2024 | 12/06/2023 | 0 | 2488 | inf | nan | 80 | 0
15 | Tamluk Division | PURBA MEDINIPUR | Panskura | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. | SM/10585 | TSM/010151 | New |  |  |  | 18/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1356 | inf | nan | 8 | 0
16 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. | SM/10586 | TSM/010150 | New |  |  |  | 18/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1311 | inf | nan | 8 | 0
17 | Tamluk Division | PURBA MEDINIPUR | Khejuri - I | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | TSM/010122 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 18/04/2022 | 08/08/2022 | 31/12/2023 | 12/06/2023 | 0 | 0 | inf | nan | 35 | 0
18 | Tamluk Division | PURBA MEDINIPUR | Khejuri - I | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | TSM/010120 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 18/04/2022 | 14/10/2022 | 31/12/2023 | 12/06/2023 | 0 | 0 | inf | nan | 40 | 0
19 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | TSM/010094 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 18/04/2022 | 12/07/2022 | 31/12/2023 | 14/09/2023 | 0 | 0 | inf | nan | 36 | 0
20 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - II | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. | SM/10617 | TSM/010295 | New |  |  |  | 20/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 704 | inf | nan | 8 | 0
21 | Tamluk Division | PURBA MEDINIPUR | Panskura | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. | SM/10618 | TSM/010147 | New |  |  |  | 20/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1306 | inf | nan | 8 | 0
22 | Tamluk Division | PURBA MEDINIPUR | Bhagawanpur - II | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10619 | TSM/010131 | New |  |  |  | 20/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1080 | inf | nan | 8 | 0
23 | Tamluk Division | PURBA MEDINIPUR | Potashpur - II | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. | SM/10620 | TSM/010128 | New |  |  |  | 20/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1279 | inf | nan | 8 | 0
24 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - I | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. | SM/10621 | TSM/010127 | New |  |  |  | 20/04/2022 | 10/03/2023 | 31/12/2023 | 05/10/2023 | 0 | 1105 | inf | nan | 8 | 0
25 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | TSM/010095 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/04/2022 | 12/07/2022 | 31/12/2023 | 14/09/2023 | 0 | 5157 | inf | nan | 98 | 0
26 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | TSM/010118 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/04/2022 | 02/11/2022 | 31/12/2023 | 12/06/2023 | 0 | 0 | inf | nan | 50 | 0
27 | Tamluk Division | PURBA MEDINIPUR | Chandipur | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10666 | TSM/010130 | New |  |  |  | 26/04/2022 | 05/04/2023 | 31/12/2023 | 14/09/2023 | 0 | 1451 | inf | nan | 8 | 0
28 | Tamluk Division | PURBA MEDINIPUR | Tamluk | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10681 | TSM/008372 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 06/05/2022 | 01/12/2022 | 31/12/2023 | 12/06/2023 | 0 | 6101 | inf | nan | 55 | 0
29 | Tamluk Division | PURBA MEDINIPUR | Nanda Kumar | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | TSM/008369 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 06/05/2022 | 26/09/2022 | 31/12/2023 | 14/09/2023 | 0 | 5547 | inf | nan | 65 | 0
30 | Tamluk Division | PURBA MEDINIPUR | Sutahata | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | TSM/008367 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 06/05/2022 | 14/10/2022 | 31/12/2023 | 12/06/2023 | 0 | 5528 | inf | nan | 50 | 0
31 | Tamluk Division | PURBA MEDINIPUR | Bhagawanpur - I | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10689 | TSM/010132 | New |  |  |  | 12/05/2022 | 05/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 2443 | inf | nan | 4 | 0
32 | Tamluk Division | PURBA MEDINIPUR | Egra - II | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I | SM/10725 | TSM/010096 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 18/05/2022 | 20/12/2022 | 31/03/2024 | 12/06/2023 | 0 | 3032 | inf | nan | 33 | 0
33 | Tamluk Division | PURBA MEDINIPUR | Contai - III | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. | SM/11613 | TSM/010580 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 26/07/2022 | 18/08/2022 | 31/12/2023 | 12/06/2023 | 0 | 0 | inf | nan | 35 | 0
34 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) | SM/11616 | TSM/011148 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 26/07/2022 | 02/11/2022 | 31/12/2023 | 05/10/2023 | 0 | 0 | inf | nan | 82 | 0
35 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | SM/11618 | TSM/011144 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 26/07/2022 | 02/11/2022 | 31/03/2024 | 14/09/2023 | 0 | 6291 | inf | nan | 84 | 0
36 | Tamluk Division | PURBA MEDINIPUR |  | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. | SM/11710 | TSM/011709 | Support | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/08/2022 | 02/11/2022 | 31/03/2024 | 05/10/2023 | 0 | 0 | inf | nan | 35 | 0
37 | Tamluk Division | PURBA MEDINIPUR |  | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | TSM/011710 | Support | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/08/2022 | 30/12/2022 | 31/03/2024 | 05/10/2023 | 0 | 0 | inf | nan | 30 | 0
38 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) | SM/11948 | TSM/010119 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 24/08/2022 | 02/11/2022 | 31/12/2023 | 12/06/2023 | 0 | 4380 | inf | nan | 60 | 0
39 | Tamluk Division | PURBA MEDINIPUR | Sahid Matangini | GOBINDAPUR & ADJOINING MOUZAS | SM/12149 | TSM/013193 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 07/09/2022 | 12/07/2023 | 31/03/2024 | 12/09/2023 | 0 | 910 | inf | nan | 9 | 0
40 | Tamluk Division | PURBA MEDINIPUR | Sahid Matangini | HOGALBERYA AND ADJOINING MOUJAS PWSS | SM/12150 | TSM/013195 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 07/09/2022 | 12/07/2023 | 31/03/2024 | 12/09/2023 | 0 | 2680 | inf | nan | 9 | 0
41 | Tamluk Division | PURBA MEDINIPUR | Sahid Matangini | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. | SM/12301 | TSM/010963 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 09/09/2022 | 26/09/2022 | 31/12/2023 | 05/10/2023 | 0 | 2244 | inf | nan | 80 | 0
42 | Tamluk Division | PURBA MEDINIPUR | Khejuri - II | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | SM/12302 | TSM/010936 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 09/09/2022 | 09/12/2022 | 31/12/2023 | 06/11/2023 | 0 | 763 | inf | nan | 95 | 0
43 | Tamluk Division | PURBA MEDINIPUR | Egra - II | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | SM/12303 | TSM/013464 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 09/09/2022 | 17/02/2023 | 31/03/2024 | 12/09/2023 | 0 | 2340 | inf | nan | 30 | 0
44 | Tamluk Division | PURBA MEDINIPUR | Bhagawanpur - I | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | SM/12404 | TSM/014419 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 13/09/2022 | 10/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 1656 | inf | nan | 9 | 0
45 | Tamluk Division | PURBA MEDINIPUR | Deshopran | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | SM/12405 | TSM/014390 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 13/09/2022 | 21/07/2023 | 31/03/2024 | 12/09/2023 | 0 | 893 | inf | nan | 5 | 0
46 | Tamluk Division | PURBA MEDINIPUR | Potashpur - I | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | TSM/014777 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 13/09/2022 | 25/07/2023 | 31/03/2024 | 06/11/2023 | 0 | 1833 | inf | nan | 5 | 0
47 | Tamluk Division | PURBA MEDINIPUR | Sahid Matangini | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | TSM/014723 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/09/2022 | 02/05/2023 | 31/03/2024 | 12/09/2023 | 0 | 1914 | inf | nan | 9 | 0
48 | Tamluk Division | PURBA MEDINIPUR | Khejuri - I | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | TSM/014704 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/09/2022 | 12/07/2023 | 31/03/2024 | 06/11/2023 | 0 | 2411 | inf | nan | 10 | 0
49 | Tamluk Division | PURBA MEDINIPUR |  | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. | SM/13369 | TSM/014316 | Support |  |  |  | 19/10/2022 | 10/01/2023 | 31/03/2024 | 05/10/2023 | 0 | 0 | inf | nan | 20 | 0
50 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - II | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | TSM/015729 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 14/11/2022 | 10/03/2023 | 31/03/2024 | 12/09/2023 | 0 | 2111 | inf | nan | 9 | 0
51 | Tamluk Division | PURBA MEDINIPUR | Contai - I | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | TSM/015579 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 14/11/2022 | 12/05/2023 | 31/03/2024 | 03/11/2023 | 0 | 1475 | inf | nan | 24 | 0
52 | Tamluk Division | PURBA MEDINIPUR | Mahisadal | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | TSM/016024 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 25/11/2022 | 20/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 249 | inf | nan | 5 | 0
53 | Tamluk Division | PURBA MEDINIPUR | Contai - I | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | TSM/016081 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/11/2022 | 16/08/2023 | 31/03/2024 | 12/09/2023 | 0 | 1023 | inf | nan | 5 | 0
54 | Tamluk Division | PURBA MEDINIPUR |  | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission | SM/14458 | TSM/017553 | Support |  |  |  | 20/01/2023 | 20/09/2023 | 31/03/2024 | 05/10/2023 | 0 | 0 | inf | nan | 5 | 0
55 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - I | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | TSM/019331 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 20/02/2023 | 31/07/2023 | 31/03/2024 | 06/11/2023 | 0 | 158 | inf | nan | 9 | 0
56 | Tamluk Division | PURBA MEDINIPUR | Contai - I | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16257 | TSM/017160 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 24/02/2023 | 08/06/2023 | 31/03/2024 | 12/09/2023 | 0 | 958 | inf | nan | 9 | 0
57 | Tamluk Division | PURBA MEDINIPUR | Moyna | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me | SM/16452 | TSM/013424 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/12/2023 | 14/09/2023 | 0 | 610 | inf | nan | 75 | 0
58 | Tamluk Division | PURBA MEDINIPUR | Bhagawanpur - II | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | SM/16453 | TSM/017483 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 08/06/2023 | 31/03/2024 | 19/07/2023 | 0 | 1321 | inf | nan | 30 | 0
59 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - II | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | TSM/018905 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 03/03/2023 | 05/06/2023 | 31/03/2024 | 08/08/2023 | 0 | 675 | inf | nan | 11 | 0
60 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - II | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | SM/16461 | TSM/018238 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 03/03/2023 | 17/05/2023 | 31/03/2024 | 12/09/2023 | 0 | 176 | inf | nan | 7 | 0
61 | Tamluk Division | PURBA MEDINIPUR | Mahisadal | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | SM/16463 | TSM/018162 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 03/03/2023 | 19/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 920 | inf | nan | 7 | 0
62 | Tamluk Division | PURBA MEDINIPUR | Egra - II | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) | SM/16466 | TSM/018683 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 305 | inf | nan | 10 | 0
63 | Tamluk Division | PURBA MEDINIPUR | Ramnagar - I | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) | SM/16467 | TSM/018682 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 319 | inf | nan | 30 | 0
64 | Tamluk Division | PURBA MEDINIPUR | Kolaghat | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) | SM/16468 | TSM/018312 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 545 | inf | nan | 25 | 0
65 | Tamluk Division | PURBA MEDINIPUR | Kolaghat | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M | SM/16469 | TSM/018277 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/12/2023 | 14/09/2023 | 0 | 1180 | inf | nan | 78 | 0
66 | Tamluk Division | PURBA MEDINIPUR | Kolaghat | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA | SM/16470 | TSM/018280 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/03/2023 | 19/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 851 | inf | nan | 15 | 0
67 | Tamluk Division | PURBA MEDINIPUR | Egra - I | Augmentation of Ground Water Based Bagmari Water Supply Scheme | SM/16711 | TSM/009993 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 14/03/2023 | 04/05/2023 | 31/03/2024 | 03/11/2023 | 0 | 929 | inf | nan | 64 | 0
68 | Tamluk Division | PURBA MEDINIPUR | Potashpur - II | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | SM/16713 | TSM/009924 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 14/03/2023 | 07/08/2023 | 31/03/2024 | 12/09/2023 | 0 | 0 | inf | nan | 4 | 0
69 | Tamluk Division | PURBA MEDINIPUR | Deshopran | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16939 | TSM/020298 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2023 | 20/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 0 | inf | nan | 3 | 0
70 | Tamluk Division | PURBA MEDINIPUR | Egra - II | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16941 | TSM/018767 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2023 | 05/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 896 | inf | nan | 16 | 0
71 | Tamluk Division | PURBA MEDINIPUR | Contai - III | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) | SM/16946 | TSM/020297 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 16/03/2023 | 19/05/2023 | 31/03/2024 | 12/09/2023 | 0 | 0 | inf | nan | 10 | 0
72 | Tamluk Division | PURBA MEDINIPUR | Deshopran | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/16948 | TSM/020289 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2023 | 05/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 322 | inf | nan | 4 | 0
73 | Tamluk Division | PURBA MEDINIPUR | Deshopran | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte | SM/17173 | TSM/020403 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 16/03/2023 | 05/04/2023 | 31/03/2024 | 12/09/2023 | 0 | 840 | inf | nan | 16 | 0
Total | [14 empty] | 0 | 111747 | 0 | 0 |  | NAN