## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06792 | TSM/005755 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 23/09/2020 | 09/10/2020 | 28/02/2022 | 12/06/2023 | 0 | 981 | inf | nan | 100 | 0
2 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41) , Baurisol (42) and Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its | SM/06795 | TSM/005758 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 23/09/2020 | 11/12/2020 | 28/02/2022 | 21/07/2023 | 0 | 1090 | inf | nan | 100 | 0
3 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | SM/06801 | TSM/005748 | Retrofitting | Khatra Sub-Division |  | Junior Engineer | 23/09/2020 | 09/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 580 | inf | nan | 100 | 0
4 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Taldanga, Upar Narrah, Khe | SM/06806 | TSM/005733 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 23/09/2020 | 09/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 1057 | inf | nan | 100 | 0
5 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mouzas (Junbedia) of HARIALGORA (Z | SM/06817 | TSM/005738 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 23/09/2020 | 08/10/2020 | 28/02/2022 | 12/06/2023 | 0 | 881 | inf | nan | 100 | 0
6 | Bankura Division | BANKURA | Chhatna | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyalda | SM/07240 | TSM/005975 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 09/07/2021 | 28/02/2022 | 12/06/2023 | 0 | 1131 | inf | nan | 100 | 0
7 | Bankura Division | BANKURA | Bankura - I | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | SM/07244 | TSM/005985 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/12/2020 | 18/11/2021 | 31/12/2024 | 31/08/2024 | 0 | 806 | inf | nan | 90 | 0
8 | Bankura Division | BANKURA | Bankura - I | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dadhimukha, Jamboni,Jagdal | SM/07245 | TSM/005986 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 19/01/2021 | 28/02/2022 | 12/06/2023 | 0 | 1185 | inf | nan | 100 | 0
9 | Bankura Division | BANKURA | Bankura - I | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | TSM/005991 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 10/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 918 | inf | nan | 100 | 0
10 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | TSM/005922 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 665 | inf | nan | 100 | 0
11 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Purunia, sangrampur, Laxminarayanpur, Baharkhulia & Gangadarpu | SM/07256 | TSM/005923 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 19/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 700 | inf | nan | 100 | 0
12 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Dakaisini, Khandari, Bansol, Dhwajmonipur & Damodarpur) of | SM/07260 | TSM/005927 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 08/12/2020 | 19/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 959 | inf | nan | 100 | 0
13 | Bankura Division | BANKURA | Khatra | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Bara | SM/07265 | TSM/005892 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 08/12/2020 | 23/09/2021 |  | 09/04/2024 | 0 | 874 | inf | nan | 100 | 0
14 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | TSM/005908 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 08/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 1265 | inf | nan | 100 | 0
15 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | TSM/006001 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 10/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 1304 | inf | nan | 100 | 0
16 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - II) of MALIARA (Zone - A) under Bankura - I,II & | SM/07307 | TSM/006006 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 25/02/2021 | 31/03/2022 | 12/06/2023 | 0 | 954 | inf | nan | 100 | 0
17 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | TSM/005994 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 19/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 932 | inf | nan | 100 | 0
18 | Bankura Division | BANKURA | Bankura - I | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola | SM/07318 | TSM/005983 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 04/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 1164 | inf | nan | 100 | 0
19 | Bankura Division | BANKURA | Chhatna | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | TSM/005944 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 10/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 995 | inf | nan | 100 | 0
20 | Bankura Division | BANKURA | Chhatna | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 Nos. Mouzas (Malpara, Harokabedy, Mangalda, Palsora, Kalai, Amdiha, Parasi | SM/07324 | TSM/005956 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 05/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 1058 | inf | nan | 100 | 0
21 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Ramchandrapur, Paschim Brindabanpur, Palsana & Saluka) of Jo | SM/07328 | TSM/005965 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 923 | inf | nan | 100 | 0
22 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Wa | SM/07331 | TSM/005907 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 10/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 1207 | inf | nan | 100 | 0
23 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis | SM/07334 | TSM/005911 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 10/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 1254 | inf | nan | 100 | 0
24 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | TSM/005920 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 10/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 955 | inf | nan | 100 | 0
25 | Bankura Division | BANKURA | Barjora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | TSM/005932 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 11/12/2020 | 19/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 1056 | inf | nan | 100 | 0
26 | Bankura Division | BANKURA | Bankura - I | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos mousas (Helna, Fagua kanali, Dumur | SM/07348 | TSM/005934 | Retrofitting | Bankura Sadar Sub-Division |  | Junior Engineer | 11/12/2020 | 10/02/2021 | 28/02/2022 | 12/06/2023 | 0 | 1018 | inf | nan | 100 | 0
27 | Bankura Division | BANKURA | Sonamukhi | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-B) | SM/07351 | TSM/006011 | Retrofitting | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 25/08/2021 | 28/12/2024 | 20/02/2024 | 0 | 869 | inf | nan | 89 | 0
28 | Bankura Division | BANKURA | Khatra | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | TSM/005891 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 828 | inf | nan | 100 | 0
29 | Bankura Division | BANKURA | Khatra | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) & Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under | SM/07356 | TSM/005895 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 05/02/2021 | 31/08/2024 | 02/09/2024 | 0 | 735 | inf | nan | 100 | 0
30 | Bankura Division | BANKURA | Khatra | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Z | SM/07360 | TSM/005899 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 05/02/2021 | 30/10/2024 | 02/09/2024 | 0 | 1103 | inf | nan | 100 | 0
31 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Raniban | SM/07362 | TSM/005905 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 939 | inf | nan | 100 | 0
32 | Bankura Division | BANKURA | Hirbandh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (6 | SM/07364 | TSM/005913 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 788 | inf | nan | 100 | 0
33 | Bankura Division | BANKURA | Khatra | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (1 | SM/07366 | TSM/005915 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 11/12/2020 | 29/12/2020 | 28/02/2022 | 12/06/2023 | 0 | 945 | inf | nan | 100 | 0
34 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | TSM/007313 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 25/05/2021 | 23/09/2021 | 30/06/2024 | 01/07/2024 | 0 | 1000 | inf | nan | 100 | 0
35 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S | SM/09234 | TSM/007315 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 25/05/2021 | 23/09/2021 |  | 09/04/2024 | 0 | 967 | inf | nan | 100 | 0
36 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by | SM/09235 | TSM/007317 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 25/05/2021 | 08/11/2021 |  | 09/04/2024 | 0 | 885 | inf | nan | 100 | 0
37 | Bankura Division | BANKURA | Chhatna | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | TSM/005972 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 15/12/2021 | 29/03/2024 | 09/08/2023 | 0 | 917 | inf | nan | 100 | 0
38 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Ekteswar (Part, 70%) & Sankarhati) of pipe water supply scheme for E | SM/09310 | TSM/007478 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 16/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 452 | inf | nan | 90 | 0
39 | Bankura Division | BANKURA | Saltora | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 nos. Mouzas (Kastara, Rangamati, Kendana, Sat-deuli) of pipe water supply sc | SM/09311 | TSM/007479 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 18/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 38 | inf | nan | 90 | 0
40 | Bankura Division | BANKURA | Barjora | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Su | SM/09312 | TSM/007457 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 09/03/2022 | 31/12/2024 | 20/09/2024 | 0 | 1949 | inf | nan | 95 | 0
41 | Bankura Division | BANKURA | Barjora | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Hariramp | SM/09313 | TSM/007458 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 17/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 938 | inf | nan | 90 | 0
42 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | TSM/007482 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 11/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 3480 | inf | nan | 90 | 0
43 | Bankura Division | BANKURA | Bankura - II | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | TSM/007466 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 20/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 2035 | inf | nan | 95 | 0
44 | Bankura Division | BANKURA | Barjora | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishn | SM/09327 | TSM/007474 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 13/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 2355 | inf | nan | 90 | 0
45 | Bankura Division | BANKURA | Barjora | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 nos. Mouzas (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, P | SM/09328 | TSM/007475 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/11/2021 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 1891 | inf | nan | 90 | 0
46 | Bankura Division | BANKURA | Sonamukhi | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | TSM/008992 | Augmentation | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 25/01/2023 | 31/12/2024 | 24/08/2024 | 0 | 1564 | inf | nan | 88 | 0
47 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | SM/09475 | TSM/008190 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 28/02/2022 |  | 09/04/2024 | 0 | 0 | inf | nan | 100 | 0
48 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas by retrofitting of Water Supply Scheme for Pa | SM/09476 | TSM/008191 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 28/02/2022 |  | 09/04/2024 | 0 | 569 | inf | nan | 100 | 0
49 | Bankura Division | BANKURA | Raipur | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | TSM/008193 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 03/01/2022 |  | 09/04/2024 | 0 | 0 | inf | nan | 100 | 0
50 | Bankura Division | BANKURA | Ranibundh | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | SM/09498 | TSM/008195 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 30/04/2023 | 31/12/2024 | 20/09/2024 | 0 | 2933 | inf | nan | 90 | 0
51 | Bankura Division | BANKURA | Chhatna | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | TSM/008407 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 22/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 2721 | inf | nan | 90 | 0
52 | Bankura Division | BANKURA | Chhatna | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | TSM/008409 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 23/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 2274 | inf | nan | 90 | 0
53 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), | SM/09503 | TSM/008410 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 14/12/2021 |  | 05/04/2024 | 0 | 2356 | inf | nan | 90 | 0
54 | Bankura Division | BANKURA | Onda | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur | SM/09529 | TSM/008624 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 25/04/2022 | 31/12/2024 | 01/07/2024 | 0 | 2872 | inf | nan | 90 | 0
55 | Bankura Division | BANKURA | Onda | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by | SM/09530 | TSM/008626 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 21/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 3143 | inf | nan | 97 | 0
56 | Bankura Division | BANKURA | Onda | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | SM/09534 | TSM/008648 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 19/11/2021 | 21/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 2339 | inf | nan | 90 | 0
57 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and | SM/09618 | TSM/007303 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 25/11/2021 | 30/06/2024 | 01/07/2024 | 0 | 1119 | inf | nan | 100 | 0
58 | Bankura Division | BANKURA | Indus | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | TSM/007405 | Retrofitting | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 01/02/2022 | 31/12/2024 | 20/02/2024 | 0 | 2610 | inf | nan | 95 | 0
59 | Bankura Division | BANKURA | Indus | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | TSM/007407 | Retrofitting | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 13/09/2022 | 31/12/2024 | 10/08/2024 | 0 | 3761 | inf | nan | 85 | 0
60 | Bankura Division | BANKURA | Barjora | New pipe line with Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas | SM/09632 | TSM/007460 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 27/11/2021 | 31/12/2024 | 20/09/2024 | 0 | 1796 | inf | nan | 90 | 0
61 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme ( | SM/09635 | TSM/007282 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 25/11/2021 |  | 09/04/2024 | 0 | 813 | inf | nan | 100 | 0
62 | Bankura Division | BANKURA | Simlapal | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | SM/09641 | TSM/007288 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 12/05/2022 |  | 09/04/2024 | 0 | 2304 | inf | nan | 100 | 0
63 | Bankura Division | BANKURA | Sarenga | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | TSM/007294 | Retrofitting | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 24/11/2021 | 03/03/2022 |  | 09/04/2024 | 0 | 1015 | inf | nan | 100 | 0
64 | Bankura Division | BANKURA | Onda | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | SM/09853 | TSM/008038 | Augmentation | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 03/12/2021 | 09/02/2022 | 31/12/2024 | 20/09/2024 | 0 | 7078 | inf | nan | 99 | 0
65 | Bankura Division | BANKURA | Bankura - I | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | TSM/005016 | Augmentation | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/12/2021 | 06/07/2022 | 31/12/2024 | 04/10/2024 | 0 | 3690 | inf | nan | 82 | 0
66 | Bankura Division | BANKURA | Jaypur | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | TSM/008990 | Augmentation | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 09/12/2021 | 06/02/2023 | 31/12/2024 | 25/07/2024 | 0 | 1224 | inf | nan | 81 | 0
67 | Bankura Division | BANKURA | Indpur | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10858 | TSM/012415 | New | RWS Bankura Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 10/12/2022 | 31/07/2024 | 20/04/2024 | 0 | 36 | inf | nan | 92 | 0
68 | Bankura Division | BANKURA | Bankura - I | MINI PIPED WATER SUPPLY SCHEME FOR SUPURDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10899 | TSM/012113 | New | RWS Bankura Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 22/08/2022 | 30/07/2024 | 20/04/2024 | 0 | 20 | inf | nan | 85 | 0
69 | Bankura Division | BANKURA | Bankura - I | MINI PIPED WATER SUPPLY SCHEME FOR MAKARKENDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10900 | TSM/012115 | New | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 06/12/2022 | 30/06/2024 | 20/04/2024 | 0 | 40 | inf | nan | 85 | 0
70 | Bankura Division | BANKURA | Bankura - I | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10902 | TSM/012118 | New | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 23/12/2022 | 30/07/2024 | 20/04/2024 | 0 | 51 | inf | nan | 85 | 0
71 | Bankura Division | BANKURA | Bankura - I | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10906 | TSM/012140 | New | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 19/12/2022 | 24/07/2024 | 20/04/2024 | 0 | 76 | inf | nan | 85 | 0
72 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Jamsala, House Hold:60) | SM/11143 | TSM/012260 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 317 | inf | nan | 82 | 0
73 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balananda, House Hold:42) | SM/11147 | TSM/012256 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 19/04/2024 | 0 | 508 | inf | nan | 88 | 0
74 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balaramp[ur, House Hold:49) | SM/11149 | TSM/012254 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 591 | inf | nan | 87 | 0
75 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) | SM/11151 | TSM/012252 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/08/2022 | 31/12/2024 | 08/04/2024 | 0 | 244 | inf | nan | 89 | 0
76 | Bankura Division | BANKURA | Kotulpur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Metelsair, House Hold No.: 93) | SM/11153 | TSM/012250 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 384 | inf | nan | 86 | 0
77 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) | SM/11156 | TSM/012247 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 20 | inf | nan | 88 | 0
78 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Radhanagar, House Hold No.: 97) | SM/11171 | TSM/012242 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 04/10/2024 | 0 | 97 | inf | nan | 85 | 0
79 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) | SM/11175 | TSM/012236 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 04/10/2024 | 0 | 75 | inf | nan | 85 | 0
80 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Kumardubi, House Hold No.: 50) | SM/11176 | TSM/012234 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 50 | inf | nan | 96 | 0
81 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Hajipur, House Hold No.: 87) | SM/11177 | TSM/012232 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 04/10/2024 | 0 | 87 | inf | nan | 95 | 0
82 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chanpatala, House Hold No.: 63) | SM/11179 | TSM/012229 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 63 | inf | nan | 86 | 0
83 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Basantapur, House Hold No.: 62) | SM/11181 | TSM/012226 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 62 | inf | nan | 93 | 0
84 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Mahishabandi, House Hold No.: 93) | SM/11183 | TSM/012221 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 399 | inf | nan | 81 | 0
85 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Shibdanga, House Hold No.: 74) | SM/11184 | TSM/012218 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 74 | inf | nan | 81 | 0
86 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) | SM/11434 | TSM/012230 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 71 | inf | nan | 90 | 0
87 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) | SM/11435 | TSM/012228 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 208 | inf | nan | 87 | 0
88 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Parashia, House Hold:71 | SM/11443 | TSM/012205 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 71 | inf | nan | 90 | 0
89 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Brindabanpur, House Hold:60 | SM/11445 | TSM/012193 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 20/10/2022 | 31/12/2024 | 08/04/2024 | 0 | 183 | inf | nan | 85 | 0
90 | Bankura Division | BANKURA | Patrasayer | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Bhetia, House Hold:78 | SM/11449 | TSM/012181 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 10/10/2022 | 31/12/2024 | 22/02/2024 | 0 | 78 | inf | nan | 87 | 0
91 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bagsara, House Hold No.: 25) | SM/11683 | TSM/012159 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 25 | inf | nan | 92 | 0
92 | Bankura Division | BANKURA | Jaypur | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Madhurpur, House Hold No.: 93) | SM/11692 | TSM/012127 | New | Brishnupur Sub-Division | Assistant Engineer | Junior Engineer | 30/05/2022 | 05/08/2022 | 31/12/2024 | 25/06/2024 | 0 | 93 | inf | nan | 94 | 0
93 | Bankura Division | BANKURA | Chhatna | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | SM/11823 | TSM/011376 | Retrofitting | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/08/2022 | 27/08/2022 | 31/12/2024 | 20/09/2024 | 0 | 8274 | inf | nan | 90 | 0
94 | Bankura Division | BANKURA | Sarenga | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | SM/12381 | TSM/011121 | Augmentation | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 13/09/2022 | 15/09/2022 |  | 09/04/2024 | 0 | 607 | inf | nan | 100 | 0
95 | Bankura Division | BANKURA | Bankura - II | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | TSM/014178 | Augmentation | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 22/09/2022 | 23/02/2023 | 31/05/2023 | 12/06/2023 | 0 | 1946 | inf | nan | 100 | 0
96 | Bankura Division | BANKURA | Khatra | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | TSM/016323 | Augmentation | Khatra Sub-Division | Assistant Engineer | Junior Engineer | 04/02/2023 | 01/06/2023 | 31/12/2025 | 24/07/2024 | 0 | 608 | inf | nan | 81 | 0
97 | Bankura Division | BANKURA | Bankura - I | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | SM/16951 | TSM/019126 | Augmentation | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/03/2023 | 14/08/2023 | 31/10/2024 | 20/07/2024 | 0 | 180 | inf | nan | 85 | 0
98 | Bankura Division | BANKURA | Chhatna | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | TSM/018939 | Augmentation | Bankura Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/03/2023 | 20/03/2023 | 31/03/2025 | 30/08/2024 | 0 | 765 | inf | nan | 85 | 0
Total | [14 empty] | 0 | 111510 | 0 | 0 |  | NAN