## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | TSM/005581 | Retrofitting | RCFA Division I | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | 21/12/2020 | 23/12/2020 | 30/09/2024 | 23/09/2024 | 72 | 9726 | inf | inf | 95 | 97
2 | RCFA Division I | PASCHIM BARDHAMAN | Salanpur | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | TSM/004718 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | 10/12/2021 | 24/02/2022 | 31/08/2024 | 18/01/2024 | 167 | 29009 | inf | inf | 84 | 74
3 | RCFA Division I | PASCHIM BARDHAMAN | Barabani | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | TSM/009727 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | 11/02/2022 | 12/02/2022 | 31/08/2024 | 18/01/2024 | 23 | 3513 | inf | inf | 84 | 62
4 | RCFA Division I | PASCHIM BARDHAMAN | Barabani | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | TSM/010518 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | 19/04/2022 | 20/04/2022 | 31/08/2024 | 18/01/2024 | 20 | 2773 | inf | inf | 80 | 45
5 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | TSM/009730 | Augmentation | RCFA Division I | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 22/04/2022 | 25/04/2022 | 31/08/2024 | 18/01/2024 | 11 | 0 | inf | inf | 51 | 10
6 | RCFA Division I | PASCHIM BARDHAMAN | Barabani | Augmentation of Roshna Piped Water Supply Scheme . | SM/10642 | TSM/010052 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | 22/04/2022 | 25/04/2022 | 31/08/2024 | 18/01/2024 | 28 | 1250 | inf | inf | 87 | 60
7 | RCFA Division I | PASCHIM BARDHAMAN | Barabani | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | TSM/010051 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 22/04/2022 | 26/04/2022 | 31/08/2024 | 18/01/2024 | 29 | 1738 | inf | inf | 85 | 58
8 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | Augmentation of Madantor Water Supply Scheme | SM/10845 | TSM/010054 | Augmentation | RCFA Division I | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | 30/05/2022 | 31/05/2022 | 31/08/2024 | 18/01/2024 | 14 | 1125 | inf | inf | 83 | 35
9 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | TSM/009729 | Augmentation | RCFA Division I | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | 06/06/2022 | 07/06/2022 | 31/08/2024 | 18/01/2024 | 13 | 555 | inf | inf | 70 | 47
10 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | TSM/011412 | Augmentation | RCFA Division I | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | 22/07/2022 | 25/07/2022 | 31/08/2024 | 18/01/2024 | 15 | 4240 | inf | inf | 31 | 59
11 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | TSM/011404 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/07/2022 | 25/07/2022 | 31/08/2024 | 18/01/2024 | 10 | 3367 | inf | inf | 30 | 32
12 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | TSM/012742 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 15 | 5048 | inf | inf | 90 | 54
13 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | TSM/014345 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 10 | 3450 | inf | inf | 20 | 35
14 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | TSM/014346 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 13 | 4411 | inf | inf | 20 | 35
15 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | TSM/014347 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 12 | 3468 | inf | inf | 35 | 28
16 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | TSM/014348 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 16 | 1976 | inf | inf | 20 | 41
17 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | TSM/014349 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 19 | 2623 | inf | inf | 25 | 39
18 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | TSM/014350 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 7 | 4933 | inf | inf | 20 | 49
19 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | TSM/014351 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 02/09/2022 | 31/08/2024 | 18/01/2024 | 9 | 2558 | inf | inf | 21 | 36
20 | RCFA Division I | PASCHIM BARDHAMAN | Pandabeswar | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | TSM/014352 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 19 | 794 | inf | inf | 30 | 39
21 | RCFA Division I | PASCHIM BARDHAMAN | Pandabeswar | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | TSM/014353 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 10 | 2865 | inf | inf | 40 | 44
22 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | TSM/014354 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 10 | 2426 | inf | inf | 40 | 15
23 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | TSM/014355 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 8 | 3700 | inf | inf | 70 | 48
24 | RCFA Division I | PASCHIM BARDHAMAN | Jamuria | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | TSM/014356 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 10 | 3472 | inf | inf | 20 | 28
25 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | TSM/014357 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 01/09/2022 | 05/09/2022 | 31/08/2024 | 18/01/2024 | 8 | 4861 | inf | inf | 50 | 69
26 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | TSM/014889 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 07/09/2022 | 08/09/2022 | 31/08/2024 | 18/01/2024 | 24 | 2833 | inf | inf | 20 | 67
27 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | TSM/014885 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 07/09/2022 | 08/09/2022 | 31/08/2024 | 18/01/2024 | 38 | 2548 | inf | inf | 50 | 59
28 | RCFA Division I | PASCHIM BARDHAMAN | Pandabeswar | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. | SM/12216 | TSM/014880 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 07/09/2022 | 08/09/2022 | 31/08/2024 | 18/01/2024 | 10 | 1685 | inf | inf | 20 | 44
29 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. | SM/12218 | TSM/014890 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 07/09/2022 | 08/09/2022 | 31/08/2024 | 18/01/2024 | 21 | 1081 | inf | inf | 60 | 42
30 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | TSM/014376 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 18 | 2886 | inf | inf | 35 | 50
31 | RCFA Division I | PASCHIM BARDHAMAN | Raniganj | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | TSM/014878 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 14 | 1364 | inf | inf | 55 | 62
32 | RCFA Division I | PASCHIM BARDHAMAN | Pandabeswar | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | TSM/013220 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 4 | 2224 | inf | inf | 40 | 19
33 | RCFA Division I | PASCHIM BARDHAMAN | Pandabeswar | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | TSM/013219 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 18 | 2096 | inf | inf | 20 | 38
34 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | TSM/012791 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 17 | 2270 | inf | inf | 16 | 54
35 | RCFA Division I | PASCHIM BARDHAMAN | Ondal | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | TSM/012768 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 07/09/2022 | 09/09/2022 | 31/08/2024 | 18/01/2024 | 16 | 181 | inf | inf | 18 | 29
Total | [14 empty] | 748 | 123049 | 0 | 0 |  | NAN