## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme | SM/08013 | TSM/007058 | Retrofitting |  |  |  | 25/01/2021 | 05/05/2021 | 30/11/2021 | 12/06/2023 | 1 | 1951 | inf | inf | 95 | 45
2 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur Part-I, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme | SM/08015 | TSM/007057 | Retrofitting |  |  |  | 25/01/2021 |  | 30/11/2021 | 12/06/2023 | 1 | 1590 | inf | inf | 95 | 41
3 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-II Part-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme | SM/08016 | TSM/007053 | Retrofitting |  |  |  | 25/01/2021 | 04/05/2021 | 30/11/2021 | 12/06/2023 | 1 | 1302 | inf | inf | 95 | 46
4 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | TSM/009161 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 14/12/2021 | 03/01/2023 | 31/12/2022 | 30/06/2023 | 4 | 3563 | inf | inf | 85 | 55
5 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | TSM/009143 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 14/12/2021 | 09/01/2023 | 24/12/2022 | 30/06/2023 | 6 | 4003 | inf | inf | 95 | 57
6 | Nadia Arsenic Division I | NADIA | Santipur | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | TSM/009160 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | 14/12/2021 | 10/01/2023 | 13/12/2022 | 30/06/2023 | 16 | 450 | inf | inf | 91 | 73
7 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | TSM/010369 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | 22/04/2022 | 13/01/2023 | 31/12/2023 | 30/06/2023 | 10 | 3400 | inf | inf | 92 | 34
8 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | TSM/009138 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 22/04/2022 | 13/01/2023 | 31/03/2023 | 30/06/2023 | 8 | 8441 | inf | inf | 95 | 37
9 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | TSM/010349 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | 22/04/2022 | 14/01/2023 | 31/12/2023 | 30/06/2023 | 3 | 3500 | inf | inf | 93 | 42
10 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | TSM/010371 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | 22/04/2022 | 14/01/2023 | 31/12/2023 | 30/06/2023 | 12 | 3660 | inf | inf | 91 | 39
11 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | TSM/010367 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | 22/04/2022 | 15/01/2023 | 31/12/2023 | 30/06/2023 | 7 | 2382 | inf | inf | 92 | 48
12 | Nadia Arsenic Division I | NADIA | Hanskhali | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | TSM/011006 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 27/07/2022 | 17/01/2023 | 27/04/2023 | 30/06/2023 | 6 | 900 | inf | inf | 86 | 30
13 | Nadia Arsenic Division I | NADIA | Hanskhali | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | TSM/011085 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 01/09/2022 | 18/01/2023 | 31/03/2024 | 13/10/2023 | 13 | 2000 | inf | inf | 98 | 12
14 | Nadia Arsenic Division I | NADIA | Santipur | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | TSM/011119 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 01/09/2022 | 19/01/2023 | 31/07/2024 | 20/03/2024 | 11 | 1830 | inf | inf | 99 | 18
15 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | TSM/011118 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | 01/09/2022 | 20/01/2023 | 30/06/2024 | 10/10/2023 | 22 | 1960 | inf | inf | 98 | 51
16 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | TSM/014935 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 18/11/2022 | 21/01/2023 | 18/05/2024 | 30/06/2023 | 5 | 501 | inf | inf | 89 | 1
17 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | TSM/015176 | New | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | 10/01/2023 | 21/01/2023 | 10/07/2024 | 30/06/2023 | 5 | 812 | inf | inf | 92 | 18
18 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Saguna Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15542 | TSM/019501 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 18/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | inf | 78 | 20
19 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15544 | TSM/019497 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 19/02/2023 | 16/08/2023 | 30/06/2023 | 2 | 0 | inf | nan | 80 | 0
20 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Gayeshpur Zone II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15545 | TSM/019620 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 19/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | inf | 75 | 17
21 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | TSM/019624 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 20/02/2023 | 31/07/2024 | 22/04/2024 | 7 | 0 | inf | inf | 97 | 31
22 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Nabla Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15547 | TSM/019629 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 20/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | inf | 66 | 12
23 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte.. | SM/15548 | TSM/019631 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 16/02/2023 | 21/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | nan | 67 | 0
24 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Beharia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15549 | TSM/019502 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 21/02/2023 | 16/08/2023 | 30/06/2023 | 2 | 0 | inf | inf | 78 | 27
25 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15550 | TSM/019625 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 22/02/2023 | 16/08/2023 | 30/06/2023 | 2 | 0 | inf | inf | 81 | 15
26 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15551 | TSM/019494 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 16/02/2023 | 22/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | nan | 78 | 0
27 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15552 | TSM/019500 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 16/02/2023 | 23/02/2023 | 16/08/2023 | 30/06/2023 | 1 | 0 | inf | nan | 72 | 0
28 | Nadia Arsenic Division I | NADIA | Santipur | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | TSM/019493 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | 16/02/2023 | 23/02/2023 | 16/08/2023 | 30/06/2023 | 3 | 0 | inf | nan | 80 | 0
29 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | TSM/018089 | New |  |  |  | 21/06/2023 | 26/06/2023 | 31/07/2024 | 20/03/2024 | 32 | 0 | inf | inf | 3 | 12
Total | [14 empty] | 185 | 42245 | 0 | 0 |  | NAN