## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Nadia Arsenic Division I | NADIA | Chakdah | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. | SM/11489 | TSM/011113 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-II | Junior Engineer-IV | 15/07/2022 | 16/01/2023 |  | 30/06/2023 | 5 | 4789 | inf | inf | 100 | 7
2 | Nadia Arsenic Division I | NADIA | Chakdah | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. | SM/11490 | TSM/011112 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-II | Junior Engineer-IV | 15/07/2022 | 17/01/2023 |  | 30/06/2023 | 4 | 5188 | inf | inf | 100 | 0
3 | Nadia Arsenic Division I | NADIA | Santipur | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | TSM/011145 | Augmentation | Nadia Arsenic Division I | Assistant Engineer-I | Junior Engineer-II | 01/09/2022 | 18/01/2023 |  | 30/06/2023 | 8 | 5498 | inf | inf | 100 | 8
4 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | TSM/014935 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 18/11/2022 | 21/01/2023 | 18/05/2024 | 30/06/2023 | 5 | 501 | inf | inf | 89 | 1
5 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | TSM/014920 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 11/01/2023 | 22/01/2023 | 11/01/2025 | 30/06/2023 | 6 | 1385 | inf | inf | 92 | 1
6 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | TSM/015030 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 16/01/2023 | 23/01/2023 | 16/01/2025 | 30/06/2023 | 3 | 5176 | inf | inf | 92 | 1
7 | Nadia Arsenic Division I | NADIA | Ranaghat - II | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | TSM/015322 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 16/01/2023 | 23/01/2023 | 16/01/2025 | 30/06/2023 | 4 | 3128 | inf | inf | 94 | 3
8 | Nadia Arsenic Division I | NADIA | Ranaghat - I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | TSM/014928 | New | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 20/01/2023 | 24/01/2023 | 20/01/2025 | 30/06/2023 | 5 | 5468 | inf | inf | 94 | 1
9 | Nadia Arsenic Division I | NADIA | Hanskhali | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone- II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15543 | TSM/019685 | Augmentation | Nadia Arsenic Division I | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | 16/02/2023 | 18/02/2023 | 30/11/2024 | 14/05/2024 | 2 | 0 | inf | inf | 95 | 1
Total | [14 empty] | 42 | 31133 | 0 | 0 |  | NAN