## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Durgapur W/S Division | PASCHIM BARDHAMAN |  | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. | SM/06638 | TSM/005391 | Support |  |  |  | 05/02/2020 |  |  | 10/11/2022 | 2 | 0 | inf | inf | 100 | 60
2 | Durgapur W/S Division | PASCHIM BARDHAMAN |  | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | TSM/007440 | School |  |  |  | 03/11/2021 |  |  | 10/11/2022 | 7 | 0 | inf | inf | 100 | 94
3 | Durgapur W/S Division | PASCHIM BARDHAMAN | Kanksa | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | TSM/009278 | New |  |  |  | 16/06/2022 | 01/07/2022 |  | 12/06/2023 | 2 | 112 | inf | inf | 100 | 54
Total | [14 empty] | 11 | 112 | 0 | 0 |  | NAN