## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Purulia Division | PURULIA | Bagmundi | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | TSM/005481 | New | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 04/11/2020 | 18/11/2020 | 31/05/2024 | 06/05/2024 | 31 | 2122 | inf | inf | 94 | 54
2 | Purulia Division | PURULIA |  | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission | SM/08682 | TSM/007271 | Support | RWS Purulia Sub-Division | Assistant Engineer |  | 19/08/2021 | 11/01/2022 | 31/05/2024 | 06/05/2024 | 7 | 0 | inf | inf | 85 | 84
3 | Purulia Division | PURULIA |  | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | TSM/005223 | Anganwadi | Purulia Sadar Sub-Division | Assistant Engineer |  | 03/09/2021 | 19/01/2022 | 31/08/2024 | 06/05/2024 | 27 | 1105 | inf | inf | 90 | 72
4 | Purulia Division | PURULIA |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purulia District. | SM/09027 | TSM/008138 | Support |  |  |  | 30/10/2021 | 16/11/2021 | 31/07/2024 | 06/05/2024 | 0 | 0 | inf | inf | 85 | 85
5 | Purulia Division | PURULIA |  | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) | SM/09028 | TSM/008046 | School | RWS Purulia Sub-Division | Assistant Engineer |  | 30/10/2021 | 20/01/2022 | 31/08/2024 | 06/05/2024 | 2 | 0 | inf | inf | 85 | 30
6 | Purulia Division | PURULIA | Purulia - II | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | TSM/008391 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 54 | 2888 | inf | inf | 79 | 49
7 | Purulia Division | PURULIA | Purulia - II | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | SM/09037 | TSM/008388 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 40 | 2031 | inf | inf | 71 | 51
8 | Purulia Division | PURULIA | Arsha | Augmentation of Satra Water Supply Scheme | SM/09038 | TSM/008387 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 33 | 3823 | inf | inf | 70 | 63
9 | Purulia Division | PURULIA | Barabazar | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | SM/09209 | TSM/008431 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 32 | 2359 | inf | inf | 78 | 56
10 | Purulia Division | PURULIA | Kashipur | Augmentation of Sonathali W/S Scheme | SM/09210 | TSM/008397 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 24 | 1218 | inf | inf | 67 | 48
11 | Purulia Division | PURULIA | Neturia | Augmentation of Bathanbari W/S Scheme | SM/09211 | TSM/008398 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 26 | 988 | inf | inf | 50 | 80
12 | Purulia Division | PURULIA | Raghunathpur - II | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | TSM/008395 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 20 | 768 | inf | inf | 60 | 54
13 | Purulia Division | PURULIA | Arsha | Augmentation of Baram Water Supply Scheme | SM/09213 | TSM/008385 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 31/05/2024 | 06/05/2024 | 26 | 1241 | inf | inf | 52 | 60
14 | Purulia Division | PURULIA | Bagmundi | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | TSM/008392 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 31/07/2024 | 06/05/2024 | 31 | 2135 | inf | inf | 74 | 69
15 | Purulia Division | PURULIA | Jhalda - II | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | SM/09216 | TSM/008390 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 29 | 1140 | inf | inf | 64 | 59
16 | Purulia Division | PURULIA | Bagmundi | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | TSM/008389 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 30 | 271 | inf | inf | 66 | 65
17 | Purulia Division | PURULIA | Arsha | Augmentation of Beldi Water Supply Scheme | SM/09218 | TSM/008386 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 30/10/2021 | 18/11/2021 | 30/06/2024 | 06/05/2024 | 12 | 1849 | inf | inf | 54 | 58
18 | Purulia Division | PURULIA | Jhalda - II | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | SM/09577 | TSM/009010 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 22/11/2021 | 02/12/2021 | 30/06/2024 | 06/05/2024 | 38 | 3531 | inf | inf | 81 | 68
19 | Purulia Division | PURULIA | Arsha | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | TSM/008379 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 22/11/2021 | 08/12/2021 | 30/06/2024 | 06/05/2024 | 37 | 4309 | inf | inf | 79 | 61
20 | Purulia Division | PURULIA | Kashipur | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | TSM/009009 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 22/11/2021 | 09/12/2021 | 30/06/2024 | 06/05/2024 | 35 | 1450 | inf | inf | 61 | 72
21 | Purulia Division | PURULIA | Kashipur | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | TSM/009008 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 22/11/2021 | 13/12/2021 | 30/06/2024 | 06/05/2024 | 50 | 860 | inf | inf | 60 | 61
22 | Purulia Division | PURULIA | Hura | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | TSM/009005 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 22/11/2021 | 07/12/2021 | 30/06/2024 | 06/05/2024 | 46 | 81 | inf | inf | 65 | 81
23 | Purulia Division | PURULIA | Kashipur | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | TSM/009002 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 22/11/2021 | 08/12/2021 | 30/06/2024 | 06/05/2024 | 24 | 237 | inf | inf | 52 | 68
24 | Purulia Division | PURULIA | Neturia | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | TSM/009000 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 22/11/2021 | 09/12/2021 | 30/06/2024 | 06/05/2024 | 19 | 1857 | inf | inf | 41 | 51
25 | Purulia Division | PURULIA | Hura | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | TSM/008396 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 14/12/2021 | 24/12/2021 | 30/06/2024 | 06/05/2024 | 32 | 800 | inf | inf | 70 | 74
26 | Purulia Division | PURULIA | Santuri | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | TSM/008462 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 24/01/2022 | 10/02/2022 | 30/06/2024 | 06/05/2024 | 37 | 47 | inf | inf | 84 | 63
27 | Purulia Division | PURULIA | Balarampur | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | TSM/008456 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 24/01/2022 | 11/02/2022 | 31/08/2024 | 06/05/2024 | 54 | 13173 | inf | inf | 85 | 37
28 | Purulia Division | PURULIA | Kashipur | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | TSM/008394 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | 24/01/2022 | 09/02/2022 | 31/07/2024 | 06/05/2024 | 34 | 4032 | inf | inf | 87 | 58
29 | Purulia Division | PURULIA | Puncha | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | TSM/008384 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 24/01/2022 | 10/02/2022 | 31/01/2024 | 06/05/2024 | 46 | 4501 | inf | inf | 87 | 54
30 | Purulia Division | PURULIA | Bundwan | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | TSM/009014 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 22/02/2022 | 02/03/2022 | 30/09/2024 | 31/07/2024 | 52 | 4421 | inf | inf | 94 | 52
31 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | TSM/009805 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 6 | 0 | inf | inf | 96 | 62
32 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | TSM/009804 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 11 | 0 | inf | inf | 92 | 66
33 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | TSM/009806 | School | Raghunathpur Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 10 | 0 | inf | inf | 92 | 93
34 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | TSM/009810 | School | Raghunathpur Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 9 | 0 | inf | inf | 92 | 75
35 | Purulia Division | PURULIA |  | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | TSM/009746 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 6 | 0 | inf | inf | 92 | 60
36 | Purulia Division | PURULIA |  | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | TSM/009743 | School | Raghunathpur Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 13 | 0 | inf | inf | 92 | 91
37 | Purulia Division | PURULIA |  | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | TSM/009744 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 7 | 0 | inf | inf | 92 | 98
38 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | TSM/009803 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 6 | 0 | inf | inf | 95 | 71
39 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | TSM/009812 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 10 | 0 | inf | inf | 94 | 94
40 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | TSM/009797 | Anganwadi | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 03/07/2024 | 16 | 0 | inf | inf | 97 | 50
41 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | TSM/009800 | Anganwadi | Raghunathpur Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 23 | 0 | inf | inf | 97 | 33
42 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | TSM/009801 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 28 | 0 | inf | inf | 90 | 66
43 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | TSM/009782 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 17 | 0 | inf | inf | 91 | 69
44 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | TSM/009787 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 21 | 0 | inf | inf | 91 | 94
45 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | TSM/009795 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 23 | 0 | inf | inf | 88 | 65
46 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | TSM/009791 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 24 | 0 | inf | inf | 90 | 86
47 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | TSM/009811 | School | Purulia Sadar Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 6 | 0 | inf | inf | 91 | 94
48 | Purulia Division | PURULIA |  | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. | SM/10257 | TSM/008880 | School | RWS Purulia Sub-Division | Assistant Engineer |  | 24/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 7 | 0 | inf | inf | 88 | 21
49 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | TSM/009799 | Anganwadi | Raghunathpur Sub-Division | Assistant Engineer |  | 25/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 13 | 0 | inf | inf | 89 | 74
50 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | TSM/009789 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 16/06/2022 | 31/07/2024 | 06/05/2024 | 33 | 0 | inf | inf | 89 | 48
51 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | TSM/009790 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 07/03/2022 | 31/07/2024 | 06/05/2024 | 35 | 0 | inf | inf | 89 | 98
52 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | TSM/009792 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 16/06/2022 | 31/07/2024 | 06/05/2024 | 16 | 0 | inf | inf | 89 | 97
53 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | TSM/009794 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 9 | 0 | inf | inf | 87 | 32
54 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | TSM/009793 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 16 | 0 | inf | inf | 91 | 86
55 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | TSM/009796 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 28 | 0 | inf | inf | 90 | 83
56 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | TSM/009783 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 15 | 0 | inf | inf | 90 | 74
57 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | TSM/009785 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 45 | 0 | inf | inf | 91 | 86
58 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | TSM/009786 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 22 | 0 | inf | inf | 92 | 92
59 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | TSM/009784 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 7 | 0 | inf | inf | 90 | 16
60 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | TSM/009798 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 38 | 0 | inf | inf | 91 | 47
61 | Purulia Division | PURULIA |  | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | TSM/009788 | Anganwadi | RWS Purulia Sub-Division | Assistant Engineer |  | 25/02/2022 | 08/03/2022 | 31/07/2024 | 06/05/2024 | 20 | 0 | inf | inf | 92 | 98
62 | Purulia Division | PURULIA | Purulia - I | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | SM/10347 | TSM/008455 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 16/03/2022 | 01/04/2022 | 31/07/2024 | 06/05/2024 | 24 | 3104 | inf | inf | 68 | 37
63 | Purulia Division | PURULIA | Purulia - II | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | TSM/008461 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 29/03/2022 | 14/04/2022 | 31/08/2024 | 06/05/2024 | 52 | 5991 | inf | inf | 75 | 19
64 | Purulia Division | PURULIA | Arsha | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | TSM/010923 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 18/04/2022 | 29/04/2022 | 31/07/2024 | 06/05/2024 | 13 | 0 | inf | inf | 95 | 26
65 | Purulia Division | PURULIA | Para | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | TSM/009015 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | 18/05/2022 | 27/05/2022 | 31/07/2024 | 06/05/2024 | 38 | 6702 | inf | inf | 82 | 60
66 | Purulia Division | PURULIA | Manbazar - I | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | TSM/009013 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 18/05/2022 | 30/05/2022 | 31/08/2024 | 06/05/2024 | 35 | 5016 | inf | inf | 71 | 44
67 | Purulia Division | PURULIA | Neturia | Sarbari Piped Water Supply Scheme to Accommodate FHTC | SM/10720 | TSM/009012 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 18/05/2022 | 26/05/2022 | 31/08/2024 | 06/05/2024 | 35 | 3650 | inf | inf | 79 | 43
68 | Purulia Division | PURULIA | Neturia | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | TSM/009011 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 18/05/2022 | 25/05/2022 | 31/07/2024 | 06/05/2024 | 33 | 3676 | inf | inf | 80 | 48
69 | Purulia Division | PURULIA | Jaipur | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | TSM/009004 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 18/05/2022 | 27/05/2022 | 31/08/2024 | 06/05/2024 | 67 | 7881 | inf | inf | 77 | 39
70 | Purulia Division | PURULIA | Jhalda - II | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | TSM/009003 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 18/05/2022 | 26/05/2022 | 31/08/2024 | 06/05/2024 | 74 | 8268 | inf | inf | 84 | 64
71 | Purulia Division | PURULIA | Kashipur | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | TSM/008399 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | 12/07/2022 | 27/07/2022 | 31/08/2024 | 06/05/2024 | 47 | 6896 | inf | inf | 75 | 42
72 | Purulia Division | PURULIA | Raghunathpur - I | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | TSM/016037 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 05/12/2022 | 14/12/2022 | 31/10/2024 | 06/05/2024 | 19 | 3031 | inf | inf | 71 | 38
73 | Purulia Division | PURULIA | Raghunathpur - II | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | TSM/016038 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 05/12/2022 | 13/12/2022 | 31/10/2024 | 06/05/2024 | 13 | 2868 | inf | inf | 75 | 39
74 | Purulia Division | PURULIA |  | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | TSM/017570 | Support | RWS Purulia Sub-Division | Assistant Engineer |  | 02/01/2023 | 09/02/2023 | 31/08/2024 | 06/05/2024 | 40 | 0 | inf | inf | 55 | 93
75 | Purulia Division | PURULIA | Manbazar - I | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/14251 | TSM/013873 | New | Purulia Division | Assistant Engineer(HQ) |  | 20/01/2023 | 22/02/2023 | 31/03/2024 | 26/07/2023 | 1 | 22 | inf | inf | 1 | 15
76 | Purulia Division | PURULIA | Santuri | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | TSM/016080 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | 20/01/2023 | 01/04/2023 | 31/08/2024 | 06/05/2024 | 16 | 658 | inf | inf | 71 | 43
77 | Purulia Division | PURULIA | Para | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | TSM/016045 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | 20/01/2023 | 20/04/2023 | 31/10/2024 | 06/05/2024 | 16 | 2424 | inf | inf | 57 | 58
78 | Purulia Division | PURULIA | Raghunathpur - I | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | TSM/016035 | Augmentation | Purulia Division | Assistant Engineer(HQ) |  | 31/01/2023 | 22/02/2023 | 31/10/2024 | 06/05/2024 | 13 | 0 | inf | inf | 66 | 22
79 | Purulia Division | PURULIA | Raghunathpur - II | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | TSM/016039 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 31/01/2023 | 22/02/2023 | 31/10/2024 | 06/05/2024 | 14 | 3183 | inf | inf | 68 | 36
80 | Purulia Division | PURULIA | Santuri | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | TSM/019808 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 04/02/2023 | 22/02/2023 | 31/08/2024 | 06/05/2024 | 8 | 0 | inf | inf | 8 | 22
81 | Purulia Division | PURULIA | Bagmundi | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | TSM/019807 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 04/02/2023 | 20/02/2023 | 31/10/2024 | 06/05/2024 | 9 | 0 | inf | inf | 9 | 23
82 | Purulia Division | PURULIA | Purulia - II | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | SM/15336 | TSM/019806 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 09/02/2023 | 22/02/2023 | 31/10/2024 | 03/09/2024 | 5 | 0 | inf | inf | 8 | 11
83 | Purulia Division | PURULIA | Bagmundi | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/15380 | TSM/013606 | New | Purulia Division | Assistant Engineer(HQ) |  | 07/02/2023 | 22/02/2023 | 31/03/2024 | 26/07/2023 | 1 | 44 | inf | inf | 1 | 11
84 | Purulia Division | PURULIA | Manbazar - II | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | TSM/010889 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 22/02/2023 | 03/04/2023 | 31/08/2024 | 06/05/2024 | 15 | 3421 | inf | inf | 85 | 49
85 | Purulia Division | PURULIA | Jaipur | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/16091 | TSM/013718 | New | Purulia Division | Assistant Engineer(HQ) |  | 22/02/2023 | 27/02/2023 | 31/03/2024 | 26/07/2023 | 1 | 97 | inf | inf | 2 | 8
86 | Purulia Division | PURULIA | Arsha | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/16570 | TSM/013556 | New | Purulia Division | Assistant Engineer(HQ) |  | 09/03/2023 | 15/03/2023 | 31/03/2024 | 26/07/2023 | 1 | 50 | inf | inf | 1 | 8
87 | Purulia Division | PURULIA | Raghunathpur - II | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | TSM/016036 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 16/06/2023 | 03/07/2023 | 31/10/2024 | 06/05/2024 | 9 | 3798 | inf | inf | 54 | 12
88 | Purulia Division | PURULIA | Raghunathpur - I | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | TSM/012987 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 09/10/2023 | 10/10/2023 | 31/10/2024 | 06/06/2024 | 23 | 0 | inf | inf | 23 | 8
Total | [14 empty] | 2090 | 134017 | 0 | 0 |  | NAN