## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Hooghly Division | HOOGHLY |  | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | TSM/005378 | Support | Hooghly Division | Assistant Engineer(HQ) |  | 05/02/2020 |  |  | 31/05/2021 | 0 | 0 | inf | nan | 0 | 0
2 | Hooghly Division | HOOGHLY | Polba - Dadpur | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | TSM/007131 | Retrofitting |  |  |  | 21/01/2021 | 03/02/2021 |  | 12/06/2023 | 0 | 2559 | inf | nan | 100 | 0
3 | Hooghly Division | HOOGHLY | Polba - Dadpur | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | TSM/007139 | Retrofitting |  |  |  | 21/01/2021 | 06/05/2021 |  | 12/06/2023 | 0 | 3320 | inf | nan | 100 | 0
4 | Hooghly Division | HOOGHLY |  | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/08967 | TSM/008128 | Support | Hooghly Division | Assistant Engineer(HQ) |  | 28/10/2021 |  |  | 29/10/2021 | 0 | 0 | inf | nan | 0 | 0
5 | Hooghly Division | HOOGHLY |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Hooghly District. | SM/08974 | TSM/008145 | Support |  |  |  | 29/10/2021 |  |  | 31/10/2021 | 0 | 0 | inf | nan | 0 | 0
6 | Hooghly Division | HOOGHLY |  | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | TSM/006351 | Disaster | Hooghly Division | Assistant Engineer(HQ) |  | 30/10/2021 |  |  | 02/11/2021 | 0 | 0 | inf | nan | 0 | 0
7 | Hooghly Division | HOOGHLY |  | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. | SM/11989 | TSM/012046 | Support |  |  |  | 01/09/2022 |  |  | 05/09/2022 | 0 | 0 | inf | nan | 0 | 0
8 | Hooghly Division | HOOGHLY |  | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | TSM/012044 | Support |  |  |  | 01/09/2022 | 11/10/2023 |  | 05/09/2022 | 0 | 0 | inf | nan | 0 | 0
9 | Hooghly Division | HOOGHLY |  | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte | SM/18130 | TSM/020470 | Support | Chinsuria Sub-Division | Assistant Engineer (Civil) |  | 29/03/2023 | 23/08/2023 |  | 31/03/2023 | 0 | 0 | inf | nan | 0 | 0
10 | Hooghly Division | HOOGHLY |  | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | SM/18131 | TSM/020471 | Support | Hooghly Division | Assistant Engineer(HQ) |  | 29/03/2023 |  |  | 31/03/2023 | 0 | 0 | inf | nan | 0 | 0
11 | Hooghly Division | HOOGHLY |  | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | TSM/021975 | Support |  |  |  | 05/12/2023 | 19/02/2024 |  | 05/12/2023 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 0 | 5879 | 0 | 0 |  | NAN