## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Burdwan Division | PURBA BARDHAMAN | Kalna - I | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | TSM/006611 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 31/12/2020 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 11 | 1555 | inf | inf | 80 | 68
2 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | TSM/006597 | Retrofitting | Burdwan Division | AE(HQs) |  | 31/12/2020 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 7 | 1744 | inf | inf | 75 | 30
3 | Burdwan Division | PURBA BARDHAMAN | Manteswar | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | TSM/006657 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 31/12/2020 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 8 | 1153 | inf | inf | 75 | 53
4 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | TSM/006599 | Retrofitting | Burdwan Division | AE(HQs),Assistant Engineer |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 13 | 2550 | inf | inf | 75 | 45
5 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | TSM/006602 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 7 | 2615 | inf | inf | 65 | 29
6 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | TSM/006591 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 8 | 2118 | inf | inf | 60 | 71
7 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | TSM/006671 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 14 | 5098 | inf | inf | 70 | 44
8 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | SM/07799 | TSM/006601 | Retrofitting | Burdwan Division | AE(HQs) |  | 07/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 2 | 1431 | inf | inf | 95 | 25
9 | Burdwan Division | PURBA BARDHAMAN | Mangolkote | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | TSM/006622 | Retrofitting | Katwa Sub-division | Assistant Engineer |  | 07/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 5 | 1910 | inf | inf | 80 | 22
10 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | TSM/006607 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 18 | 2942 | inf | inf | 80 | 52
11 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | TSM/006594 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 9 | 4050 | inf | inf | 70 | 41
12 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | TSM/006596 | Retrofitting | Burdwan Division | AE(HQs) |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 17 | 2307 | inf | inf | 80 | 79
13 | Burdwan Division | PURBA BARDHAMAN | Memari - I | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | SM/07819 | TSM/006647 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 3 | 3993 | inf | inf | 80 | 7
14 | Burdwan Division | PURBA BARDHAMAN | Raina - II | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | TSM/006627 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 12 | 2176 | inf | inf | 80 | 68
15 | Burdwan Division | PURBA BARDHAMAN | Memari - I | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | TSM/006625 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 7 | 1654 | inf | inf | 80 | 55
16 | Burdwan Division | PURBA BARDHAMAN | Burdwan - II | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | TSM/006626 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 15 | 2579 | inf | inf | 75 | 36
17 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - II | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | TSM/006664 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 03/10/2023 | 2 | 1969 | inf | inf | 90 | 75
18 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | TSM/006687 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 08/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 12 | 3257 | inf | inf | 70 | 51
19 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | TSM/006608 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 17 | 2730 | inf | inf | 80 | 59
20 | Burdwan Division | PURBA BARDHAMAN | Burdwan - I | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | TSM/006641 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 7 | 1853 | inf | inf | 80 | 13
21 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | TSM/006629 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 15 | 3926 | inf | inf | 80 | 63
22 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | TSM/006623 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 22 | 2107 | inf | inf | 80 | 71
23 | Burdwan Division | PURBA BARDHAMAN | Burdwan - I | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | TSM/006643 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 10 | 2164 | inf | inf | 55 | 49
24 | Burdwan Division | PURBA BARDHAMAN | Burdwan - II | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | TSM/006652 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 13 | 2535 | inf | inf | 80 | 84
25 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | TSM/006689 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 15 | 3050 | inf | inf | 50 | 18
26 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | TSM/006700 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 14/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 15 | 3125 | inf | inf | 59 | 20
27 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - II | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | TSM/006592 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 25/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 21 | 34987 | inf | inf | 45 | 77
28 | Burdwan Division | PURBA BARDHAMAN | Memari - I | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme | SM/08031 | TSM/006628 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 25/01/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 8 | 5077 | inf | inf | 30 | 60
29 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | TSM/006696 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 25/01/2021 | 08/02/2022 | 30/09/2024 | 18/04/2024 | 30 | 6580 | inf | inf | 70 | 32
30 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | TSM/006604 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 19/02/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 7 | 6182 | inf | inf | 55 | 37
31 | Burdwan Division | PURBA BARDHAMAN | Burdwan - I | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | TSM/006645 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 9 | 8834 | inf | inf | 60 | 38
32 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | TSM/006655 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 19/02/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 8 | 5112 | inf | inf | 60 | 52
33 | Burdwan Division | PURBA BARDHAMAN | Kalna - I | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | TSM/006656 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 19/02/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 13 | 5704 | inf | inf | 60 | 46
34 | Burdwan Division | PURBA BARDHAMAN | Bhatar | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | TSM/006669 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/02/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 17 | 5098 | inf | inf | 40 | 45
35 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | TSM/007681 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 03/09/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 13 | 5237 | inf | inf | 70 | 17
36 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | TSM/007680 | Retrofitting | Burdwan Division | AE(HQs) | JE/RWS/JAMALPUR | 03/09/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 26 | 3098 | inf | inf | 75 | 35
37 | Burdwan Division | PURBA BARDHAMAN | Memari - I | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | TSM/007676 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 03/09/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 11 | 4909 | inf | inf | 75 | 43
38 | Burdwan Division | PURBA BARDHAMAN | Kalna - I | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio | SM/08712 | TSM/007672 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 03/09/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 6 | 2643 | inf | inf | 90 | 56
39 | Burdwan Division | PURBA BARDHAMAN | Burdwan - II | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | TSM/007682 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 03/09/2021 | 08/02/2022 | 30/04/2024 | 29/02/2024 | 11 | 2879 | inf | inf | 80 | 51
40 | Burdwan Division | PURBA BARDHAMAN | Memari - II | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | TSM/008574 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 29/10/2021 | 08/02/2022 | 30/04/2024 | 13/03/2024 | 9 | 2744 | inf | inf | 99 | 79
41 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | TSM/008315 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 28/10/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 20 | 4335 | inf | inf | 60 | 29
42 | Burdwan Division | PURBA BARDHAMAN | Kalna - II | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | TSM/008580 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 17/11/2021 | 08/02/2022 | 31/12/2023 | 12/06/2023 | 12 | 657 | inf | inf | 40 | 53
43 | Burdwan Division | PURBA BARDHAMAN | Raina - I | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | TSM/008525 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 17/11/2021 | 08/02/2022 | 30/09/2024 | 13/03/2024 | 10 | 2829 | inf | inf | 65 | 76
44 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | TSM/008524 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 17/11/2021 | 08/02/2022 | 30/06/2024 | 13/03/2024 | 13 | 3783 | inf | inf | 80 | 60
45 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | TSM/008073 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 17/11/2021 | 08/02/2022 | 31/10/2024 | 13/03/2024 | 20 | 2940 | inf | inf | 65 | 59
46 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | TSM/008530 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 17/11/2021 | 08/02/2022 | 31/05/2024 | 13/03/2024 | 13 | 1935 | inf | inf | 85 | 53
47 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | TSM/008753 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 19/11/2021 | 08/02/2022 | 30/06/2024 | 13/03/2024 | 9 | 3020 | inf | inf | 95 | 80
48 | Burdwan Division | PURBA BARDHAMAN | Raina - I | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09493 | TSM/008751 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 19/11/2021 | 03/03/2022 | 31/08/2024 | 13/03/2024 | 12 | 2087 | inf | inf | 80 | 75
49 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - II | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | TSM/008170 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 26/11/2021 | 03/04/2023 | 31/03/2024 | 13/03/2024 | 19 | 2772 | inf | inf | 98 | 6
50 | Burdwan Division | PURBA BARDHAMAN | Manteswar | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | TSM/008336 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 26/11/2021 | 08/02/2022 | 31/05/2024 | 13/03/2024 | 15 | 1762 | inf | inf | 90 | 48
51 | Burdwan Division | PURBA BARDHAMAN |  | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | TSM/005355 | Anganwadi | Burdwan Sadar Sub-Division | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 30/12/2021 | 08/02/2022 | 31/03/2024 | 29/02/2024 | 21 | 0 | inf | inf | 80 | 65
52 | Burdwan Division | PURBA BARDHAMAN | Kalna - II | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | TSM/008767 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 19/01/2022 | 08/02/2022 | 30/09/2024 | 15/07/2024 | 19 | 5865 | inf | inf | 77 | 72
53 | Burdwan Division | PURBA BARDHAMAN | Kalna - I | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | TSM/009133 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 25/02/2022 | 28/02/2022 | 30/11/2024 | 19/06/2024 | 18 | 6540 | inf | inf | 57 | 67
54 | Burdwan Division | PURBA BARDHAMAN |  | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | TSM/009900 | School | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 23/03/2022 | 05/12/2022 | 31/03/2024 | 10/08/2023 | 26 | 0 | inf | inf | 50 | 41
55 | Burdwan Division | PURBA BARDHAMAN | Bhatar | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | TSM/010056 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 24/03/2022 | 30/03/2022 | 31/03/2024 | 03/10/2023 | 11 | 4079 | inf | inf | 39 | 55
56 | Burdwan Division | PURBA BARDHAMAN |  | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | TSM/009908 | School | Kalna Sub-division | Assistant Engineer |  | 28/06/2022 | 01/03/2023 | 31/03/2024 | 09/08/2023 | 8 | 0 | inf | inf | 20 | 36
57 | Burdwan Division | PURBA BARDHAMAN |  | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | TSM/009906 | School | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 28/06/2022 | 01/09/2022 | 31/03/2023 | 05/05/2023 | 8 | 0 | inf | inf | 0 | 27
58 | Burdwan Division | PURBA BARDHAMAN |  | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | TSM/009902 | School | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/06/2022 | 01/09/2022 | 31/03/2023 | 05/05/2023 | 13 | 0 | inf | inf | 0 | 60
59 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | TSM/010910 | New | Burdwan Division | AE(HQs),ASSISTANT ENGINEER | JUNIOR ENGINEER | 19/07/2022 | 08/09/2022 | 31/03/2024 | 21/02/2024 | 15 | 1442 | inf | inf | 90 | 52
60 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | TSM/010918 | New | Burdwan Division | AE(HQs),ASSISTANT ENGINEER | JUNIOR ENGINEER | 19/07/2022 | 05/08/2022 | 31/03/2024 | 21/02/2024 | 24 | 2015 | inf | inf | 77 | 44
61 | Burdwan Division | PURBA BARDHAMAN |  | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | TSM/009909 | School | Katwa Sub-division | Assistant Engineer |  | 19/07/2022 | 15/11/2022 | 31/05/2023 | 05/05/2023 | 10 | 0 | inf | inf | 0 | 59
62 | Burdwan Division | PURBA BARDHAMAN | Mangolkote | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | TSM/013345 | Retrofitting | Katwa Sub-division | Assistant Engineer |  | 02/09/2022 |  | 02/12/2022 | 12/06/2023 | 6 | 414 | inf | inf | 80 | 64
63 | Burdwan Division | PURBA BARDHAMAN | Katwa - I | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | TSM/014286 | Retrofitting | Katwa Sub-division | Assistant Engineer |  | 02/09/2022 | 15/12/2022 | 31/03/2024 | 29/02/2024 | 5 | 1250 | inf | inf | 50 | 65
64 | Burdwan Division | PURBA BARDHAMAN | Manteswar | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | TSM/015238 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 17/10/2022 | 15/03/2023 | 31/03/2024 | 24/11/2023 | 11 | 1672 | inf | inf | 56 | 52
65 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | TSM/015829 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 17/10/2022 | 23/03/2023 | 31/05/2024 | 13/03/2024 | 9 | 543 | inf | inf | 71 | 40
66 | Burdwan Division | PURBA BARDHAMAN | Burdwan - II | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | TSM/015313 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 17/10/2022 | 30/01/2023 | 31/07/2024 | 13/03/2024 | 11 | 1011 | inf | inf | 90 | 49
67 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | TSM/015846 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 02/11/2022 | 06/04/2023 | 30/06/2024 | 13/03/2024 | 8 | 1316 | inf | inf | 77 | 40
68 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | TSM/015779 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 02/11/2022 | 17/01/2023 | 31/03/2024 | 27/09/2023 | 9 | 382 | inf | inf | 78 | 40
69 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | TSM/015781 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 02/11/2022 | 14/04/2023 | 31/03/2024 | 21/02/2024 | 10 | 2435 | inf | inf | 71 | 35
70 | Burdwan Division | PURBA BARDHAMAN | Memari - I | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | TSM/015784 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 02/11/2022 | 10/01/2023 | 31/03/2024 | 13/03/2024 | 9 | 1188 | inf | inf | 88 | 47
71 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | TSM/015796 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 02/11/2022 | 12/01/2023 | 31/03/2024 | 21/02/2024 | 12 | 800 | inf | inf | 61 | 34
72 | Burdwan Division | PURBA BARDHAMAN | Memari - II | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | TSM/015812 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 02/11/2022 | 15/03/2023 | 31/07/2024 | 13/03/2024 | 9 | 1938 | inf | inf | 74 | 3
73 | Burdwan Division | PURBA BARDHAMAN | Memari - II | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | TSM/015770 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 02/11/2022 | 15/03/2023 | 30/04/2024 | 13/03/2024 | 15 | 2306 | inf | inf | 88 | 36
74 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | TSM/015772 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 02/11/2022 | 17/03/2023 | 30/07/2024 | 13/03/2024 | 11 | 2692 | inf | inf | 74 | 33
75 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - I | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | TSM/015833 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 02/11/2022 | 29/03/2023 | 30/04/2024 | 13/03/2024 | 10 | 182 | inf | inf | 69 | 32
76 | Burdwan Division | PURBA BARDHAMAN | Raina - II | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | TSM/015302 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 02/11/2022 | 11/05/2023 | 30/06/2024 | 13/03/2024 | 8 | 320 | inf | inf | 65 | 28
77 | Burdwan Division | PURBA BARDHAMAN | Bhatar | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | TSM/016551 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 29/11/2022 | 25/03/2023 | 22/08/2024 | 15/07/2024 | 11 | 319 | inf | inf | 57 | 25
78 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | TSM/016296 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 01/12/2022 | 04/05/2023 | 31/03/2024 | 21/02/2024 | 8 | 1984 | inf | inf | 51 | 31
79 | Burdwan Division | PURBA BARDHAMAN | Bhatar | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | TSM/016257 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 04/02/2023 | 25/08/2023 | 04/08/2024 | 15/07/2024 | 10 | 1666 | inf | inf | 4 | 2
80 | Burdwan Division | PURBA BARDHAMAN | Raina - I | MACHKHARA PIPED WATER SUPPLY SCHEME | SM/14967 | TSM/017645 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 04/02/2023 | 06/10/2023 | 04/08/2024 | 16/01/2024 | 8 | 1661 | inf | inf | 10 | 1
81 | Burdwan Division | PURBA BARDHAMAN | Raina - I | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | TSM/017623 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 04/02/2023 | 06/10/2023 | 04/08/2024 | 28/12/2023 | 9 | 1708 | inf | inf | 2 | 1
82 | Burdwan Division | PURBA BARDHAMAN | Mangolkote | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | TSM/017646 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 08/02/2023 | 05/10/2023 | 08/08/2024 | 04/03/2024 | 9 | 3022 | inf | inf | 3 | 2
83 | Burdwan Division | PURBA BARDHAMAN | Raina - I | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | TSM/019279 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 07/02/2023 | 29/08/2023 | 07/08/2023 | 12/06/2023 | 2 | 0 | inf | nan | 0 | 0
84 | Burdwan Division | PURBA BARDHAMAN | Memari - II | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | TSM/019265 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 07/02/2023 | 18/08/2023 | 31/10/2024 | 13/03/2024 | 4 | 0 | inf | inf | 77 | 1
85 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | TSM/019252 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | 07/02/2023 | 17/05/2023 | 31/03/2024 | 17/07/2023 | 9 | 544 | inf | inf | 17 | 22
86 | Burdwan Division | PURBA BARDHAMAN | Memari - II | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | TSM/017601 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 16/02/2023 | 28/07/2023 | 01/07/2024 | 29/02/2024 | 4 | 444 | inf | inf | 5 | 13
87 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - II | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | TSM/018388 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 16/02/2023 | 17/11/2023 | 03/03/2024 | 29/02/2024 | 4 | 1000 | inf | nan | 2 | 0
88 | Burdwan Division | PURBA BARDHAMAN | Jamalpur | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | SM/15602 | TSM/019256 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 16/02/2023 | 01/03/2023 | 31/03/2024 | 14/07/2023 | 4 | 500 | inf | inf | 50 | 25
89 | Burdwan Division | PURBA BARDHAMAN | Raina - II | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA | SM/15718 | TSM/018150 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 20/02/2023 | 01/03/2023 | 30/06/2024 | 13/03/2024 | 1 | 140 | inf | nan | 27 | 0
90 | Burdwan Division | PURBA BARDHAMAN | Ketugram - II | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | TSM/018124 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 21/02/2023 | 24/03/2023 | 31/03/2024 | 12/03/2024 | 7 | 466 | inf | inf | 91 | 33
91 | Burdwan Division | PURBA BARDHAMAN | Kalna - II | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | TSM/017751 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 23/02/2023 | 25/08/2023 | 23/08/2024 | 09/01/2024 | 8 | 1996 | inf | inf | 3 | 1
92 | Burdwan Division | PURBA BARDHAMAN | Manteswar | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | TSM/019604 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 23/02/2023 | 01/06/2023 | 31/03/2024 | 24/11/2023 | 6 | 600 | inf | inf | 20 | 18
93 | Burdwan Division | PURBA BARDHAMAN | Purbasthali - II | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | TSM/020229 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 23/02/2023 | 12/10/2023 | 23/08/2023 | 12/06/2023 | 5 | 300 | inf | inf | 5 | 19
94 | Burdwan Division | PURBA BARDHAMAN | Mangolkote | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME | SM/16477 | TSM/017651 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 02/03/2023 | 05/10/2023 | 02/09/2024 | 04/03/2024 | 8 | 1812 | inf | inf | 3 | 2
95 | Burdwan Division | PURBA BARDHAMAN | Burdwan - I | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | TSM/018136 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 02/03/2023 | 07/06/2023 | 31/03/2024 | 12/06/2023 | 3 | 4085 | inf | inf | 5 | 1
96 | Burdwan Division | PURBA BARDHAMAN | Mangolkote | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | TSM/018139 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 02/03/2023 | 13/04/2023 | 03/10/2024 | 12/03/2024 | 5 | 2200 | inf | inf | 5 | 2
97 | Burdwan Division | PURBA BARDHAMAN | Raina - I | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | TSM/016909 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 14/03/2023 | 22/12/2023 | 14/09/2024 | 28/12/2023 | 8 | 1424 | inf | inf | 5 | 1
98 | Burdwan Division | PURBA BARDHAMAN | Khandaghosh | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | TSM/019268 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 13/03/2023 | 21/03/2023 | 31/07/2024 | 03/06/2024 | 14 | 0 | inf | inf | 10 | 21
99 | Burdwan Division | PURBA BARDHAMAN | Kalna - I | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | TSM/019289 | Augmentation |  |  |  | 18/07/2023 | 08/08/2023 | 18/07/2024 | 05/01/2024 | 6 | 9130 | inf | inf | 29 | 26
Total | [14 empty] | 1085 | 265186 | 0 | 0 |  | NAN