## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | TSM/005613 | Retrofitting |  |  |  | 18/09/2020 | 18/02/2021 | 31/10/2022 | 12/06/2023 | 5 | 777 | inf | inf | 90 | 84
2 | Birbhum Division | BIRBHUM | Suri - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | TSM/005602 | Retrofitting |  |  |  | 18/09/2020 | 21/09/2020 | 31/05/2021 | 12/06/2023 | 8 | 1860 | inf | inf | 92 | 89
3 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | TSM/005604 | Retrofitting |  |  |  | 18/09/2020 | 23/12/2020 | 31/12/2021 | 12/06/2023 | 9 | 1265 | inf | inf | 95 | 84
4 | Birbhum Division | BIRBHUM | Illambazar | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | TSM/006176 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 03/11/2020 | 11/04/2022 | 30/09/2023 | 10/09/2023 | 10 | 1500 | inf | inf | 99 | 25
5 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | SM/06946 | TSM/006172 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 03/11/2020 | 16/07/2021 | 31/05/2021 | 12/06/2023 | 3 | 1510 | inf | inf | 0 | 39
6 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | TSM/006175 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 ,JE_BLK_NANOOR | 03/11/2020 | 13/01/2021 | 30/09/2023 | 10/09/2023 | 12 | 1520 | inf | inf | 99 | 88
7 | Birbhum Division | BIRBHUM | Suri - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | TSM/005603 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE3 | 13/11/2020 | 04/08/2021 | 01/02/2024 | 30/06/2023 | 3 | 1393 | inf | inf | 85 | 95
8 | Birbhum Division | BIRBHUM | Rampurhat - I | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | TSM/006177 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 01/12/2020 | 23/12/2020 | 31/03/2024 | 27/09/2023 | 9 | 1408 | inf | inf | 96 | 76
9 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | TSM/006185 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 01/12/2020 | 16/08/2021 | 31/12/2023 | 20/07/2023 | 4 | 1510 | inf | inf | 80 | 84
10 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | TSM/006178 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE | 31/12/2020 | 25/01/2022 | 01/02/2024 | 30/06/2023 | 7 | 4984 | inf | inf | 80 | 81
11 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | TSM/006186 | Retrofitting | Birbhum Division | AE(HQ) | Estimator | 31/12/2020 | 09/02/2022 | 30/06/2023 | 30/06/2023 | 7 | 2702 | inf | inf | 85 | 48
12 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) | SM/07647 | TSM/006722 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 07/01/2021 | 16/07/2021 | 30/03/2024 | 20/07/2023 | 3 | 1050 | inf | inf | 90 | 4
13 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS | SM/07648 | TSM/006721 | Retrofitting | RWS Birbhum Sub-Division | AE |  | 07/01/2021 | 03/04/2022 | 12/06/2024 | 11/12/2023 | 7 | 1750 | inf | inf | 70 | 76
14 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | TSM/006724 | Retrofitting |  |  |  | 07/01/2021 | 15/06/2021 | 30/11/2022 | 12/06/2023 | 12 | 1760 | inf | inf | 90 | 84
15 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | TSM/007022 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 08/02/2021 | 15/06/2021 | 31/12/2023 | 27/09/2023 | 6 | 1525 | inf | inf | 95 | 35
16 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | TSM/007021 | Retrofitting |  |  |  | 08/02/2021 | 26/02/2021 | 31/10/2021 | 12/06/2023 | 12 | 1520 | inf | inf | 0 | 72
17 | Birbhum Division | BIRBHUM | Suri - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | TSM/006181 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE2 | 09/02/2021 | 09/11/2021 | 31/03/2023 | 12/06/2023 | 31 | 14748 | inf | inf | 90 | 92
18 | Birbhum Division | BIRBHUM | Labpur | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | TSM/008198 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 29/09/2021 | 30/08/2022 | 31/10/2023 | 04/09/2023 | 6 | 2882 | inf | inf | 28 | 14
19 | Birbhum Division | BIRBHUM | Sainthia | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. | SM/08894 | TSM/008201 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE3 | 29/09/2021 | 04/04/2022 | 10/02/2024 | 30/06/2023 | 5 | 2299 | inf | inf | 75 | 50
20 | Birbhum Division | BIRBHUM | Labpur | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | TSM/008202 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 29/09/2021 | 13/12/2021 | 30/09/2023 | 10/09/2023 | 4 | 1500 | inf | inf | 99 | 45
21 | Birbhum Division | BIRBHUM | Labpur | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | TSM/008208 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 ,JE4 | 29/09/2021 | 07/10/2021 | 31/01/2023 | 12/06/2023 | 4 | 1682 | inf | inf | 99 | 66
22 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | TSM/008210 | Retrofitting | Rampurhat Sub-Division | AE | JE2 | 29/09/2021 | 29/10/2021 | 31/12/2023 | 27/09/2023 | 5 | 2377 | inf | inf | 96 | 58
23 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | TSM/008573 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | 12/11/2021 | 22/04/2022 | 28/02/2023 | 12/06/2023 | 13 | 4002 | inf | inf | 90 | 53
24 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09363 | TSM/008572 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 28/07/2022 | 31/12/2023 | 27/09/2023 | 4 | 2910 | inf | inf | 60 | 28
25 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | TSM/008571 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 12/11/2021 | 19/09/2022 | 30/06/2024 | 04/01/2024 | 4 | 3622 | inf | inf | 74 | 48
26 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | TSM/008522 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 12/11/2021 | 13/04/2022 | 12/02/2024 | 23/11/2023 | 8 | 2805 | inf | inf | 77 | 62
27 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09367 | TSM/008520 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 18/08/2022 | 03/03/2024 | 27/09/2023 | 14 | 6979 | inf | inf | 90 | 40
28 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | TSM/008519 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 13/04/2022 | 30/09/2023 | 27/09/2023 | 6 | 1054 | inf | inf | 96 | 38
29 | Birbhum Division | BIRBHUM | Dubrajpur | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. | SM/09369 | TSM/008516 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE3 | 12/11/2021 | 07/07/2022 | 13/02/2024 | 30/06/2023 | 2 | 1199 | inf | inf | 70 | 32
30 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | TSM/008515 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 12/11/2021 | 15/09/2022 | 30/06/2024 | 04/01/2024 | 4 | 2238 | inf | inf | 88 | 68
31 | Birbhum Division | BIRBHUM | Suri - II | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | TSM/008567 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 12/11/2021 | 18/08/2022 | 08/02/2024 | 30/06/2023 | 13 | 3060 | inf | inf | 50 | 64
32 | Birbhum Division | BIRBHUM | Rajnagar | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | TSM/008501 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 29/10/2021 | 21/01/2022 | 31/03/2023 | 12/06/2023 | 30 | 3546 | inf | inf | 90 | 62
33 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. | SM/09490 | TSM/008521 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE2 | 19/11/2021 | 06/04/2023 | 19/02/2022 | 12/06/2023 | 2 | 4634 | inf | nan | 0 | 0
34 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | TSM/009066 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/11/2021 | 17/12/2021 | 15/02/2024 | 10/01/2024 | 4 | 2295 | inf | inf | 91 | 71
35 | Birbhum Division | BIRBHUM |  | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | TSM/005348 | Anganwadi | RWS Birbhum Sub-Division | AE | JE | 17/11/2021 | 23/04/2022 | 12/06/2024 | 11/12/2023 | 39 | 0 | inf | inf | 10 | 30
36 | Birbhum Division | BIRBHUM | Bolpur Sriniketan | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | TSM/008807 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | 30/11/2021 | 21/02/2022 | 10/02/2024 | 04/09/2023 | 46 | 12114 | inf | inf | 75 | 41
37 | Birbhum Division | BIRBHUM | Suri - I | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | TSM/009571 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 04/03/2022 | 11/01/2023 | 28/03/2024 | 11/10/2023 | 8 | 969 | inf | inf | 18 | 47
38 | Birbhum Division | BIRBHUM | Sainthia | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | TSM/009869 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 04/03/2022 | 23/05/2022 | 13/02/2024 | 30/06/2023 | 8 | 4884 | inf | inf | 46 | 56
39 | Birbhum Division | BIRBHUM | Dubrajpur | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | TSM/009572 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 04/03/2022 | 23/05/2022 | 31/03/2023 | 12/06/2023 | 14 | 4179 | inf | inf | 80 | 49
40 | Birbhum Division | BIRBHUM | Sainthia | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | TSM/009564 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE3,Junior Engineer | 04/03/2022 | 23/05/2022 | 12/02/2024 | 12/10/2023 | 8 | 1605 | inf | inf | 84 | 65
41 | Birbhum Division | BIRBHUM | Murarai - II | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | TSM/007453 | Augmentation | Nalhati Sub-Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | 07/03/2022 | 28/04/2022 | 30/06/2024 | 04/01/2024 | 164 | 56246 | inf | inf | 71 | 85
42 | Birbhum Division | BIRBHUM | Mohammad Bazar | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | TSM/007455 | Augmentation | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | 07/03/2022 | 11/05/2022 | 05/02/2024 | 28/05/2024 | 86 | 28764 | inf | inf | 69 | 50
43 | Birbhum Division | BIRBHUM | Khoyrasol | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | TSM/009739 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 14/03/2022 | 23/05/2022 | 03/02/2024 | 30/06/2023 | 13 | 783 | inf | inf | 85 | 65
44 | Birbhum Division | BIRBHUM | Suri - I | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | SM/10665 | TSM/010390 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE2 | 22/04/2022 | 17/11/2022 | 28/02/2023 | 12/06/2023 | 3 | 903 | inf | inf | 65 | 85
45 | Birbhum Division | BIRBHUM | Labpur | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12069 | TSM/010615 | New | RWS Birbhum Sub-Division | AE,Assistant Engineer (HQ) | JE,Junior Engineer | 02/09/2022 | 28/11/2022 | 02/03/2024 | 11/12/2023 | 1 | 570 | inf | nan | 8 | 0
46 | Birbhum Division | BIRBHUM | Sainthia | Meherpur and Adjoining Mouzas PWSS | SM/12457 | TSM/013178 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 13/09/2022 | 22/08/2023 | 31/07/2024 | 06/12/2023 | 4 | 1520 | inf | inf | 6 | 2
47 | Birbhum Division | BIRBHUM | Sainthia | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | TSM/013258 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 13/09/2022 | 12/07/2023 | 31/05/2024 | 18/01/2024 | 6 | 1347 | inf | inf | 13 | 35
48 | Birbhum Division | BIRBHUM | Murarai - II | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | TSM/013068 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE1,Junior Engineer | 15/09/2022 | 25/08/2023 | 31/07/2024 | 10/01/2024 | 6 | 3542 | inf | inf | 32 | 9
49 | Birbhum Division | BIRBHUM | Rajnagar | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) | SM/12637 | TSM/014500 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE | 19/09/2022 | 13/07/2023 | 31/07/2024 | 15/05/2024 | 1 | 530 | inf | inf | 5 | 29
50 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | TSM/014636 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 19/09/2022 | 28/02/2023 | 31/03/2024 | 28/05/2024 | 4 | 376 | inf | inf | 30 | 65
51 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme | SM/12658 | TSM/014584 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/09/2022 | 20/04/2023 | 15/02/2024 | 10/01/2024 | 0 | 211 | inf | nan | 90 | 0
52 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | TSM/014524 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 19/09/2022 | 03/08/2023 | 31/03/2024 | 28/05/2024 | 5 | 2304 | inf | inf | 50 | 14
53 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. | SM/12660 | TSM/014631 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 19/09/2022 | 19/04/2023 | 19/12/2022 | 12/06/2023 | 1 | 319 | inf | inf | 0 | 32
54 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. | SM/12661 | TSM/014641 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 19/09/2022 | 10/08/2023 | 31/03/2024 | 27/09/2023 | 1 | 700 | inf | nan | 30 | 0
55 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. | SM/12662 | TSM/014573 | Retrofitting | Rampurhat Sub-Division | AE | JE2 | 19/09/2022 | 03/10/2022 | 31/01/2024 | 25/01/2024 | 1 | 826 | inf | inf | 10 | 9
56 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme | SM/12664 | TSM/014561 | Retrofitting | Nalhati Sub-Division | AE | JE3 | 19/09/2022 | 14/12/2022 | 30/09/2023 | 26/07/2023 | 1 | 909 | inf | nan | 48 | 0
57 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Danghara (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12665 | TSM/014667 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 19/09/2022 | 01/05/2023 | 31/03/2024 | 04/01/2024 | 0 | 272 | inf | nan | 45 | 0
58 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12666 | TSM/014635 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/09/2022 | 18/04/2023 | 20/02/2024 | 10/01/2024 | 2 | 1404 | inf | inf | 56 | 19
59 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kurumgram (Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12668 | TSM/014743 | Retrofitting | Nalhati Sub-Division | AE | JE3 | 19/09/2022 |  | 19/12/2022 | 12/06/2023 | 0 | 179 | inf | nan | 0 | 0
60 | Birbhum Division | BIRBHUM | Sainthia | Deoash and Adjoining Mouzas PWSS | SM/12670 | TSM/013165 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 19/09/2022 | 12/04/2023 | 19/03/2024 | 28/02/2024 | 4 | 2323 | inf | inf | 8 | 46
61 | Birbhum Division | BIRBHUM | Sainthia | Nanubazar Piped Water Supply Scheme | SM/12673 | TSM/014273 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 19/09/2022 | 10/08/2023 | 19/03/2024 | 12/06/2023 | 4 | 1536 | inf | nan | 0 | 0
62 | Birbhum Division | BIRBHUM | Sainthia | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | TSM/014264 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 19/09/2022 | 17/04/2023 | 30/09/2024 | 08/07/2024 | 4 | 1248 | inf | inf | 21 | 5
63 | Birbhum Division | BIRBHUM | Mohammad Bazar | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | TSM/011621 | New | Birbhum Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | 19/09/2022 | 12/04/2023 | 30/08/2024 | 06/12/2023 | 5 | 2082 | inf | inf | 52 | 51
64 | Birbhum Division | BIRBHUM | Mohammad Bazar | Asenga Piped Water Supply Scheme. | SM/12680 | TSM/014568 | New | Birbhum Division | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | 20/09/2022 | 20/04/2023 | 31/08/2024 | 11/10/2023 | 7 | 2144 | inf | inf | 40 | 20
65 | Birbhum Division | BIRBHUM | Dubrajpur | Balijuri Piped Water Supply Scheme. | SM/12682 | TSM/014823 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 21/09/2022 | 10/08/2023 | 21/03/2024 | 12/06/2023 | 2 | 2567 | inf | inf | 0 | 6
66 | Birbhum Division | BIRBHUM | Dubrajpur | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | TSM/014821 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 21/09/2022 | 10/08/2023 | 21/03/2024 | 12/06/2023 | 2 | 1121 | inf | nan | 0 | 0
67 | Birbhum Division | BIRBHUM | Murarai - I | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | TSM/014564 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE2,Junior Engineer | 21/09/2022 | 10/08/2023 | 21/03/2024 | 12/06/2023 | 4 | 1773 | inf | nan | 0 | 0
68 | Birbhum Division | BIRBHUM | Murarai - I | Harinduba Piped Water Supply Scheme. | SM/12692 | TSM/014677 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE3,Junior Engineer | 20/09/2022 | 20/04/2023 | 31/05/2024 | 29/11/2023 | 3 | 1850 | inf | nan | 3 | 0
69 | Birbhum Division | BIRBHUM | Murarai - II | Kamarkhul Piped Water Supply Scheme. | SM/12693 | TSM/014527 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE1,Junior Engineer | 21/09/2022 | 29/09/2023 | 31/05/2024 | 11/01/2024 | 3 | 2268 | inf | inf | 18 | 1
70 | Birbhum Division | BIRBHUM | Murarai - II | Kulara Piped Water Supply Scheme. | SM/12695 | TSM/014400 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE1,Junior Engineer | 21/09/2022 | 06/04/2023 | 30/09/2024 | 10/01/2024 | 7 | 2968 | inf | inf | 34 | 8
71 | Birbhum Division | BIRBHUM | Murarai - I | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | TSM/013256 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE1,Junior Engineer | 21/09/2022 | 25/04/2023 | 08/05/2024 | 10/01/2024 | 5 | 3051 | inf | nan | 34 | 0
72 | Birbhum Division | BIRBHUM | Sainthia | Melanpur Piped Water Supply Scheme. | SM/12699 | TSM/014519 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 21/09/2022 | 20/04/2023 | 30/09/2024 | 22/03/2024 | 4 | 1312 | inf | inf | 5 | 18
73 | Birbhum Division | BIRBHUM | Sainthia | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | TSM/011614 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE2,Junior Engineer | 22/09/2022 | 17/04/2023 | 30/09/2024 | 28/06/2024 | 7 | 1269 | inf | inf | 5 | 8
74 | Birbhum Division | BIRBHUM | Sainthia | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | TSM/011618 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 22/09/2022 | 17/04/2023 | 31/12/2023 | 22/09/2023 | 15 | 2033 | inf | inf | 58 | 43
75 | Birbhum Division | BIRBHUM | Murarai - II | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | TSM/011735 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE3,Junior Engineer | 22/09/2022 | 14/07/2023 | 31/05/2024 | 29/11/2023 | 13 | 2677 | inf | inf | 22 | 19
76 | Birbhum Division | BIRBHUM | Murarai - I | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | TSM/012842 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE3,Junior Engineer | 23/09/2022 | 09/05/2024 | 24/09/2024 | 10/06/2024 | 3 | 2309 | inf | nan | 3 | 0
77 | Birbhum Division | BIRBHUM | Mohammad Bazar | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | TSM/011622 | New | Birbhum Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | 23/09/2022 | 22/03/2023 | 23/03/2024 | 03/10/2023 | 5 | 835 | inf | inf | 26 | 27
78 | Birbhum Division | BIRBHUM | Sainthia | Jashoda Piped Water Supply Scheme. | SM/12891 | TSM/011728 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 23/09/2022 | 10/05/2023 | 30/04/2024 | 26/09/2023 | 7 | 1114 | inf | inf | 8 | 9
79 | Birbhum Division | BIRBHUM | Suri - II | HATIKRA PIPED WATER SUPPLY SCHEME. | SM/12893 | TSM/011731 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 23/09/2022 | 12/04/2023 | 30/09/2024 | 06/08/2024 | 3 | 1587 | inf | inf | 7 | 4
80 | Birbhum Division | BIRBHUM | Dubrajpur | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | TSM/014825 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 22/09/2022 | 03/01/2024 | 31/03/2024 | 04/01/2024 | 8 | 1314 | inf | inf | 8 | 13
81 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme | SM/13372 | TSM/014630 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 19/10/2022 | 01/05/2023 | 30/06/2024 | 04/01/2024 | 1 | 320 | inf | inf | 85 | 47
82 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sadasibpur (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/13373 | TSM/014686 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/10/2022 | 22/12/2022 | 20/02/2024 | 10/01/2024 | 0 | 207 | inf | nan | 85 | 0
83 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. | SM/13374 | TSM/014690 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 19/10/2022 |  | 19/01/2023 | 12/06/2023 | 0 | 215 | inf | nan | 0 | 0
84 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. | SM/13375 | TSM/014696 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 19/10/2022 | 02/08/2023 | 31/03/2024 | 27/09/2023 | 0 | 432 | inf | nan | 7 | 0
85 | Birbhum Division | BIRBHUM | Nanoor | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | TSM/015486 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 18/10/2022 | 28/10/2022 | 18/04/2024 | 16/10/2023 | 5 | 1334 | inf | inf | 4 | 1
86 | Birbhum Division | BIRBHUM | Illambazar | BHUBANESWAR PIPED WATER SUPPLY SCHEME | SM/13387 | TSM/015542 | New | Bolpur Sub-Division | Assistant Engineer | JE1 | 18/10/2022 | 28/10/2022 | 18/04/2024 | 14/03/2024 | 5 | 2288 | inf | inf | 2 | 0
87 | Birbhum Division | BIRBHUM | Nanoor | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | TSM/015476 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 02/11/2022 | 14/11/2022 | 02/05/2024 | 16/10/2023 | 4 | 1526 | inf | inf | 4 | 1
88 | Birbhum Division | BIRBHUM | Mayureswar - I | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | TSM/015470 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 02/11/2022 | 01/06/2023 | 31/03/2024 | 27/09/2023 | 9 | 902 | inf | inf | 30 | 20
89 | Birbhum Division | BIRBHUM | Nanoor | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | TSM/015471 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | 02/11/2022 | 13/11/2022 | 02/05/2024 | 05/12/2023 | 5 | 1734 | inf | inf | 2 | 0
90 | Birbhum Division | BIRBHUM | Mayureswar - I | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | TSM/015431 | New | Birbhum Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | 02/11/2022 | 24/11/2023 | 31/07/2024 | 05/12/2023 | 8 | 1118 | inf | inf | 6 | 9
91 | Birbhum Division | BIRBHUM | Nanoor | Charkalgram Piped Water Supply Scheme | SM/13481 | TSM/015455 | New | Bolpur Sub-Division | Assistant Engineer | JE_BLK_NANOOR | 02/11/2022 | 23/05/2023 | 30/06/2024 | 21/05/2024 | 5 | 2189 | inf | inf | 3 | 0
92 | Birbhum Division | BIRBHUM | Bolpur Sriniketan | Bergram Piped Water Supply Scheme. | SM/13482 | TSM/015559 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | 02/11/2022 | 10/08/2023 | 02/05/2024 | 12/06/2023 | 4 | 1351 | inf | nan | 0 | 0
93 | Birbhum Division | BIRBHUM | Dubrajpur | Kukutia piped water supply scheme. | SM/13601 | TSM/015187 | New | Central Mechanical Sub-DivisionIII | Assistant Engineer-III | Junior Engineer | 09/11/2022 | 10/08/2023 | 09/05/2024 | 12/06/2023 | 4 | 1341 | inf | nan | 0 | 0
94 | Birbhum Division | BIRBHUM | Sainthia | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | TSM/011617 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE2,Junior Engineer | 11/11/2022 | 10/06/2023 | 31/03/2024 | 27/09/2023 | 6 | 1545 | inf | inf | 1 | 5
95 | Birbhum Division | BIRBHUM | Dubrajpur | Gokrui Piped Water Supply Scheme. | SM/13631 | TSM/015224 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 11/11/2022 | 10/08/2023 | 11/05/2024 | 12/06/2023 | 4 | 826 | inf | nan | 0 | 0
96 | Birbhum Division | BIRBHUM | Dubrajpur | Majuria Piped Water Supply Scheme. | SM/13632 | TSM/015230 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 11/11/2022 | 10/08/2023 | 11/05/2024 | 12/06/2023 | 2 | 2503 | inf | nan | 0 | 0
97 | Birbhum Division | BIRBHUM | Mayureswar - II | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | TSM/015494 | New | Birbhum Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | 11/11/2022 | 24/04/2023 | 31/10/2024 | 19/12/2023 | 7 | 1500 | inf | inf | 8 | 36
98 | Birbhum Division | BIRBHUM | Illambazar | CHUNPALASHI PIPED WATER SUPPLY SCHEME | SM/13637 | TSM/015493 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | 11/11/2022 | 22/06/2023 | 11/05/2024 | 14/03/2024 | 4 | 1863 | inf | inf | 2 | 0
99 | Birbhum Division | BIRBHUM | Bolpur Sriniketan | Ikshudhara piped water supply scheme. | SM/13639 | TSM/015100 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | 11/11/2022 | 01/09/2023 | 30/08/2024 | 06/12/2023 | 5 | 2543 | inf | inf | 16 | 19
100 | Birbhum Division | BIRBHUM | Rampurhat - I | Kanaipur piped water supply scheme. | SM/13640 | TSM/015178 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 11/11/2022 | 26/07/2023 | 31/10/2024 | 06/12/2023 | 7 | 2508 | inf | inf | 11 | 13
101 | Birbhum Division | BIRBHUM | Illambazar | Kayera Water Supply Scheme | SM/13641 | TSM/015495 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | 11/11/2022 | 26/07/2023 | 31/10/2024 | 30/05/2024 | 6 | 1231 | inf | inf | 6 | 1
102 | Birbhum Division | BIRBHUM | Illambazar | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | TSM/015499 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | 11/11/2022 | 21/08/2023 | 31/08/2024 | 25/04/2024 | 5 | 1848 | inf | inf | 8 | 3
103 | Birbhum Division | BIRBHUM | Rampurhat - II | Nabagram Piped Water Supply Scheme. | SM/13646 | TSM/015339 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 11/11/2022 | 11/08/2023 | 30/09/2024 | 11/01/2024 | 10 | 1353 | inf | inf | 8 | 2
104 | Birbhum Division | BIRBHUM | Illambazar | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | TSM/015543 | New | Bolpur Sub-Division | Assistant Engineer | JE1 | 11/11/2022 | 28/12/2022 | 11/05/2024 | 14/03/2024 | 5 | 2439 | inf | inf | 2 | 0
105 | Birbhum Division | BIRBHUM | Mohammad Bazar | Sadanandapur piped water supply scheme. | SM/13648 | TSM/015506 | New | Birbhum Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | 11/11/2022 | 06/06/2023 | 11/05/2024 | 03/10/2023 | 4 | 1233 | inf | inf | 31 | 27
106 | Birbhum Division | BIRBHUM | Rampurhat - II | Sahapur Piped water Supply Scheme. | SM/13649 | TSM/015328 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 11/11/2022 | 11/08/2023 | 11/05/2024 | 27/09/2023 | 7 | 1721 | inf | nan | 2 | 0
107 | Birbhum Division | BIRBHUM | Dubrajpur | Sekupur piped water supply scheme. | SM/13650 | TSM/015254 | New | Birbhum Sadar Sub-Division | AE | JE3 | 11/11/2022 | 10/08/2023 | 11/05/2024 | 12/06/2023 | 4 | 762 | inf | nan | 0 | 0
108 | Birbhum Division | BIRBHUM | Rampurhat - II | Shaspur Piped Water Supply Scheme. | SM/13651 | TSM/015337 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 11/11/2022 | 01/08/2023 | 30/09/2024 | 28/05/2024 | 10 | 1371 | inf | inf | 11 | 2
109 | Birbhum Division | BIRBHUM | Illambazar | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | TSM/015500 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | 11/11/2022 | 10/10/2023 | 11/05/2024 | 14/03/2024 | 5 | 1568 | inf | inf | 2 | 0
110 | Birbhum Division | BIRBHUM | Rampurhat - II | Gaytha Piped Water Supply Scheme | SM/13712 | TSM/015546 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 14/11/2022 | 20/04/2023 | 30/09/2024 | 28/05/2024 | 9 | 1164 | inf | inf | 20 | 4
111 | Birbhum Division | BIRBHUM | Rampurhat - II | Podda Piped Water Supply Scheme | SM/13714 | TSM/015557 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 14/11/2022 | 20/04/2023 | 31/10/2024 | 28/05/2024 | 9 | 889 | inf | inf | 75 | 16
112 | Birbhum Division | BIRBHUM | Nanoor | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | TSM/015433 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 18/11/2022 | 07/12/2022 | 18/05/2024 | 05/12/2023 | 5 | 1502 | inf | inf | 2 | 0
113 | Birbhum Division | BIRBHUM | Khoyrasol | Ekura Piped Water Supply Scheme. | SM/13949 | TSM/016748 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 01/12/2022 | 18/07/2023 | 01/06/2024 | 10/05/2024 | 4 | 667 | inf | inf | 2 | 0
114 | Birbhum Division | BIRBHUM | Nanoor | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/13950 | TSM/016099 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 01/12/2022 | 10/12/2022 | 01/06/2024 | 16/10/2023 | 4 | 1812 | inf | inf | 4 | 1
115 | Birbhum Division | BIRBHUM | Labpur | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | TSM/016098 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 01/12/2022 | 09/03/2023 | 01/09/2024 | 13/06/2024 | 4 | 1851 | inf | inf | 2 | 0
116 | Birbhum Division | BIRBHUM | Nanoor | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | TSM/016091 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 01/12/2022 | 26/07/2023 | 01/06/2024 | 21/05/2024 | 4 | 1822 | inf | inf | 3 | 0
117 | Birbhum Division | BIRBHUM | Labpur | TATINAPARA PIPED WATER SUPPLY SCHEME | SM/13979 | TSM/015894 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 01/12/2022 | 01/01/2023 | 30/09/2024 | 28/06/2024 | 3 | 2460 | inf | inf | 2 | 0
118 | Birbhum Division | BIRBHUM | Rampurhat - II | Khamedda Piped Water Supply Scheme | SM/13980 | TSM/015742 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 01/12/2022 | 30/12/2022 | 30/06/2024 | 28/05/2024 | 6 | 2017 | inf | inf | 17 | 3
119 | Birbhum Division | BIRBHUM | Rampurhat - II | Sandhyajol Piped Water Supply Scheme | SM/13981 | TSM/015736 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 01/12/2022 | 30/12/2022 | 01/06/2024 | 08/12/2023 | 5 | 2016 | inf | inf | 2 | 0
120 | Birbhum Division | BIRBHUM | Mayureswar - I | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | TSM/015724 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 01/12/2022 | 03/03/2023 | 31/03/2024 | 27/09/2023 | 10 | 588 | inf | inf | 34 | 22
121 | Birbhum Division | BIRBHUM | Rampurhat - I | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | TSM/009459 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 05/12/2022 | 16/12/2022 | 31/03/2024 | 27/09/2023 | 8 | 656 | inf | inf | 38 | 46
122 | Birbhum Division | BIRBHUM | Rampurhat - I | Radipur Piped Water Supply Scheme. | SM/14027 | TSM/016078 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 05/12/2022 | 10/08/2023 | 05/06/2024 | 12/06/2023 | 3 | 1716 | inf | nan | 0 | 0
123 | Birbhum Division | BIRBHUM | Mohammad Bazar | Haridaspur Piped Water Supply Scheme. | SM/14028 | TSM/016071 | New | Birbhum Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | 05/12/2022 | 01/08/2023 | 31/08/2024 | 29/03/2024 | 5 | 3535 | inf | inf | 7 | 6
124 | Birbhum Division | BIRBHUM | Rampurhat - I | Banhat Piped Water Supply Scheme. | SM/14029 | TSM/016070 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 05/12/2022 | 04/04/2023 | 31/10/2024 | 06/12/2023 | 6 | 2002 | inf | inf | 41 | 36
125 | Birbhum Division | BIRBHUM | Suri - I | Chormara Piped Water Supply Scheme. | SM/14030 | TSM/015886 | New | Birbhum Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | 05/12/2022 | 25/04/2023 | 05/06/2024 | 29/03/2024 | 3 | 881 | inf | inf | 3 | 2
126 | Birbhum Division | BIRBHUM | Sainthia | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/14037 | TSM/010671 | New | RWS Birbhum Sub-Division | AE,Assistant Engineer | JE,Junior Engineer | 12/12/2022 | 13/12/2022 | 31/10/2024 | 11/12/2023 | 1 | 1376 | inf | nan | 40 | 0
127 | Birbhum Division | BIRBHUM | Khoyrasol | Rupaspur Piped Water Supply Scheme. | SM/14081 | TSM/016778 | New | Birbhum Sadar Sub-Division | AE | JE2 | 12/12/2022 | 18/10/2023 | 12/06/2024 | 10/05/2024 | 4 | 975 | inf | inf | 2 | 4
128 | Birbhum Division | BIRBHUM | Khoyrasol | Aliat Piped Water Supply Scheme | SM/14083 | TSM/016735 | New | Birbhum Sadar Sub-Division | AE | JE | 12/12/2022 | 20/07/2023 | 12/06/2024 | 10/05/2024 | 4 | 804 | inf | inf | 2 | 2
129 | Birbhum Division | BIRBHUM | Khoyrasol | Bagahola Piped Water Supply Scheme | SM/14084 | TSM/016715 | New | Birbhum Sadar Sub-Division | AE | JE2 | 12/12/2022 | 26/07/2023 | 12/06/2024 | 10/05/2024 | 4 | 514 | inf | inf | 2 | 0
130 | Birbhum Division | BIRBHUM | Rampurhat - II | Ninga Piped Water Supply Scheme | SM/14089 | TSM/015711 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 12/12/2022 | 02/08/2023 | 12/06/2024 | 06/03/2024 | 5 | 2013 | inf | inf | 3 | 1
131 | Birbhum Division | BIRBHUM | Khoyrasol | Bhaddi Piped Water Supply Scheme | SM/14114 | TSM/016712 | New | Birbhum Sadar Sub-Division | AE | JE | 02/01/2023 | 06/09/2023 | 02/07/2024 | 10/05/2024 | 4 | 897 | inf | inf | 2 | 0
132 | Birbhum Division | BIRBHUM | Mayureswar - I | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | TSM/016201 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 02/01/2023 | 14/08/2023 | 31/10/2024 | 05/12/2023 | 8 | 869 | inf | inf | 12 | 18
133 | Birbhum Division | BIRBHUM | Bolpur Sriniketan | Salan Piped Water Supply Scheme. | SM/14207 | TSM/015574 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | 10/01/2023 | 21/09/2023 | 10/07/2024 | 12/06/2023 | 3 | 2622 | inf | nan | 0 | 0
134 | Birbhum Division | BIRBHUM | Labpur | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | TSM/017000 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 20/01/2023 | 23/03/2023 | 20/07/2024 | 13/06/2024 | 2 | 2499 | inf | inf | 2 | 0
135 | Birbhum Division | BIRBHUM | Labpur | KADOA PIPED WAYER SUPPLY SCHEME | SM/14668 | TSM/017099 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 31/01/2023 | 20/02/2023 | 31/07/2024 | 13/06/2024 | 5 | 1039 | inf | inf | 2 | 0
136 | Birbhum Division | BIRBHUM | Khoyrasol | Bhadulia Piped Water Supply Scheme | SM/14674 | TSM/016717 | New | Birbhum Sadar Sub-Division | AE | JE | 31/01/2023 | 14/06/2023 | 31/07/2024 | 10/05/2024 | 4 | 985 | inf | inf | 2 | 4
137 | Birbhum Division | BIRBHUM | Mayureswar - II | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | TSM/016711 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 31/01/2023 | 25/04/2023 | 31/08/2024 | 28/05/2024 | 8 | 2321 | inf | inf | 4 | 0
138 | Birbhum Division | BIRBHUM | Labpur | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | TSM/016217 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 31/01/2023 | 20/02/2023 | 31/07/2024 | 13/06/2024 | 5 | 1169 | inf | inf | 2 | 0
139 | Birbhum Division | BIRBHUM | Nanoor | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | TSM/016227 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 31/01/2023 | 26/07/2023 | 31/07/2024 | 21/05/2024 | 5 | 2296 | inf | inf | 4 | 0
140 | Birbhum Division | BIRBHUM | Nanoor | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | TSM/015547 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | 31/01/2023 | 26/07/2023 | 31/07/2024 | 21/05/2024 | 5 | 1966 | inf | inf | 4 | 0
141 | Birbhum Division | BIRBHUM | Labpur | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | TSM/016231 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 31/01/2023 | 24/03/2023 | 31/07/2024 | 13/06/2024 | 5 | 2184 | inf | inf | 2 | 0
142 | Birbhum Division | BIRBHUM | Rampurhat - I | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | TSM/014955 | Augmentation | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 31/01/2023 | 26/09/2023 | 31/05/2024 | 27/09/2023 | 8 | 4098 | inf | inf | 9 | 20
143 | Birbhum Division | BIRBHUM | Rampurhat - I | Kanduri Piped Water Supply Scheme. | SM/14824 | TSM/016079 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 04/02/2023 | 29/11/2023 | 04/08/2024 | 12/06/2023 | 4 | 1977 | inf | nan | 0 | 0
144 | Birbhum Division | BIRBHUM | Nanoor | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | TSM/017430 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | 03/02/2023 | 10/03/2023 | 03/08/2024 | 05/12/2023 | 4 | 1576 | inf | inf | 2 | 0
145 | Birbhum Division | BIRBHUM | Nanoor | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | TSM/016086 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | 03/02/2023 | 03/03/2023 | 03/08/2024 | 05/12/2023 | 5 | 1132 | inf | inf | 2 | 0
146 | Birbhum Division | BIRBHUM | Nanoor | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | TSM/017432 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | 03/02/2023 | 13/02/2023 | 03/08/2024 | 16/10/2023 | 3 | 1440 | inf | inf | 4 | 1
147 | Birbhum Division | BIRBHUM | Khoyrasol | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) | SM/14851 | TSM/017783 | New | Birbhum Sadar Sub-Division | AE | JE | 03/02/2023 | 21/08/2023 | 03/08/2024 | 10/05/2024 | 4 | 1165 | inf | inf | 2 | 3
148 | Birbhum Division | BIRBHUM | Khoyrasol | Baraban Piped Water Supply Scheme (Khoyrasole Block) | SM/14852 | TSM/017781 | New | Birbhum Sadar Sub-Division | AE | JE3 | 03/02/2023 | 14/06/2023 | 03/08/2024 | 10/05/2024 | 4 | 1408 | inf | inf | 2 | 0
149 | Birbhum Division | BIRBHUM | Khoyrasol | Haripur Piped Water Supply Scheme | SM/14853 | TSM/017492 | New | Birbhum Sadar Sub-Division | AE | JE | 03/02/2023 | 19/05/2023 | 03/08/2024 | 10/05/2024 | 5 | 2142 | inf | inf | 2 | 5
150 | Birbhum Division | BIRBHUM | Khoyrasol | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) | SM/14854 | TSM/017490 | New | Birbhum Sadar Sub-Division | AE | JE | 03/02/2023 | 26/07/2023 | 03/08/2024 | 10/05/2024 | 4 | 1544 | inf | inf | 2 | 0
151 | Birbhum Division | BIRBHUM | Khoyrasol | Parsundi Piped Water Supply Scheme | SM/14855 | TSM/017487 | New | Birbhum Sadar Sub-Division | AE | JE | 03/02/2023 | 20/02/2024 | 03/08/2024 | 18/04/2024 | 6 | 1178 | inf | inf | 2 | 1
152 | Birbhum Division | BIRBHUM | Rajnagar | Ahmadpur Piped Water Supply Scheme | SM/14889 | TSM/016714 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 03/02/2023 | 31/05/2023 | 31/10/2024 | 22/03/2024 | 6 | 1737 | inf | inf | 7 | 11
153 | Birbhum Division | BIRBHUM | Mayureswar - I | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | TSM/016708 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 04/02/2023 | 10/04/2023 | 04/08/2024 | 27/09/2023 | 11 | 401 | inf | inf | 53 | 41
154 | Birbhum Division | BIRBHUM | Nanoor | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/14895 | TSM/016256 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | 04/02/2023 | 14/02/2023 | 04/08/2024 | 16/10/2023 | 5 | 1649 | inf | inf | 4 | 1
155 | Birbhum Division | BIRBHUM | Labpur | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | TSM/016258 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 14/03/2023 | 04/08/2024 | 13/06/2024 | 4 | 1914 | inf | inf | 2 | 0
156 | Birbhum Division | BIRBHUM | Mohammad Bazar | Dhamara Piped Water Supply Scheme. | SM/14898 | TSM/016240 | New | Birbhum Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | 04/02/2023 | 17/04/2023 | 04/08/2024 | 03/10/2023 | 5 | 1473 | inf | inf | 25 | 27
157 | Birbhum Division | BIRBHUM | Labpur | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | TSM/016169 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 20/02/2023 | 04/08/2024 | 13/06/2024 | 5 | 3136 | inf | inf | 2 | 0
158 | Birbhum Division | BIRBHUM | Rajnagar | Patalpur Piped Water Supply Scheme | SM/14955 | TSM/017157 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 04/02/2023 | 03/10/2023 | 04/08/2024 | 12/06/2023 | 3 | 219 | inf | nan | 0 | 0
159 | Birbhum Division | BIRBHUM | Labpur | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | TSM/017121 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 20/02/2023 | 04/08/2024 | 13/06/2024 | 5 | 1672 | inf | inf | 2 | 1
160 | Birbhum Division | BIRBHUM | Nanoor | RAYEN PIPED WATER SUPPLY SCHEME | SM/14957 | TSM/017123 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | 04/02/2023 | 14/02/2023 | 04/08/2024 | 16/10/2023 | 5 | 698 | inf | inf | 4 | 1
161 | Birbhum Division | BIRBHUM | Labpur | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | TSM/017151 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 27/02/2023 | 04/08/2024 | 01/08/2024 | 3 | 2391 | inf | inf | 4 | 7
162 | Birbhum Division | BIRBHUM | Rampurhat - II | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | TSM/017348 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 04/02/2023 | 20/04/2023 | 04/08/2024 | 28/05/2024 | 8 | 8299 | inf | inf | 41 | 19
163 | Birbhum Division | BIRBHUM | Rampurhat - II | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | TSM/015001 | Augmentation | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE1,Junior Engineer | 04/02/2023 | 08/03/2024 | 31/08/2024 | 23/03/2024 | 3 | 3733 | inf | inf | 6 | 4
164 | Birbhum Division | BIRBHUM | Labpur | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | TSM/017115 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 20/02/2023 | 04/08/2024 | 13/06/2024 | 3 | 1010 | inf | inf | 2 | 0
165 | Birbhum Division | BIRBHUM | Labpur | FARIDPUR PIPED WATER SUPPLY SCHEME | SM/14971 | TSM/016785 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 04/02/2023 | 20/02/2023 | 04/08/2024 | 13/06/2024 | 5 | 1444 | inf | inf | 2 | 0
166 | Birbhum Division | BIRBHUM | Khoyrasol | Demurtita Piped Water Supply Scheme. | SM/14981 | TSM/016788 | New | Birbhum Sadar Sub-Division | AE | JE | 04/02/2023 | 24/10/2023 | 04/08/2024 | 10/05/2024 | 4 | 588 | inf | inf | 2 | 0
167 | Birbhum Division | BIRBHUM | Rampurhat - II | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | TSM/015009 | Augmentation | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 07/02/2023 | 22/12/2023 | 30/09/2024 | 28/05/2024 | 7 | 705 | inf | inf | 8 | 4
168 | Birbhum Division | BIRBHUM | Illambazar | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | TSM/015544 | New | Bolpur Sub-Division | Assistant Engineer | JE1 | 06/02/2023 | 23/11/2023 | 06/08/2024 | 14/03/2024 | 5 | 1633 | inf | inf | 2 | 0
169 | Birbhum Division | BIRBHUM | Illambazar | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | TSM/015545 | New | Bolpur Sub-Division | Assistant Engineer | JE1 | 06/02/2023 | 20/02/2023 | 06/08/2024 | 14/03/2024 | 4 | 1055 | inf | inf | 2 | 0
170 | Birbhum Division | BIRBHUM | Nanoor | MADDA PIPED WATER SUPPLY SCHEME | SM/15255 | TSM/016100 | New | Bolpur Sub-Division | Assistant Engineer | JE2 | 07/02/2023 | 07/03/2023 | 07/08/2024 | 05/12/2023 | 4 | 1390 | inf | inf | 2 | 0
171 | Birbhum Division | BIRBHUM | Khoyrasol | Chora Piped Water Supply Scheme | SM/15523 | TSM/016718 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 16/02/2023 | 26/05/2023 | 16/08/2024 | 10/05/2024 | 5 | 482 | inf | inf | 2 | 0
172 | Birbhum Division | BIRBHUM | Nanoor | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | TSM/016090 | New | Bolpur Sub-Division | Assistant Engineer | JE2 | 15/02/2023 | 10/03/2023 | 15/08/2024 | 05/12/2023 | 5 | 1042 | inf | inf | 2 | 0
173 | Birbhum Division | BIRBHUM | Khoyrasol | Hatikata Piped Water Supply Scheme | SM/16198 | TSM/017489 | New | Birbhum Sadar Sub-Division | AE | JE | 23/02/2023 | 30/03/2023 | 23/08/2024 | 10/05/2024 | 4 | 619 | inf | inf | 2 | 0
174 | Birbhum Division | BIRBHUM | Khoyrasol | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) | SM/16270 | TSM/017780 | New | Birbhum Sadar Sub-Division | AE | JE | 24/02/2023 | 11/07/2023 | 24/08/2024 | 10/05/2024 | 4 | 272 | inf | inf | 2 | 0
175 | Birbhum Division | BIRBHUM | Khoyrasol | Nichinta Piped Water Supply Scheme (Khoyrasole Block) | SM/16271 | TSM/017782 | New | Birbhum Sadar Sub-Division | AE | JE | 24/02/2023 | 27/05/2024 | 24/08/2024 | 28/05/2024 | 4 | 237 | inf | inf | 3 | 0
176 | Birbhum Division | BIRBHUM | Khoyrasol | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) | SM/16272 | TSM/017779 | New | Birbhum Sadar Sub-Division | AE | JE2 | 24/02/2023 | 26/10/2023 | 24/08/2024 | 10/05/2024 | 4 | 538 | inf | inf | 2 | 15
177 | Birbhum Division | BIRBHUM | Khoyrasol | Mayandal Piped Water Supply Scheme | SM/16273 | TSM/017491 | New | Birbhum Sadar Sub-Division | AE | JE | 23/02/2023 | 11/10/2023 | 23/08/2024 | 10/05/2024 | 4 | 342 | inf | inf | 2 | 0
178 | Birbhum Division | BIRBHUM | Labpur | RANIPARA PIPED WATER SUPPLY SCHEME | SM/16276 | TSM/017183 | New | Bolpur Sub-Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | 24/02/2023 | 28/02/2023 | 24/08/2024 | 13/06/2024 | 4 | 876 | inf | inf | 2 | 0
179 | Birbhum Division | BIRBHUM | Khoyrasol | Penchalia Piped Water Supply Scheme | SM/16282 | TSM/017488 | New | Birbhum Sadar Sub-Division | AE | JE | 24/02/2023 | 27/05/2024 | 24/08/2024 | 28/05/2024 | 4 | 831 | inf | inf | 3 | 0
180 | Birbhum Division | BIRBHUM | Rampurhat - II | Budhigram Piped Water Supply Scheme | SM/16762 | TSM/015741 | New | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 13/03/2023 | 30/04/2023 | 30/09/2024 | 06/12/2023 | 4 | 1888 | inf | inf | 5 | 2
181 | Birbhum Division | BIRBHUM | Rampurhat - II | Augmentation of Margram piped water supply scheme. | SM/18372 | TSM/011981 | Augmentation | Rampurhat Sub-Division | AE,Assistant Engineer-III | JE3,Junior Engineer | 11/07/2023 | 10/08/2023 | 11/04/2024 | 07/11/2023 | 8 | 7205 | inf | inf | 8 | 4
182 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | SM/18783 | TSM/021456 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE2, Birbhum Sadar Sub-Division | 29/08/2023 | 22/11/2023 | 31/07/2024 | 26/07/2024 | 3 | 1303 | inf | inf | 5 | 13
Total | [14 empty] | 1309 | 417023 | 0 | 0 |  | NAN