## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | TSM/005613 | Retrofitting |  |  |  | 18/09/2020 | 18/02/2021 | 31/10/2022 | 12/06/2023 | 0 | 777 | inf | nan | 90 | 0
2 | Birbhum Division | BIRBHUM | Rajnagar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | SM/06733 | TSM/005600 | Retrofitting |  |  |  | 18/09/2020 | 21/09/2020 | 31/05/2021 | 12/06/2023 | 0 | 1860 | inf | nan | 100 | 0
3 | Birbhum Division | BIRBHUM | Suri - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | TSM/005601 | Retrofitting |  |  |  | 18/09/2020 | 04/11/2020 | 31/05/2021 | 12/06/2023 | 0 | 1645 | inf | nan | 100 | 0
4 | Birbhum Division | BIRBHUM | Suri - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | TSM/005602 | Retrofitting |  |  |  | 18/09/2020 | 21/09/2020 | 31/05/2021 | 12/06/2023 | 0 | 1860 | inf | nan | 92 | 0
5 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | TSM/005604 | Retrofitting |  |  |  | 18/09/2020 | 23/12/2020 | 31/12/2021 | 12/06/2023 | 0 | 1265 | inf | nan | 95 | 0
6 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | TSM/005607 | Retrofitting |  |  |  | 18/09/2020 | 31/12/2020 | 31/05/2021 | 12/06/2023 | 0 | 1752 | inf | nan | 100 | 0
7 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) | SM/06739 | TSM/005605 | Retrofitting |  |  |  | 18/09/2020 |  | 31/05/2021 | 12/06/2023 | 0 | 1755 | inf | nan | 100 | 0
8 | Birbhum Division | BIRBHUM | Illambazar | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | TSM/005608 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 ,JE4 | 18/09/2020 | 21/09/2020 | 31/05/2021 | 12/06/2023 | 0 | 1875 | inf | nan | 100 | 0
9 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | TSM/005609 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 | 18/09/2020 | 05/10/2021 | 31/12/2021 | 12/06/2023 | 0 | 1860 | inf | nan | 100 | 0
10 | Birbhum Division | BIRBHUM | Illambazar | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | TSM/005610 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 18/09/2020 | 04/11/2020 | 31/12/2021 | 12/06/2023 | 0 | 1830 | inf | nan | 100 | 0
11 | Birbhum Division | BIRBHUM | Rampurhat - I | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | TSM/005611 | Retrofitting |  |  |  | 18/09/2020 | 23/12/2020 | 31/05/2021 | 12/06/2023 | 0 | 1760 | inf | nan | 100 | 0
12 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | TSM/005612 | Retrofitting |  |  |  | 18/09/2020 | 08/02/2021 | 31/05/2021 | 12/06/2023 | 0 | 957 | inf | nan | 100 | 0
13 | Birbhum Division | BIRBHUM | Rajnagar | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | TSM/006171 | Retrofitting |  |  |  | 03/11/2020 | 10/12/2021 | 31/10/2022 | 12/06/2023 | 0 | 1520 | inf | nan | 100 | 0
14 | Birbhum Division | BIRBHUM | Illambazar | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | TSM/006176 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 03/11/2020 | 11/04/2022 | 30/09/2023 | 10/09/2023 | 0 | 1500 | inf | nan | 99 | 0
15 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | TSM/006174 | Retrofitting |  |  |  | 04/11/2020 | 16/07/2021 | 31/05/2021 | 12/06/2023 | 0 | 1510 | inf | nan | 100 | 0
16 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | TSM/006175 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 ,JE_BLK_NANOOR | 03/11/2020 | 13/01/2021 | 30/09/2023 | 10/09/2023 | 0 | 1520 | inf | nan | 99 | 0
17 | Birbhum Division | BIRBHUM | Murarai - I | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | TSM/006188 | Retrofitting |  |  |  | 03/11/2020 | 23/12/2020 | 31/08/2021 | 12/06/2023 | 0 | 1520 | inf | nan | 100 | 0
18 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | TSM/006180 | Retrofitting |  |  |  | 03/11/2020 | 16/08/2021 | 30/06/2022 | 12/06/2023 | 0 | 1530 | inf | nan | 100 | 0
19 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | TSM/006182 | Retrofitting |  |  |  | 03/11/2020 | 24/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 1658 | inf | nan | 100 | 0
20 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06951 | TSM/006184 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 03/11/2020 | 18/08/2021 | 30/06/2023 | 12/06/2023 | 0 | 1135 | inf | nan | 100 | 0
21 | Birbhum Division | BIRBHUM | Suri - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | TSM/005603 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE3 | 13/11/2020 | 04/08/2021 | 01/02/2024 | 30/06/2023 | 0 | 1393 | inf | nan | 85 | 0
22 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07152 | TSM/006173 | Retrofitting |  |  |  | 01/12/2020 | 08/12/2021 | 30/06/2022 | 12/06/2023 | 0 | 851 | inf | nan | 100 | 0
23 | Birbhum Division | BIRBHUM | Rampurhat - I | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | TSM/006177 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 01/12/2020 | 23/12/2020 | 31/03/2024 | 27/09/2023 | 0 | 1408 | inf | nan | 96 | 0
24 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | TSM/006179 | Retrofitting |  |  |  | 01/12/2020 | 04/01/2021 | 30/06/2022 | 12/06/2023 | 0 | 1290 | inf | nan | 100 | 0
25 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | TSM/006183 | Retrofitting |  |  |  | 31/12/2020 | 26/02/2021 | 30/04/2022 | 12/06/2023 | 0 | 3113 | inf | nan | 100 | 0
26 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | TSM/006186 | Retrofitting | Birbhum Division | AE(HQ) | Estimator | 31/12/2020 | 09/02/2022 | 30/06/2023 | 30/06/2023 | 0 | 2702 | inf | nan | 85 | 0
27 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | TSM/006187 | Retrofitting |  |  |  | 31/12/2020 | 27/01/2021 | 30/06/2021 | 12/06/2023 | 0 | 2864 | inf | nan | 100 | 0
28 | Birbhum Division | BIRBHUM | Rampurhat - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | TSM/006720 | Retrofitting |  |  |  | 07/01/2021 | 11/01/2021 | 31/10/2022 | 12/06/2023 | 0 | 1478 | inf | nan | 100 | 0
29 | Birbhum Division | BIRBHUM | Illambazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | TSM/006726 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 ,JE4 | 07/01/2021 | 26/02/2021 | 31/07/2022 | 12/06/2023 | 0 | 1396 | inf | nan | 100 | 0
30 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) | SM/07647 | TSM/006722 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 07/01/2021 | 16/07/2021 | 30/03/2024 | 20/07/2023 | 0 | 1050 | inf | nan | 90 | 0
31 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | TSM/006723 | Retrofitting |  |  |  | 07/01/2021 | 18/08/2021 | 01/12/2022 | 12/06/2023 | 0 | 1745 | inf | nan | 100 | 0
32 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | TSM/006725 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 | 07/01/2021 | 02/09/2021 | 30/04/2022 | 12/06/2023 | 0 | 848 | inf | nan | 100 | 0
33 | Birbhum Division | BIRBHUM | Khoyrasol | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | TSM/006724 | Retrofitting |  |  |  | 07/01/2021 | 15/06/2021 | 30/11/2022 | 12/06/2023 | 0 | 1760 | inf | nan | 90 | 0
34 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | TSM/007022 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 08/02/2021 | 15/06/2021 | 31/12/2023 | 27/09/2023 | 0 | 1525 | inf | nan | 95 | 0
35 | Birbhum Division | BIRBHUM | Suri - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | TSM/006181 | Retrofitting | Birbhum Sadar Sub-Division | AE | JE2 | 09/02/2021 | 09/11/2021 | 31/03/2023 | 12/06/2023 | 0 | 14748 | inf | nan | 90 | 0
36 | Birbhum Division | BIRBHUM | Suri - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | TSM/008199 | Retrofitting |  |  |  | 29/09/2021 | 25/10/2021 | 30/11/2022 | 12/06/2023 | 0 | 1500 | inf | nan | 100 | 0
37 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | TSM/008200 | Retrofitting | Nalhati Sub-Division | AE | JE3 | 29/09/2021 | 29/10/2021 | 30/06/2023 | 12/06/2023 | 0 | 6050 | inf | nan | 100 | 0
38 | Birbhum Division | BIRBHUM | Labpur | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | TSM/008202 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 | 29/09/2021 | 13/12/2021 | 30/09/2023 | 10/09/2023 | 0 | 1500 | inf | nan | 99 | 0
39 | Birbhum Division | BIRBHUM | Labpur | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | TSM/008208 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE1 ,JE4 | 29/09/2021 | 07/10/2021 | 31/01/2023 | 12/06/2023 | 0 | 1682 | inf | nan | 99 | 0
40 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | TSM/008210 | Retrofitting | Rampurhat Sub-Division | AE | JE2 | 29/09/2021 | 29/10/2021 | 31/12/2023 | 27/09/2023 | 0 | 2377 | inf | nan | 96 | 0
41 | Birbhum Division | BIRBHUM | Nanoor | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | TSM/008573 | Retrofitting | Bolpur Sub-Division | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | 12/11/2021 | 22/04/2022 | 28/02/2023 | 12/06/2023 | 0 | 4002 | inf | nan | 90 | 0
42 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | TSM/008570 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 05/04/2022 | 31/12/2023 | 27/09/2023 | 0 | 1851 | inf | nan | 100 | 0
43 | Birbhum Division | BIRBHUM | Rampurhat - II | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09367 | TSM/008520 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 18/08/2022 | 03/03/2024 | 27/09/2023 | 0 | 6979 | inf | nan | 90 | 0
44 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | TSM/008519 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 12/11/2021 | 13/04/2022 | 30/09/2023 | 27/09/2023 | 0 | 1054 | inf | nan | 96 | 0
45 | Birbhum Division | BIRBHUM | Murarai - II | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | TSM/008515 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 12/11/2021 | 15/09/2022 | 30/06/2024 | 04/01/2024 | 0 | 2238 | inf | nan | 88 | 0
46 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | TSM/008514 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 12/11/2021 | 05/04/2022 | 31/03/2023 | 20/07/2023 | 0 | 1622 | inf | nan | 100 | 0
47 | Birbhum Division | BIRBHUM | Rajnagar | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | TSM/008501 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE,Junior Engineer | 29/10/2021 | 21/01/2022 | 31/03/2023 | 12/06/2023 | 0 | 3546 | inf | nan | 90 | 0
48 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | TSM/009066 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/11/2021 | 17/12/2021 | 15/02/2024 | 10/01/2024 | 0 | 2295 | inf | nan | 91 | 0
49 | Birbhum Division | BIRBHUM | Khoyrasol | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | TSM/009739 | Augmentation | Birbhum Sadar Sub-Division | AE,Assistant Engineer-III | JE2,Junior Engineer | 14/03/2022 | 23/05/2022 | 03/02/2024 | 30/06/2023 | 0 | 783 | inf | nan | 85 | 0
50 | Birbhum Division | BIRBHUM | Murarai - I | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | TSM/010389 | Retrofitting | Nalhati Sub-Division | AE | JE3 | 13/04/2022 | 21/04/2022 | 31/03/2023 | 12/06/2023 | 0 | 1063 | inf | nan | 100 | 0
51 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme | SM/12658 | TSM/014584 | Retrofitting | Nalhati Sub-Division | AE | JE1 | 19/09/2022 | 20/04/2023 | 15/02/2024 | 10/01/2024 | 0 | 211 | inf | nan | 90 | 0
52 | Birbhum Division | BIRBHUM | Mohammad Bazar | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | TSM/014565 | Retrofitting | Rampurhat Sub-Division | AE | JE3 | 19/09/2022 | 11/09/2024 | 31/03/2023 | 12/06/2023 | 0 | 1465 | inf | nan | 100 | 0
53 | Birbhum Division | BIRBHUM | Mayureswar - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. | SM/12667 | TSM/014656 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 19/09/2022 | 17/11/2022 |  | 12/06/2023 | 0 | 382 | inf | nan | 100 | 0
54 | Birbhum Division | BIRBHUM | Sainthia | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | TSM/011613 | New | Birbhum Sadar Sub-Division | AE,Assistant Engineer | JE2,Junior Engineer | 22/09/2022 | 02/02/2024 | 31/12/2024 | 15/02/2024 | 0 | 1717 | inf | nan | 96 | 0
55 | Birbhum Division | BIRBHUM | Mayureswar - II | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | TSM/014645 | Retrofitting | Rampurhat Sub-Division | AE | JE1 | 19/10/2022 | 28/07/2023 |  | 12/06/2023 | 0 | 392 | inf | nan | 100 | 0
56 | Birbhum Division | BIRBHUM | Nalhati - I | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme | SM/13372 | TSM/014630 | Retrofitting | Nalhati Sub-Division | AE | JE2 | 19/10/2022 | 01/05/2023 | 30/06/2024 | 04/01/2024 | 0 | 320 | inf | nan | 85 | 0
57 | Birbhum Division | BIRBHUM | Murarai - I | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | TSM/015508 | New | Nalhati Sub-Division | AE,Assistant Engineer | JE1,Junior Engineer | 22/03/2023 | 10/04/2023 | 31/03/2025 | 10/01/2024 | 0 | 1276 | inf | nan | 84 | 0
Total | [14 empty] | 0 | 113565 | 0 | 0 |  | NAN