## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | TSM/005776 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD |  | 18/09/2020 | 16/10/2020 | 16/11/2023 | 04/10/2023 | 0 | 1763 | inf | nan | 100 | 0
2 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | TSM/005777 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD |  | 18/09/2020 | 16/10/2022 | 30/09/2024 | 28/08/2024 | 0 | 1788 | inf | nan | 95 | 0
3 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme | SM/06724 | TSM/005778 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 18/09/2020 | 16/10/2020 | 23/11/2023 | 05/12/2023 | 0 | 1573 | inf | nan | 100 | 0
4 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme | SM/06725 | TSM/005782 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 18/09/2020 | 16/10/2020 | 23/08/2023 | 12/09/2023 | 0 | 1651 | inf | nan | 100 | 0
5 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme | SM/06726 | TSM/005779 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 18/09/2020 | 16/10/2020 | 30/06/2022 | 12/06/2023 | 0 | 1218 | inf | nan | 100 | 0
6 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | TSM/005783 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 18/09/2020 | 16/10/2020 | 30/11/2022 | 12/06/2023 | 0 | 1506 | inf | nan | 100 | 0
7 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | TSM/005780 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 18/09/2020 | 16/10/2020 | 31/12/2021 | 12/06/2023 | 0 | 1175 | inf | nan | 100 | 0
8 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme | SM/06729 | TSM/005784 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 18/09/2020 |  | 31/12/2021 | 12/06/2023 | 0 | 1302 | inf | nan | 100 | 0
9 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme | SM/06730 | TSM/005781 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 18/09/2020 | 16/10/2020 | 31/12/2021 | 12/06/2023 | 0 | 1452 | inf | nan | 100 | 0
10 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme | SM/06731 | TSM/005785 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 18/09/2020 | 16/10/2020 | 16/11/2023 | 04/10/2023 | 0 | 1281 | inf | nan | 100 | 0
11 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | TSM/006325 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 30/06/2022 | 12/06/2023 | 0 | 1847 | inf | nan | 100 | 0
12 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07072 | TSM/006321 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 27/11/2020 | 28/06/2023 | 30/06/2022 | 12/06/2023 | 0 | 1139 | inf | nan | 100 | 0
13 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | TSM/006319 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD |  | 27/11/2020 | 11/12/2020 | 30/09/2024 | 28/08/2024 | 0 | 1479 | inf | nan | 93 | 0
14 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme | SM/07139 | TSM/006328 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 27/11/2020 | 11/12/2020 | 23/11/2023 | 04/10/2023 | 0 | 1389 | inf | nan | 100 | 0
15 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | TSM/006326 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 30/11/2023 | 04/10/2023 | 0 | 1458 | inf | nan | 100 | 0
16 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | TSM/006323 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 16/11/2023 | 04/10/2023 | 0 | 1788 | inf | nan | 100 | 0
17 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme | SM/07143 | TSM/006329 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 23/11/2023 | 04/10/2023 | 0 | 1004 | inf | nan | 100 | 0
18 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme | SM/07144 | TSM/006324 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 27/11/2020 |  | 31/12/2021 | 12/06/2023 | 0 | 1740 | inf | nan | 100 | 0
19 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | TSM/006327 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 30/11/2022 | 12/06/2023 | 0 | 1291 | inf | nan | 100 | 0
20 | Raiganj Division | UTTAR DINAJPUR | Islampur | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | TSM/006320 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 11/12/2020 | 31/12/2021 | 12/06/2023 | 0 | 1125 | inf | nan | 100 | 0
21 | Raiganj Division | UTTAR DINAJPUR | Islampur | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) | SM/07384 | TSM/006317 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 27/11/2020 | 04/02/2021 | 30/09/2024 | 28/08/2024 | 0 | 841 | inf | nan | 96 | 0
22 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | TSM/006318 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 27/11/2020 | 18/06/2021 | 30/09/2024 | 28/08/2024 | 0 | 1481 | inf | nan | 99 | 0
23 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | TSM/005786 | Retrofitting | Islampur Sub-Division | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | 21/12/2020 | 18/06/2021 | 30/09/2024 | 28/08/2024 | 0 | 26407 | inf | nan | 95 | 0
24 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | TSM/005787 | Retrofitting | Islampur Sub-Division | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | 21/12/2020 | 18/06/2021 | 30/09/2024 | 28/08/2024 | 0 | 44879 | inf | nan | 90 | 0
25 | Raiganj Division | UTTAR DINAJPUR |  | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. | SM/07933 | TSM/005357 | Anganwadi | Raiganj Sub-Division | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | 19/01/2021 | 24/06/2021 | 16/11/2023 | 07/07/2023 | 0 | 9023 | inf | nan | 95 | 0
26 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | TSM/006330 | Retrofitting | Raiganj Sub-Division |  | Junior Engineer, ISD ,Junior Engineer, RSD | 22/01/2021 | 18/06/2021 | 30/09/2024 | 28/08/2024 | 0 | 9907 | inf | nan | 95 | 0
27 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). | SM/09109 | TSM/009357 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 17/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
28 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Majhihar WSS for installation of FHTC. | SM/09110 | TSM/009358 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
29 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). | SM/09111 | TSM/009359 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
30 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Purba Durlavpur WSS for installation of FHTC. | SM/09112 | TSM/009360 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
31 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. | SM/09113 | TSM/009361 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 17/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
32 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. | SM/09115 | TSM/009363 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
33 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Bindal WSS for installation of FHTC. | SM/09116 | TSM/009364 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 17/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
34 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Mahammadpur WSS for installation of FHTC. | SM/09117 | TSM/009365 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 17/11/2021 | 29/12/2023 | 16/10/2023 | 0 | 0 | inf | nan | 100 | 0
35 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. | SM/09118 | TSM/009366 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD |  | 29/10/2021 | 12/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
36 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. | SM/09119 | TSM/009367 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
37 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. | SM/09121 | TSM/009369 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
38 | Raiganj Division | UTTAR DINAJPUR | Chopra | Laying of additional pipe line for retrofitting of Ghirnigaonfor installation of FHTC. | SM/09122 | TSM/009370 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 85 | 0
39 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Goagaon for installation of FHTC. | SM/09123 | TSM/009371 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 99 | 0
40 | Raiganj Division | UTTAR DINAJPUR | Islampur | Laying of additional pipe line for retrofitting of Gunabari for installation of FHTC. | SM/09124 | TSM/009372 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 17/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 95 | 0
41 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Intia WSS for installation of FHTC (Part-A & B) . | SM/09125 | TSM/009373 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 95 | 0
42 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Jaingaon WSS for installation of FHTC. | SM/09126 | TSM/009374 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 85 | 0
43 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). | SM/09127 | TSM/009375 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 17/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
44 | Raiganj Division | UTTAR DINAJPUR | Chopra | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. | SM/09128 | TSM/009376 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
45 | Raiganj Division | UTTAR DINAJPUR | Chopra | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. | SM/09131 | TSM/009379 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 85 | 0
46 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Pokheria WSS for installation of FHTC. | SM/09132 | TSM/009380 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 95 | 0
47 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Biprit WSS for installation of FHTC. | SM/09133 | TSM/009381 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
48 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Laying of additional pipe line for retrofitting of Choprabari WSS for installation of FHTC. | SM/09134 | TSM/009382 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
49 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Siripur for installation of FHTC. | SM/09136 | TSM/009384 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 17/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
50 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Debiganj for installation of FHTC. | SM/09137 | TSM/009385 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 |  | 31/08/2023 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
51 | Raiganj Division | UTTAR DINAJPUR | Chopra | Laying of additional pipe line for retrofitting of Dakshin Jibhokati for installation of FHTC. | SM/09138 | TSM/009386 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
52 | Raiganj Division | UTTAR DINAJPUR | Chopra | Laying of additional pipe line for retrofitting of Bhagabati for installation of FHTC. | SM/09139 | TSM/009387 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 82 | 0
53 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Laying of additional pipe line for retrofitting of Majlishpur for installation of FHTC. | SM/09140 | TSM/009388 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 29/10/2021 | 12/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
54 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Laying of additional pipe line for retrofitting of Gutin WSS for installation of FHTC. | SM/09141 | TSM/009389 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
55 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Baruna WSS for installation of FHTC. | SM/09142 | TSM/009390 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
56 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Laying of additional pipe line for retrofitting of Bamair WSS for installation of FHTC. | SM/09143 | TSM/009391 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
57 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Laying of additional pipe line for retrofitting of Poaltair WSS for installation of FHTC. | SM/09144 | TSM/009392 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
58 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Paharajpur WSS for installation of FHTC. | SM/09145 | TSM/009393 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 24/12/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
59 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Phulatti WSS for installation of FHTC. | SM/09146 | TSM/009394 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
60 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Bheur WSS for installation of FHTC. | SM/09147 | TSM/009395 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/11/2023 | 16/10/2023 | 0 | 0 | inf | nan | 100 | 0
61 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Chotparua WSS for installation of FHTC. | SM/09148 | TSM/009396 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
62 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Kaliganj WSS for installation of FHTC. | SM/09149 | TSM/009397 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 95 | 0
63 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of SridharpurWSS for installation of FHTC. | SM/09150 | TSM/009398 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
64 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Gopalpur for installation of FHTC. | SM/09151 | TSM/009399 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 95 | 0
65 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Nalbithi for installation of FHTC. | SM/09155 | TSM/009400 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
66 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Mahinagar for installation of FHTC. | SM/09156 | TSM/009401 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
67 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Pirojpur for installation of FHTC. | SM/09157 | TSM/009402 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
68 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Udaypur for installation of FHTC. | SM/09158 | TSM/009403 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 28/12/2023 | 16/10/2023 | 0 | 0 | inf | nan | 100 | 0
69 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Noabari for installation of FHTC. | SM/09159 | TSM/009404 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
70 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. | SM/09160 | TSM/009405 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
71 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Piplan for installation of FHTC. | SM/09161 | TSM/009406 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
72 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Malgaon for installation of FHTC. | SM/09162 | TSM/009407 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 24/12/2021 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
73 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Sripur for installation of FHTC. | SM/09163 | TSM/009408 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
74 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Laying of additional pipe line for retrofitting of Tungail for installation of FHTC. | SM/09164 | TSM/009409 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
75 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Pakhuriya for installation of FHTC. | SM/09165 | TSM/009410 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 24/11/2023 | 16/10/2023 | 0 | 0 | inf | nan | 100 | 0
76 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Maslandapur for installation of FHTC. | SM/09166 | TSM/009411 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
77 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Laying of additional pipe line for retrofitting of Sherpur for installation of FHTC. | SM/09167 | TSM/009412 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 12/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
78 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Surun for installation of FHTC. | SM/09168 | TSM/009413 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
79 | Raiganj Division | UTTAR DINAJPUR | Itahar | Laying of additional pipe line for retrofitting of Kotar for installation of FHTC. | SM/09169 | TSM/009414 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 29/10/2021 | 03/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
80 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | TSM/009415 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 |  | 12/06/2023 | 0 | 345 | inf | nan | 100 | 0
81 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | TSM/009416 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 280 | inf | nan | 98 | 0
82 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09172 | TSM/009417 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 |  | 12/06/2023 | 0 | 375 | inf | nan | 100 | 0
83 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | TSM/009418 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 375 | inf | nan | 97 | 0
84 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09174 | TSM/009419 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 855 | inf | nan | 96 | 0
85 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | TSM/009420 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 775 | inf | nan | 99 | 0
86 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09176 | TSM/009421 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 |  | 12/06/2023 | 0 | 309 | inf | nan | 100 | 0
87 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09177 | TSM/009422 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 250 | inf | nan | 100 | 0
88 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | TSM/009423 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 16/11/2023 | 05/12/2023 | 0 | 392 | inf | nan | 100 | 0
89 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. | SM/09179 | TSM/009424 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 | 30/11/2022 | 12/06/2023 | 0 | 330 | inf | nan | 100 | 0
90 | Raiganj Division | UTTAR DINAJPUR | Itahar | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09180 | TSM/009425 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 28/10/2021 | 02/11/2021 |  | 12/06/2023 | 0 | 295 | inf | nan | 100 | 0
91 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09181 | TSM/009426 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 388 | inf | nan | 100 | 0
92 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | TSM/009427 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 815 | inf | nan | 94 | 0
93 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09183 | TSM/009428 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 455 | inf | nan | 81 | 0
94 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | TSM/009429 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 458 | inf | nan | 86 | 0
95 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09185 | TSM/009430 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/06/2022 | 12/06/2023 | 0 | 448 | inf | nan | 100 | 0
96 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09186 | TSM/009431 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 388 | inf | nan | 86 | 0
97 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09188 | TSM/009433 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 715 | inf | nan | 100 | 0
98 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | TSM/009434 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 410 | inf | nan | 95 | 0
99 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | TSM/009435 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 30/09/2024 | 28/08/2024 | 0 | 725 | inf | nan | 96 | 0
100 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | TSM/009436 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 31/03/2024 | 28/08/2024 | 0 | 245 | inf | nan | 100 | 0
101 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | TSM/009437 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 02/11/2021 | 31/03/2022 | 12/06/2023 | 0 | 325 | inf | nan | 100 | 0
102 | Raiganj Division | UTTAR DINAJPUR | Chopra | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09193 | TSM/009438 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 07/01/2022 | 31/03/2024 | 28/08/2024 | 0 | 395 | inf | nan | 100 | 0
103 | Raiganj Division | UTTAR DINAJPUR | Karandighi | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09194 | TSM/009439 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 28/10/2021 | 24/12/2021 | 31/03/2024 | 28/08/2024 | 0 | 360 | inf | nan | 100 | 0
104 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | TSM/009094 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 16/12/2021 | 12/05/2022 | 30/09/2024 | 12/04/2024 | 0 | 577 | inf | nan | 93 | 0
105 | Raiganj Division | UTTAR DINAJPUR | Chopra | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | TSM/009075 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 16/12/2021 | 07/01/2022 | 30/09/2024 | 12/04/2024 | 0 | 1165 | inf | nan | 88 | 0
106 | Raiganj Division | UTTAR DINAJPUR | Chopra | Augmentation of Chopra Water Supply Scheme. | SM/10129 | TSM/009083 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | 08/02/2022 | 24/06/2022 | 30/09/2024 | 26/06/2024 | 0 | 3136 | inf | nan | 82 | 0
107 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Restoration of Pipe Line for providing FHTC for Lodhan Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10425 | TSM/010787 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 08/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
108 | Raiganj Division | UTTAR DINAJPUR | Islampur | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10426 | TSM/010788 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 08/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
109 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Restoration of Pipe Line for Retrofitting FHTC of Deona Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10427 | TSM/010777 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 08/04/2022 | 11/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
110 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Sripur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10441 | TSM/010808 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 12/04/2022 | 12/05/2022 | 31/03/2024 | 05/12/2023 | 0 | 0 | inf | nan | 100 | 0
111 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Shridharpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10442 | TSM/010803 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 12/04/2022 | 17/02/2023 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 90 | 0
112 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Sahavita Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10443 | TSM/010805 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 12/04/2022 | 12/05/2022 | 29/12/2023 | 05/12/2023 | 0 | 0 | inf | nan | 100 | 0
113 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10444 | TSM/010807 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 12/04/2022 | 17/03/2023 | 30/09/2024 | 28/08/2024 | 0 | 0 | inf | nan | 90 | 0
114 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10446 | TSM/010810 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 12/04/2022 | 12/05/2022 | 29/12/2023 | 05/12/2023 | 0 | 0 | inf | nan | 100 | 0
115 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe Line for providing FHTC for Barua Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10448 | TSM/010790 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD |  | 11/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
116 | Raiganj Division | UTTAR DINAJPUR | Chopra | Restoration of Pipe Line for Retrofitting FHTC of Mahadevpur Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10450 | TSM/010763 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 11/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
117 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Maslandpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10463 | TSM/010802 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
118 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Kaliganj Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10464 | TSM/010804 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 31/03/2023 | 31/03/2024 | 05/12/2023 | 0 | 0 | inf | nan | 100 | 0
119 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Restoration of Pipe line for providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10465 | TSM/010820 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
120 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10466 | TSM/010821 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
121 | Raiganj Division | UTTAR DINAJPUR | Chopra | Restoration of Damaged Pipe Line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) | SM/10487 | TSM/010781 | Retrofitting | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 13/04/2022 | 12/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
122 | Raiganj Division | UTTAR DINAJPUR | Hemtabad | Restoration of Pipe line for providing FHTC for Bamair Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10493 | TSM/010811 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 11/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
123 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Sherpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10494 | TSM/010813 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
124 | Raiganj Division | UTTAR DINAJPUR | Itahar | Restoration of Pipe line for providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10495 | TSM/010812 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 11/05/2022 | 30/11/2022 | 12/06/2023 | 0 | 0 | inf | nan | 100 | 0
125 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10496 | TSM/010817 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
126 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | Restoration of Pipe line for providing FHTC for Bheur Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10497 | TSM/010816 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 29/12/2023 | 04/10/2023 | 0 | 0 | inf | nan | 100 | 0
127 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10499 | TSM/010818 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 12/05/2022 | 29/12/2023 | 04/10/2023 | 0 | 0 | inf | nan | 100 | 0
128 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10500 | TSM/010819 | Retrofitting | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | 13/04/2022 | 31/03/2023 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
129 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - II | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | TSM/009723 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 03/06/2022 | 25/07/2022 | 31/12/2024 | 28/08/2024 | 0 | 2946 | inf | nan | 82 | 0
130 | Raiganj Division | UTTAR DINAJPUR | Chopra | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | TSM/011434 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 03/08/2022 | 26/08/2022 | 30/09/2024 | 26/06/2024 | 0 | 2535 | inf | nan | 82 | 0
131 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | TSM/011666 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 05/08/2022 | 26/08/2022 | 29/12/2024 | 28/08/2024 | 0 | 3014 | inf | nan | 90 | 0
132 | Raiganj Division | UTTAR DINAJPUR | Goalpokhar - I | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | TSM/011660 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 05/08/2022 | 05/09/2022 | 31/12/2024 | 28/08/2024 | 0 | 3033 | inf | nan | 84 | 0
133 | Raiganj Division | UTTAR DINAJPUR | Islampur | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | TSM/011644 | Augmentation | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 05/08/2022 | 26/08/2022 | 31/12/2024 | 26/06/2024 | 0 | 2840 | inf | nan | 89 | 0
134 | Raiganj Division | UTTAR DINAJPUR | Islampur | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | TSM/014295 | New | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | 02/09/2022 | 23/02/2023 | 31/12/2024 | 28/08/2024 | 0 | 1646 | inf | nan | 89 | 0
135 | Raiganj Division | UTTAR DINAJPUR | Kaliaganj | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | TSM/013010 | New | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | 02/09/2022 | 16/01/2023 | 31/12/2024 | 26/06/2024 | 0 | 1577 | inf | nan | 86 | 0
136 | Raiganj Division | UTTAR DINAJPUR | Islampur | DOHASO PWSS | SM/18304 | TSM/015576 | New | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | 26/06/2023 | 27/07/2023 | 31/12/2024 | 28/08/2024 | 0 | 4064 | inf | nan | 89 | 0
137 | Raiganj Division | UTTAR DINAJPUR |  | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | TSM/005420 | Augmentation |  |  |  | 12/09/2023 | 20/09/2023 | 31/03/2024 | 28/08/2024 | 0 | 0 | inf | nan | 100 | 0
138 | Raiganj Division | UTTAR DINAJPUR | Raiganj | Restoration of Pipe line for providing FHTC for Bindol Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/18993 | TSM/010814 | Retrofitting |  |  |  | 17/10/2023 | 18/10/2023 |  | 11/03/2024 | 0 | 1875 | inf | nan | 100 | 0
Total | [14 empty] | 0 | 160623 | 0 | 0 |  | NAN