## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | TSM/005790 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 06/10/2020 | 15/10/2020 | 06/01/2021 | 12/06/2023 | 9 | 1664 | inf | inf | 89 | 72
2 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | TSM/005792 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 06/10/2020 | 09/10/2020 | 06/01/2021 | 12/06/2023 | 11 | 1671 | inf | inf | 85 | 84
3 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme | SM/06841 | TSM/005795 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 06/10/2020 | 15/10/2020 | 06/01/2021 | 12/06/2023 | 7 | 1671 | inf | inf | 74 | 99
4 | Jalpaiguri Division | JALPAIGURI | Matiali | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | SM/06842 | TSM/005797 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/10/2020 | 02/11/2020 | 06/01/2021 | 12/06/2023 | 3 | 873 | inf | inf | 65 | 22
5 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme | SM/06843 | TSM/005798 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 06/10/2020 | 23/11/2020 | 06/01/2021 | 12/06/2023 | 2 | 925 | inf | inf | 80 | 30
6 | Jalpaiguri Division | JALPAIGURI | Matiali | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme | SM/06847 | TSM/005802 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/10/2020 | 06/01/2021 | 31/12/2023 | 16/10/2023 | 2 | 1019 | inf | inf | 86 | 80
7 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | TSM/005796 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 03/11/2020 | 22/12/2020 | 03/02/2021 | 12/06/2023 | 13 | 2332 | inf | inf | 93 | 88
8 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | TSM/005794 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 03/11/2020 | 18/11/2020 | 03/02/2021 | 12/06/2023 | 12 | 2431 | inf | inf | 57 | 84
9 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | TSM/005791 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 03/11/2020 | 31/12/2020 | 03/02/2021 | 12/06/2023 | 12 | 1976 | inf | inf | 79 | 67
10 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06953 | TSM/006201 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 03/11/2020 | 03/02/2021 | 31/12/2023 | 16/10/2023 | 4 | 917 | inf | inf | 96 | 100
11 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | TSM/006190 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 03/11/2020 | 04/01/2021 | 03/02/2021 | 12/06/2023 | 5 | 1225 | inf | inf | 99 | 100
12 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme | SM/06960 | TSM/006214 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 03/11/2020 | 29/11/2023 | 03/02/2021 | 12/06/2023 | 3 | 1692 | inf | inf | 15 | 9
13 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | SM/06961 | TSM/006215 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 03/11/2020 | 29/11/2023 | 03/02/2021 | 12/06/2023 | 2 | 1259 | inf | inf | 61 | 47
14 | Jalpaiguri Division | JALPAIGURI | Matiali | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | SM/07301 | TSM/006198 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 10/12/2020 | 10/03/2023 | 31/03/2024 | 16/10/2023 | 5 | 240 | inf | inf | 99 | 100
15 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Pradhanpara Mouza Under Sajnapara Piped Water Supply Scheme | SM/07302 | TSM/006208 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 10/12/2020 | 29/11/2023 | 10/03/2021 | 12/06/2023 | 0 | 1309 | inf | inf | 18 | 5
16 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | SM/07891 | TSM/006751 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/01/2021 | 23/02/2021 | 19/04/2021 | 12/06/2023 | 11 | 4696 | inf | inf | 27 | 20
17 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | SM/07892 | TSM/006750 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/01/2021 | 23/02/2021 | 19/04/2021 | 12/06/2023 | 8 | 1950 | inf | inf | 59 | 41
18 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | SM/07893 | TSM/006752 | Retrofitting |  |  |  | 19/01/2021 | 23/02/2021 | 19/04/2021 | 12/06/2023 | 12 | 2191 | inf | inf | 49 | 39
19 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | SM/08035 | TSM/006189 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 02/02/2021 | 13/05/2021 | 02/05/2021 | 12/06/2023 | 9 | 5856 | inf | inf | 19 | 36
20 | Jalpaiguri Division | JALPAIGURI | Rajganj | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | TSM/006194 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 02/02/2021 | 13/05/2021 | 02/05/2021 | 12/06/2023 | 25 | 6704 | inf | inf | 83 | 80
21 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | SM/08037 | TSM/006196 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 02/02/2021 | 19/09/2023 | 02/05/2021 | 12/06/2023 | 15 | 6385 | inf | inf | 92 | 66
22 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | SM/08038 | TSM/006206 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 02/02/2021 | 09/02/2021 | 02/05/2021 | 12/06/2023 | 45 | 6473 | inf | inf | 98 | 99
23 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | SM/08077 | TSM/007024 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 04/02/2021 | 13/03/2023 | 04/05/2021 | 12/06/2023 | 6 | 1080 | inf | inf | 61 | 74
24 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block | SM/08078 | TSM/007025 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 04/02/2021 | 13/05/2021 | 04/05/2021 | 12/06/2023 | 9 | 2090 | inf | inf | 27 | 18
25 | Jalpaiguri Division | JALPAIGURI | Matiali | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | SM/08284 | TSM/006197 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 09/02/2021 | 25/02/2021 | 09/05/2021 | 12/06/2023 | 10 | 2315 | inf | inf | 51 | 14
26 | Jalpaiguri Division | JALPAIGURI | Rajganj | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | TSM/006199 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/02/2021 | 13/05/2021 | 09/05/2021 | 12/06/2023 | 31 | 5069 | inf | inf | 99 | 99
27 | Jalpaiguri Division | JALPAIGURI | Mal | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | SM/08579 | TSM/006528 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 10/02/2021 | 25/02/2021 | 31/12/2023 | 03/07/2023 | 6 | 238 | inf | inf | 67 | 48
28 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Ghasmari Piped Water Supply Scheme. | SM/08868 | TSM/003951 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 20/09/2021 | 24/01/2022 | 31/03/2024 | 16/10/2023 | 24 | 779 | inf | inf | 57 | 46
29 | Jalpaiguri Division | JALPAIGURI | Matiali | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | TSM/005102 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/09/2021 | 18/02/2022 | 31/12/2023 | 03/07/2023 | 18 | 1236 | inf | inf | 56 | 58
30 | Jalpaiguri Division | JALPAIGURI | Mal | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | TSM/003942 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 22/09/2021 | 18/02/2022 | 13/09/2024 | 24/11/2023 | 19 | 4594 | inf | inf | 11 | 17
31 | Jalpaiguri Division | JALPAIGURI | Mal | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 | TSM/003937 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 22/09/2021 | 18/02/2022 | 31/12/2023 | 03/07/2023 | 24 | 991 | inf | inf | 80 | 71
32 | Jalpaiguri Division | JALPAIGURI | Maynaguri | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | SM/09099 | TSM/007485 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/10/2021 | 18/02/2022 | 31/12/2023 | 02/08/2023 | 12 | 1369 | inf | inf | 48 | 68
33 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | SM/09100 | TSM/007026 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 28/10/2021 | 21/01/2022 | 31/12/2022 | 12/06/2023 | 8 | 4346 | inf | inf | 53 | 65
34 | Jalpaiguri Division | JALPAIGURI | Rajganj | Augmentation of Binnaguri Piped Water Supply Scheme | SM/09344 | TSM/008442 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 12/11/2021 | 21/01/2022 | 31/03/2024 | 03/07/2023 | 22 | 2082 | inf | inf | 33 | 41
35 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Domohani Piped Water Supply Scheme | SM/09345 | TSM/008382 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 12/11/2021 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 23 | 2548 | inf | inf | 70 | 65
36 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Rejuvenation of Goralbari Piped Water Supply Scheme | SM/09390 | TSM/008375 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 12/11/2021 | 30/11/2021 | 31/12/2023 | 03/07/2023 | 34 | 0 | inf | inf | 62 | 98
37 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Sajnapara Piped Water Supply Scheme | SM/09391 | TSM/008378 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 12/11/2021 | 14/09/2022 | 31/12/2023 | 03/07/2023 | 12 | 0 | inf | inf | 35 | 24
38 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | SM/09392 | TSM/008374 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 12/11/2021 | 03/03/2022 | 31/12/2023 | 03/07/2023 | 18 | 1462 | inf | inf | 34 | 46
39 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Rejuvenation of Madhabdanga piped water supply scheme. | SM/09456 | TSM/008102 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 27/12/2021 | 31/12/2023 | 03/07/2023 | 21 | 0 | inf | inf | 45 | 82
40 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Rejuvenation of Kajaldighi piped water supply scheme. | SM/09457 | TSM/008110 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 22/11/2021 | 31/12/2023 | 03/07/2023 | 11 | 0 | inf | inf | 55 | 37
41 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Rejuvenation of Charerbari piped water supply scheme. | SM/09458 | TSM/008106 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 22/11/2021 | 31/12/2023 | 03/07/2023 | 18 | 0 | inf | inf | 49 | 77
42 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | TSM/008109 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 27/12/2021 | 31/12/2023 | 03/07/2023 | 22 | 0 | inf | inf | 89 | 87
43 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Rejuvenation of Basilardanga piped water supply scheme. | SM/09460 | TSM/008103 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 27/12/2021 | 31/12/2023 | 03/07/2023 | 21 | 0 | inf | inf | 71 | 89
44 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Rejuvenation of Porapara piped water supply scheme. | SM/09463 | TSM/008108 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 19/11/2021 | 22/02/2022 | 31/12/2023 | 03/07/2023 | 20 | 0 | inf | inf | 65 | 84
45 | Jalpaiguri Division | JALPAIGURI | Rajganj | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | TSM/008824 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/11/2021 | 18/02/2022 | 31/12/2023 | 03/07/2023 | 19 | 0 | inf | inf | 56 | 79
46 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | SM/09483 | TSM/008993 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/11/2021 | 21/01/2022 | 31/12/2023 | 03/07/2023 | 6 | 0 | inf | inf | 12 | 13
47 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/09484 | TSM/009001 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/11/2021 | 11/01/2022 | 31/12/2023 | 03/07/2023 | 19 | 0 | inf | inf | 62 | 90
48 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Khalaigram Piped Water Supply Scheme | SM/09486 | TSM/009016 | Augmentation | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 19/11/2021 | 21/01/2022 | 31/12/2023 | 03/07/2023 | 8 | 0 | inf | inf | 47 | 65
49 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | SM/09518 | TSM/008107 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 14/01/2022 | 31/12/2023 | 03/07/2023 | 17 | 0 | inf | inf | 50 | 59
50 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Rejuvenation of Mohitnagar piped water supply scheme. | SM/09519 | TSM/008105 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/11/2021 | 04/01/2022 | 31/12/2023 | 03/07/2023 | 31 | 0 | inf | inf | 79 | 81
51 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Augmentation of Purba Daukimari Piped Water Supply Scheme | SM/09560 | TSM/008810 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/11/2021 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 23 | 1586 | inf | inf | 77 | 79
52 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Augmentation of Kathapara Piped Water Supply Scheme | SM/09563 | TSM/008819 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/11/2021 | 17/03/2022 | 31/12/2023 | 03/07/2023 | 20 | 2665 | inf | inf | 20 | 24
53 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | SM/09564 | TSM/008823 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/11/2021 | 17/02/2022 | 31/12/2023 | 03/07/2023 | 16 | 0 | inf | inf | 44 | 41
54 | Jalpaiguri Division | JALPAIGURI | Matiali | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/09858 | TSM/009023 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/12/2021 | 23/03/2022 | 31/12/2023 | 16/10/2023 | 10 | 0 | inf | inf | 55 | 55
55 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | TSM/008816 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 06/12/2021 | 07/12/2021 | 31/12/2023 | 03/07/2023 | 9 | 1787 | inf | inf | 5 | 12
56 | Jalpaiguri Division | JALPAIGURI | Dhupguri | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | SM/09861 | TSM/008817 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 06/12/2021 | 05/04/2022 | 31/12/2023 | 25/07/2023 | 15 | 2219 | inf | inf | 39 | 68
57 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | TSM/009019 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/12/2021 | 25/07/2022 | 31/12/2023 | 16/10/2023 | 13 | 0 | inf | inf | 42 | 71
58 | Jalpaiguri Division | JALPAIGURI | Matiali | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | TSM/009026 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/12/2021 | 24/01/2022 | 31/12/2023 | 02/08/2023 | 31 | 1795 | inf | inf | 56 | 57
59 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | TSM/009018 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 06/12/2021 | 22/07/2022 | 31/12/2023 | 03/07/2023 | 17 | 0 | inf | inf | 16 | 54
60 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | TSM/003950 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/09/2021 | 24/01/2022 | 31/12/2023 | 17/07/2023 | 32 | 1906 | inf | inf | 50 | 51
61 | Jalpaiguri Division | JALPAIGURI | Mal | Augmentation of Kranti Piped water supply Scheme | SM/09994 | TSM/008381 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 20/12/2021 | 24/01/2022 | 13/09/2024 | 24/11/2023 | 37 | 5563 | inf | inf | 3 | 52
62 | Jalpaiguri Division | JALPAIGURI | Rajganj | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | TSM/008383 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 20/12/2021 | 23/02/2022 | 31/12/2023 | 17/07/2023 | 99 | 14294 | inf | inf | 67 | 49
63 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | TSM/006969 | Augmentation | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 17/01/2022 | 21/01/2022 | 31/12/2023 | 03/07/2023 | 35 | 3594 | inf | inf | 71 | 42
64 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | TSM/006970 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/01/2022 | 21/01/2022 | 31/12/2023 | 03/07/2023 | 26 | 3250 | inf | inf | 67 | 69
65 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | TSM/006968 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 20/01/2022 | 21/01/2022 | 31/03/2023 | 03/07/2023 | 50 | 7191 | inf | inf | 76 | 57
66 | Jalpaiguri Division | JALPAIGURI | Matiali | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | TSM/009749 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 27/01/2022 | 01/03/2022 | 31/03/2024 | 16/10/2023 | 14 | 0 | inf | inf | 43 | 62
67 | Jalpaiguri Division | JALPAIGURI | Nagrakata | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | TSM/009317 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 27/01/2022 | 05/04/2022 | 31/03/2024 | 01/02/2024 | 14 | 1235 | inf | inf | 30 | 42
68 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | TSM/006972 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 01/02/2022 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 26 | 4905 | inf | inf | 52 | 46
69 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | TSM/006973 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 01/02/2022 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 25 | 3793 | inf | inf | 45 | 49
70 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | TSM/006967 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 01/02/2022 | 02/02/2022 | 31/03/2024 | 17/08/2023 | 23 | 5781 | inf | inf | 40 | 45
71 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | TSM/006971 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 01/02/2022 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 47 | 7173 | inf | inf | 64 | 66
72 | Jalpaiguri Division | JALPAIGURI | Maynaguri | Augmentation of Barnes Water Supply Scheme. | SM/10090 | TSM/006966 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 01/02/2022 | 02/02/2022 | 31/12/2023 | 03/07/2023 | 43 | 4046 | inf | inf | 56 | 70
73 | Jalpaiguri Division | JALPAIGURI | Nagrakata | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | SM/10775 | TSM/009977 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 23/05/2022 | 01/06/2022 | 31/12/2023 | 03/07/2023 | 2 | 783 | inf | inf | 17 | 12
74 | Jalpaiguri Division | JALPAIGURI | Dhupguri | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | TSM/009995 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/08/2022 | 14/09/2022 | 31/03/2024 | 08/09/2023 | 8 | 1206 | inf | inf | 4 | 24
75 | Jalpaiguri Division | JALPAIGURI | Matiali | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | TSM/009996 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/08/2022 | 25/08/2022 | 31/03/2024 | 16/10/2023 | 24 | 1904 | inf | inf | 5 | 19
76 | Jalpaiguri Division | JALPAIGURI | Nagrakata | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | TSM/009997 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/08/2022 | 17/08/2022 | 31/03/2024 | 26/09/2023 | 33 | 1895 | inf | inf | 17 | 25
77 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | TSM/009740 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/09/2022 | 22/09/2022 | 31/12/2023 | 03/07/2023 | 28 | 5116 | inf | inf | 1 | 38
78 | Jalpaiguri Division | JALPAIGURI | Matiali | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | TSM/015677 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 14/11/2022 | 04/04/2023 | 14/05/2024 | 13/10/2023 | 6 | 210 | inf | inf | 9 | 50
79 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | TSM/015419 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 14/11/2022 | 15/05/2023 | 31/03/2024 | 10/10/2023 | 10 | 1179 | inf | inf | 14 | 27
80 | Jalpaiguri Division | JALPAIGURI | Matiali | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | TSM/013277 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 01/12/2022 | 20/03/2023 | 31/03/2024 | 23/08/2023 | 11 | 1157 | inf | inf | 30 | 49
81 | Jalpaiguri Division | JALPAIGURI | Rajganj | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | TSM/014950 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 10/01/2023 | 29/03/2023 | 31/03/2024 | 06/10/2023 | 10 | 2644 | inf | inf | 20 | 17
82 | Jalpaiguri Division | JALPAIGURI | Dhupguri | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | TSM/016178 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 31/01/2023 | 21/03/2023 | 31/03/2024 | 26/09/2023 | 9 | 2319 | inf | inf | 11 | 49
83 | Jalpaiguri Division | JALPAIGURI | Dhupguri | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | TSM/016174 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 31/01/2023 | 01/04/2023 | 31/03/2024 | 12/10/2023 | 11 | 2390 | inf | inf | 26 | 27
84 | Jalpaiguri Division | JALPAIGURI | Maynaguri | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | TSM/016170 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 31/01/2023 | 02/05/2023 | 13/09/2024 | 22/02/2024 | 10 | 469 | inf | inf | 21 | 20
85 | Jalpaiguri Division | JALPAIGURI | Mal | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14884 | TSM/016363 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 03/02/2023 | 04/08/2023 | 03/08/2024 | 12/06/2023 | 3 | 2397 | inf | nan | 0 | 0
86 | Jalpaiguri Division | JALPAIGURI | Mal | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | TSM/016190 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 03/02/2023 | 28/07/2023 | 13/09/2024 | 24/11/2023 | 14 | 2665 | inf | inf | 34 | 44
87 | Jalpaiguri Division | JALPAIGURI | Mal | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | TSM/016691 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 03/02/2023 | 03/10/2023 | 03/08/2024 | 16/10/2023 | 4 | 456 | inf | nan | 1 | 0
88 | Jalpaiguri Division | JALPAIGURI | Maynaguri | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | TSM/015976 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 03/02/2023 | 01/04/2023 | 31/03/2024 | 10/10/2023 | 12 | 2306 | inf | inf | 13 | 21
89 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | TSM/018283 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 04/02/2023 | 01/04/2023 | 31/03/2024 | 11/10/2023 | 13 | 0 | inf | inf | 8 | 29
90 | Jalpaiguri Division | JALPAIGURI | Matiali | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | TSM/018112 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 04/02/2023 | 04/08/2023 | 31/01/2024 | 16/10/2023 | 6 | 0 | inf | inf | 1 | 6
91 | Jalpaiguri Division | JALPAIGURI | Maynaguri | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | TSM/018057 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 04/02/2023 | 28/02/2023 | 04/08/2023 | 12/06/2023 | 7 | 2840 | inf | inf | 3 | 5
92 | Jalpaiguri Division | JALPAIGURI | Matiali | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | TSM/017647 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 04/02/2023 | 12/06/2023 | 31/03/2024 | 09/10/2023 | 11 | 1068 | inf | inf | 3 | 12
93 | Jalpaiguri Division | JALPAIGURI | Matiali | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | TSM/011303 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 04/02/2023 | 20/09/2023 | 31/03/2024 | 16/10/2023 | 12 | 0 | inf | inf | 4 | 35
94 | Jalpaiguri Division | JALPAIGURI | Jalpaiguri | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | SM/15132 | TSM/018659 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 04/02/2023 | 29/09/2023 | 31/03/2024 | 11/10/2023 | 2 | 0 | inf | inf | 18 | 32
95 | Jalpaiguri Division | JALPAIGURI | Dhupguri | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | TSM/014784 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 08/02/2023 | 01/04/2023 | 31/03/2024 | 27/09/2023 | 9 | 966 | inf | inf | 28 | 20
96 | Jalpaiguri Division | JALPAIGURI | Matiali | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | TSM/015385 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 07/02/2023 | 10/05/2023 | 30/06/2024 | 16/04/2024 | 10 | 1080 | inf | inf | 32 | 41
97 | Jalpaiguri Division | JALPAIGURI | Dhupguri | KHUKLUNG PIPED WATER SUPPLY SCHEME | SM/15953 | TSM/018691 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/02/2023 | 15/02/2024 | 22/08/2024 | 23/04/2024 | 3 | 118 | inf | inf | 6 | 4
98 | Jalpaiguri Division | JALPAIGURI | Nagrakata | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | TSM/017828 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 22/02/2023 | 18/03/2024 | 22/08/2024 | 03/06/2024 | 5 | 573 | inf | inf | 8 | 6
99 | Jalpaiguri Division | JALPAIGURI | Nagrakata | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | TSM/013278 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 02/03/2023 | 10/05/2023 | 02/09/2024 | 12/06/2023 | 4 | 1078 | inf | inf | 0 | 0
100 | Jalpaiguri Division | JALPAIGURI | Maynaguri | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | SM/16776 | TSM/018684 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 13/03/2023 | 20/09/2023 | 13/09/2024 | 08/02/2024 | 3 | 30 | inf | inf | 2 | 5
101 | Jalpaiguri Division | JALPAIGURI | Mal | Sisubari Tea Garden Piped Water Supply Scheme | SM/16778 | TSM/018491 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 13/03/2023 | 03/10/2023 | 13/09/2024 | 24/11/2023 | 9 | 663 | inf | inf | 7 | 4
102 | Jalpaiguri Division | JALPAIGURI | Nagrakata | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | TSM/011005 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 15/03/2023 | 15/05/2023 | 15/09/2023 | 12/06/2023 | 3 | 1317 | inf | nan | 0 | 0
103 | Jalpaiguri Division | JALPAIGURI | Dhupguri | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | TSM/014917 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 22/03/2023 | 10/06/2023 | 22/09/2024 | 07/12/2023 | 6 | 2063 | inf | inf | 11 | 21
Total | [14 empty] | 1627 | 199333 | 0 | 0 |  | NAN