## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong -I | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | SM/10600 | TSM/009882 | New |  |  |  | 18/04/2022 | 26/05/2022 |  | 12/06/2023 | 2 | 13 | inf | nan | 100 | 0
2 | Neorakhola W/S Mnt. Division | DARJEELING | Darjeeling Pulbazar | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield | SM/10772 | TSM/009472 | Retrofitting | Neorakhola W/S Mnt. Division |  | Sub-Assistant Engineer | 23/05/2022 | 24/05/2022 | 18/10/2023 | 29/09/2023 | 3 | 96 | inf | nan | 97 | 0
3 | Neorakhola W/S Mnt. Division | DARJEELING |  | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10795 | TSM/009888 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 25/05/2022 | 12/07/2022 |  | 03/10/2023 | 5 | 6 | inf | nan | 100 | 0
4 | Neorakhola W/S Mnt. Division | DARJEELING | Jorebunglow Sukiapokhri | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, | SM/11316 | TSM/009603 | Retrofitting | Kurseong Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer4 | Sub-Assistant Engineer | 13/06/2022 | 21/07/2022 |  | 12/06/2023 | 2 | 51 | inf | nan | 100 | 0
5 | Neorakhola W/S Mnt. Division | DARJEELING | Jorebunglow Sukiapokhri | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. | SM/11317 | TSM/009602 | Retrofitting | Kurseong Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | 13/06/2022 | 30/06/2022 |  | 12/06/2023 | 2 | 142 | inf | nan | 100 | 0
6 | Neorakhola W/S Mnt. Division | DARJEELING | Kurseong | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA | SM/11327 | TSM/010588 | Retrofitting | Kurseong Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | 13/06/2022 | 30/06/2022 | 13/09/2022 | 30/09/2024 | 2 | 135 | inf | nan | 100 | 0
7 | Neorakhola W/S Mnt. Division | DARJEELING | Kurseong | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11334 | TSM/010595 | Retrofitting | Kurseong Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | 13/06/2022 | 21/07/2022 |  | 12/06/2023 | 2 | 246 | inf | nan | 100 | 0
8 | Neorakhola W/S Mnt. Division | DARJEELING | Kurseong | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11346 | TSM/009534 | New | Kurseong Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | 28/06/2022 | 12/07/2022 | 28/12/2023 | 12/06/2023 | 2 | 45 | inf | nan | 81 | 0
9 | Neorakhola W/S Mnt. Division | DARJEELING | Kurseong | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11348 | TSM/009530 | New | Kurseong Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | 28/06/2022 | 25/11/2022 | 28/12/2023 | 12/06/2023 | 2 | 150 | inf | inf | 96 | 9
10 | Neorakhola W/S Mnt. Division | DARJEELING |  | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | TSM/010271 | Health Center |  |  |  | 28/06/2022 | 12/07/2022 |  | 08/09/2023 | 7 | 0 | inf | inf | 100 | 8
11 | Neorakhola W/S Mnt. Division | DARJEELING | Jorebunglow Sukiapokhri | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) | SM/11379 | TSM/011137 | Retrofitting | Darjeeling Sub-Division |  | Junior Engineer-IV,Sub-Assistant Engineer | 04/07/2022 | 12/07/2022 | 04/10/2022 | 29/09/2023 | 4 | 78 | inf | nan | 100 | 0
12 | Neorakhola W/S Mnt. Division | DARJEELING | Darjeeling Pulbazar | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | TSM/011127 | Retrofitting | Neorakhola W/S Mnt. Division |  | Sub-Assistant Engineer | 04/07/2022 | 20/07/2022 | 10/10/2023 | 29/09/2023 | 4 | 474 | inf | inf | 90 | 7
13 | Neorakhola W/S Mnt. Division | DARJEELING | Mirik | Providing functional household tap connection existing PWSS at Bunkulung | SM/11391 | TSM/011139 | Retrofitting | Kurseong Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | 04/07/2022 | 12/07/2022 | 04/10/2022 | 30/09/2024 | 1 | 155 | inf | nan | 100 | 0
14 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong - II | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | SM/13603 | TSM/012584 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 11/11/2022 | 15/02/2023 | 15/12/2024 | 19/11/2024 | 4 | 664 | inf | inf | 83 | 0
15 | Neorakhola W/S Mnt. Division | KALIMPONG | Gorubathan | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/13611 | TSM/011907 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 11/11/2022 | 21/02/2023 | 11/12/2024 | 01/08/2024 | 3 | 383 | inf | inf | 90 | 7
16 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong -I | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | TSM/015717 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/02/2023 | 06/03/2023 | 20/12/2024 | 19/11/2024 | 5 | 685 | inf | inf | 96 | 1
17 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong -I | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 | TSM/015694 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/02/2023 | 09/03/2023 | 20/10/2024 | 23/09/2024 | 4 | 275 | inf | nan | 100 | 0
18 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong - II | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | SM/15643 | TSM/013305 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/02/2023 | 10/03/2023 | 24/12/2024 | 19/11/2024 | 2 | 169 | inf | nan | 85 | 0
19 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong - II | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 | TSM/011490 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/02/2023 | 15/03/2023 | 20/12/2024 | 19/11/2024 | 4 | 171 | inf | inf | 96 | 7
20 | Neorakhola W/S Mnt. Division | KALIMPONG | Kalimpong - II | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | SM/16513 | TSM/017496 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 03/03/2023 | 15/05/2023 | 10/12/2024 | 19/11/2024 | 4 | 369 | inf | inf | 99 | 0
21 | Neorakhola W/S Mnt. Division | KALIMPONG | Gorubathan | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | SM/19112 | TSM/013403 | New |  |  |  | 21/12/2023 | 10/01/2024 |  | 19/07/2024 | 3 | 784 | inf | nan | 100 | 0
Total | [14 empty] | 67 | 5091 | 0 | 0 |  | NAN