## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Balurghat Division | DAKSHIN DINAJPUR |  | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of Laboratory. | SM/06625 | TSM/005371 | Support | RWS Balurghat Sub-Division |  | Junior Engineer 3 Sub Division | 05/02/2020 |  |  | 31/05/2021 | 3 | 0 | inf | inf | 0 | 80
2 | Balurghat Division | DAKSHIN DINAJPUR |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Dakshin Dinajpur District. | SM/08976 | TSM/008149 | Support | Balurghat Division |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | 29/10/2021 |  |  | 31/10/2021 | 0 | 0 | inf | inf | 0 | 63
3 | Balurghat Division | DAKSHIN DINAJPUR |  | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/08979 | TSM/008050 | Support | RWS Balurghat Sub-Division |  | Junior Engineer 3 Sub Division | 29/10/2021 |  |  | 31/10/2021 | 3 | 0 | inf | inf | 0 | 83
4 | Balurghat Division | DAKSHIN DINAJPUR |  | Supply, Delivery and Installation of Computer & Peripherals for Official use under Office of the Superintending Engineer, NBC-II, PHE Dte., and Balurghat Division, PHE Dte. | SM/10112 | TSM/009516 | Support |  |  |  | 02/02/2022 |  |  | 03/02/2022 | 1 | 0 | inf | inf | 0 | 34
5 | Balurghat Division | DAKSHIN DINAJPUR |  | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | TSM/009501 | School | Balurghat Division |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | 24/02/2022 |  |  | 25/02/2022 | 11 | 0 | inf | inf | 0 | 57
6 | Balurghat Division | DAKSHIN DINAJPUR |  | Procurement of Chemicals & consumables Glassware etc. required for smooth running of 05 nos. laboratories in the district of Dakshin Dinajpur. | SM/10515 | TSM/010161 | Support | RWS Balurghat Sub-Division |  | Junior Engineer 3 Sub Division | 13/04/2022 | 14/01/2023 |  | 21/05/2023 | 4 | 0 | inf | inf | 100 | 55
7 | Balurghat Division | DAKSHIN DINAJPUR |  | Procurement of Consumables i.c.w. OMAS for Water Testing Laboratories in the District of Dakshin Dinajpur under JJM (For 01 Year) | SM/11888 | TSM/011796 | Support | RWS Balurghat Sub-Division |  | Junior Engineer 3 Sub Division | 17/08/2022 | 15/02/2023 |  | 21/05/2023 | 1 | 0 | inf | inf | 100 | 37
8 | Balurghat Division | DAKSHIN DINAJPUR |  | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | TSM/021701 | Support |  |  |  | 05/12/2023 | 09/03/2024 |  | 05/12/2023 | 3 | 0 | inf | inf | 0 | 10
Total | [14 empty] | 26 | 0 | 0 | 0 |  | NAN