## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Electrical Division | HOOGHLY | Arambag | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | TSM/017575 |  |  |  |  | 07/02/2023 | 21/02/2023 | 31/03/2024 | 12/06/2023 | 1 | 0 | inf | inf | 0 | 16
2 | Electrical Division | HOWRAH | Amta - I | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | TSM/017892 |  | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer3,Junior Engineer5 | 28/02/2023 | 26/06/2023 | 31/03/2024 | 27/06/2023 | 1 | 0 | inf | inf | 1 | 18
3 | Electrical Division | HOOGHLY | Haripal | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | SM/18930 | TSM/020453 | Augmentation |  |  |  | 09/10/2023 | 28/11/2023 | 09/04/2024 | 29/11/2023 | 3 | 0 | inf | inf | 1 | 33
4 | Electrical Division | HOOGHLY | Singur | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | TSM/020469 | Augmentation |  |  |  | 09/10/2023 | 02/11/2023 | 09/04/2024 | 03/11/2023 | 6 | 0 | inf | inf | 1 | 32
Total | [14 empty] | 11 | 0 | 0 | 0 |  | NAN