## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Diamond Harbour - I | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Boria and Bayarsing Water Supply Scheme in the district of South 24 Pgs under South 24 Pgs Mechanical Division, PHE | SM/18178 | TSM/013470 |  | South 24 Pgs Mechanical Division | Assistant Engineer -II | Junior Engineer | 31/03/2023 | 07/06/2024 | 30/09/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
2 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Budge Budge - II | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Haori PWSS at Budge Budge- II Block under South 24 Pgs Mechanical Division, PHE Dte. | SM/18741 | TSM/018203 |  |  |  |  | 17/08/2023 |  | 17/02/2024 | 17/08/2023 | 0 | 0 | inf | nan | 0 | 0
3 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Sitakundu (Zone-I) PWSS at Baruipur Block under South 24 Pgs Mechanical Division, PHE Dte. | SM/18742 | TSM/018028 |  |  |  |  | 17/08/2023 |  | 17/02/2024 | 17/08/2023 | 0 | 0 | inf | nan | 0 | 0
4 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani | SM/18743 | TSM/018007 |  |  |  |  | 17/08/2023 | 07/02/2024 | 17/02/2024 | 17/08/2023 | 3 | 0 | inf | nan | 0 | 0
5 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Canning - II | Pilot scale implementation of IOT based Measurement & Monitoring of water service delivery in Srinagar Water Supply Scheme, Canning-II Block, South 24 Parganas under South 24-Pgs Mechanical Division, PHE Dte. | SM/18744 | TSM/010773 | Augmentation |  |  |  | 17/08/2023 |  | 17/02/2024 | 17/08/2023 | 0 | 0 | inf | nan | 0 | 0
6 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Sonarpur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Sahebpur PWSS at Sonarpur Block under South 24 Pgs Mechanical Division, PHE Dte. | SM/18762 | TSM/018096 |  |  |  |  | 23/08/2023 |  | 23/02/2024 | 24/08/2023 | 0 | 0 | inf | nan | 0 | 0
7 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Jaynagar - I | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Kamaria, Zone-III PWSS at Jaynagar-I Block under South 24 Pgs Mechanical Division, PHE Dte. | SM/18763 | TSM/018092 |  |  |  |  | 23/08/2023 |  | 23/02/2024 | 24/08/2023 | 0 | 0 | inf | nan | 0 | 0
8 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Sonarpur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for KANTIPOTA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Div | SM/18854 | TSM/020296 |  |  |  |  | 03/10/2023 |  | 03/04/2024 | 05/10/2023 | 0 | 0 | inf | nan | 0 | 0
9 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Sonarpur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for DEARA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divisio | SM/18855 | TSM/020295 |  |  |  |  | 03/10/2023 | 09/02/2024 | 03/04/2024 | 05/10/2023 | 1 | 0 | inf | nan | 0 | 0
10 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Sonarpur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for HOGALKURIA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Di | SM/18856 | TSM/020290 |  |  |  |  | 03/10/2023 | 09/02/2024 | 03/04/2024 | 05/10/2023 | 1 | 0 | inf | nan | 0 | 0
11 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Sonarpur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Ramchandrapur PWSS at Sonarpur Block under South 24 Pgs Mechanical Division, PHE Dte. | SM/18857 | TSM/020260 |  |  |  |  | 03/10/2023 |  | 03/04/2024 | 05/10/2023 | 0 | 0 | inf | nan | 0 | 0
12 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Harimul Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divis | SM/18858 | TSM/020277 |  |  |  |  | 03/10/2023 |  | 03/04/2024 | 05/10/2023 | 0 | 0 | inf | nan | 0 | 0
13 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Kuruli Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divisi | SM/18859 | TSM/020264 |  |  |  |  | 03/10/2023 |  | 03/04/2024 | 05/10/2023 | 0 | 0 | inf | nan | 0 | 0
14 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Jaytala Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divis | SM/18860 | TSM/020278 |  |  |  |  | 03/10/2023 |  | 03/04/2024 | 05/10/2023 | 0 | 0 | inf | nan | 0 | 0
15 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS | Baruipur | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for JELERHAT Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divi | SM/18861 | TSM/020279 |  |  |  |  | 03/10/2023 | 08/02/2024 | 03/04/2024 | 05/10/2023 | 1 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 7 | 0 | 0 | 0 |  | NAN