## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS |  | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | TSM/008137 | Disaster | South 24 Pgs Mechanical Division | Assistant Engineer -I | Junior Engineer | 30/10/2021 |  |  | 02/11/2021 | 180 | 0 | inf | inf | 0 | 96
2 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS |  | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | TSM/008134 | Disaster | South 24 Pgs Mechanical Division | Assistant Engineer | Junior Engineer | 29/10/2021 |  |  | 04/11/2021 | 190 | 0 | inf | inf | 0 | 97
3 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS |  | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | TSM/008135 | Disaster | South 24 Pgs Mechanical Division | Assistant Engineer | Junior Engineer | 29/10/2021 |  |  | 04/11/2021 | 120 | 0 | inf | inf | 0 | 97
4 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS |  | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | TSM/008136 | Disaster |  |  |  | 29/10/2021 |  |  | 04/11/2021 | 151 | 0 | inf | inf | 0 | 97
5 | South 24 Pgs Mechanical Division | SOUTH 24 PARAGANAS |  | Supply , installation, testing and commissioning of video surveillance equipments at Dakshin Roypur WTP under South 24-Parganas Mechanical Division, PHE, Dte. | SM/18276 | TSM/021498 | Support |  |  |  | 23/06/2023 |  |  | 27/06/2023 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 641 | 0 | 0 | 0 |  | NAN