## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Central Mechanical Division | PURBA BARDHAMAN | Ausgram - II | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | TSM/016511 |  | Central Mechanical Sub-Division | ASSISTANT ENGINEER | Junior Engineer | 15/03/2023 | 10/07/2023 | 12/08/2024 | 15/07/2024 | 13 | 0 | inf | inf | 25 | 26
2 | Central Mechanical Division | PURBA BARDHAMAN | Manteswar | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman | SM/18991 | TSM/019255 |  |  |  |  | 17/10/2023 | 23/04/2024 | 10/07/2024 | 02/05/2024 | 3 | 0 | inf | inf | 10 | 0
Total | [14 empty] | 16 | 0 | 0 | 0 |  | NAN