## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Asansol Mechanical Division | PASCHIM BARDHAMAN | Barabani | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | TSM/009668 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I | Junior Engineer-4 | 09/02/2022 | 11/02/2022 | 09/08/2022 | 12/06/2023 | 9 | 0 | inf | inf | 0 | 86
2 | Asansol Mechanical Division | PASCHIM BARDHAMAN | Faridpur Durgapur | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | TSM/020338 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-2 | 13/03/2023 | 04/04/2023 | 31/12/2023 | 27/09/2023 | 3 | 0 | inf | inf | 20 | 41
3 | Asansol Mechanical Division | PASCHIM BARDHAMAN | Raniganj | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | SM/16777 | TSM/020344 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 13/03/2023 | 04/04/2023 | 04/04/2024 | 20/12/2023 | 3 | 0 | inf | inf | 30 | 42
Total | [14 empty] | 15 | 0 | 0 | 0 |  | NAN