## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Salbani | Solarization of grid connected pumping installation at Kalaimuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17362 | TSM/018862 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 15/03/2023 | 23/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
2 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Garbeta - II | Solarization of grid connected pumping installation at Sutkujhuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17383 | TSM/018882 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 15/03/2023 | 23/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
3 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Salbani | Solarization of grid connected pumping installation at Dhengasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17384 | TSM/018854 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 15/03/2023 | 23/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
4 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Garbeta - II | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17738 | TSM/019302 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 17/03/2023 | 29/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
5 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Garbeta - II | Solarization of grid connected pumping installation Goaltore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17745 | TSM/019301 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 17/03/2023 | 29/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
6 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Salbani | Solarization of grid connected pumping installation Kalshibhanga PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17749 | TSM/019321 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 17/03/2023 | 29/03/2023 |  | 12/06/2023 | 1 | 0 | inf | nan | 100 | 0
7 | Midnapore Mechanical Division | PASCHIM MEDINIPUR | Ghatal | Solarization of grid connected pumping installation Mulgram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17760 | TSM/019306 |  | Midnapur Mechanical Sub Division-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | 17/03/2023 | 29/03/2023 |  | 12/06/2023 | 2 | 0 | inf | nan | 100 | 0
Total | [14 empty] | 8 | 0 | 0 | 0 |  | NAN