## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Bankura Mechanical Division | BANKURA | Sonamukhi | Construction of Grid- connection solar photo-voltaic system for Kanaipur pumping station of Panchal PWS scheme,Dist: Bankura. | SM/10271 | TSM/009607 | IOT | Bankura Mechanical Sub-Division | Assistant Engineer |  | 25/02/2022 | 28/04/2022 | 31/03/2024 | 09/10/2023 | 1 | 0 | inf | inf | 98 | 54
2 | Bankura Mechanical Division | BANKURA | Bankura - II | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura | SM/15312 | TSM/018673 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 19/04/2023 | 31/10/2024 | 10/05/2024 | 2 | 0 | inf | inf | 88 | 33
3 | Bankura Mechanical Division | BANKURA | Patrasayer | Construction of Grid-Connected solar photo -voltaic system for Patrasayer PWSS scheme Dist Bankura | SM/15313 | TSM/018674 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 19/09/2023 | 31/10/2024 | 10/05/2024 | 2 | 0 | inf | inf | 44 | 33
4 | Bankura Mechanical Division | BANKURA | Vishnupur | Construction of Grid-Connected solar photo -voltaic system for Radhanagar PWSS scheme Dist Bankura | SM/15314 | TSM/018675 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 10/02/2023 | 31/10/2023 | 23/08/2023 | 2 | 0 | inf | inf | 75 | 54
5 | Bankura Mechanical Division | BANKURA | Patrasayer | Construction of Grid-Connected solar photo -voltaic system for Nabakishor PWSS scheme Dist Bankura | SM/15316 | TSM/018679 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 20/09/2023 | 31/03/2024 | 27/02/2024 | 1 | 0 | inf | inf | 42 | 18
6 | Bankura Mechanical Division | BANKURA | Bankura - I | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura | SM/15318 | TSM/018676 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 23/05/2023 | 31/10/2024 | 10/05/2024 | 3 | 0 | inf | inf | 98 | 36
7 | Bankura Mechanical Division | BANKURA | Jaypur | Construction of Grid-Connected solar photo -voltaic system for Pump House I of Moynapur PWS scheme Dist Bankura | SM/15328 | TSM/018680 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 23/03/2023 | 09/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
8 | Bankura Mechanical Division | BANKURA | Chhatna | Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15329 | TSM/019282 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 09/02/2023 | 10/05/2023 | 31/10/2024 | 10/05/2024 | 2 | 0 | inf | inf | 50 | 11
9 | Bankura Mechanical Division | BANKURA | Jaypur | Construction of Grid-connected Solar Photo-Voltaic system for Joypur pump house-I of Joypur PWSS scheme,Dist: Bankura | SM/16932 | TSM/016449 |  | Bankura Mechanical (Drill) Sub-Division | Assistant Engineer | Junior Engineer | 16/03/2023 | 17/04/2023 | 16/09/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
10 | Bankura Mechanical Division | BANKURA | Kotulpur | Construction of Grid-connected Solar Photo-Voltaic system for Katulpur pump house-I(OHR site) of Kotulpur PWSS scheme,Dist: Bankura | SM/16963 | TSM/016444 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 16/03/2023 | 17/04/2023 | 16/09/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
11 | Bankura Mechanical Division | BANKURA | Sonamukhi | Construction of Grid-connected Solar Photo-Voltaic system for Rampur pump house-I of Rampur PWSS scheme,Dist: Bankura | SM/16965 | TSM/016561 |  | Bankura Mechanical Sub-Division | Assistant Engineer |  | 16/03/2023 | 04/05/2023 | 31/03/2024 | 25/01/2024 | 1 | 0 | inf | inf | 72 | 25
12 | Bankura Mechanical Division | BANKURA | Khatra | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | SM/17238 | TSM/019195 |  | Bankura Mechanical (Drill) Sub-Division | Driller-in-Charge |  | 15/03/2023 | 15/09/2023 | 31/03/2024 | 31/01/2024 | 4 | 0 | inf | inf | 80 | 15
Total | [14 empty] | 21 | 0 | 0 | 0 |  | NAN