## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Habra - I | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Habra - I and Sandeshkhali - I & II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15760 | TSM/017685 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/11/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
2 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Basirhat - II | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Basirhat- II Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15761 | TSM/017863 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 70 | 0
3 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Barasat - I | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Barasat- I & II And Habra-II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15762 | TSM/017865 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/11/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
4 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Hasnabad | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Hasnabad Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15763 | TSM/017866 |  |  |  |  | 20/02/2023 | 31/10/2023 | 20/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
5 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Minakhan | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Minakhan, Hingalganj and Amdanga Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15764 | TSM/017867 |  |  |  |  | 20/02/2023 | 02/11/2023 | 20/11/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
6 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Bongaon | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bongaon Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15765 | TSM/018088 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/11/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
7 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Baduria | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Baduria Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15766 | TSM/018052 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
8 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Basirhat - I | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Basirhat- I Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15767 | TSM/018069 |  |  |  |  | 20/02/2023 | 05/10/2023 | 20/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 12 | 0
9 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Gaighata | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Gaighata & Swarupnagar Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15768 | TSM/018264 |  |  |  |  | 20/02/2023 | 02/11/2023 | 20/11/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
10 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Bagda | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bagda Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15769 | TSM/018247 |  |  |  |  | 20/02/2023 | 02/11/2023 | 20/08/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
11 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Deganga | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Deganga Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/15770 | TSM/018532 |  |  |  |  | 20/02/2023 |  | 20/08/2023 | 12/06/2023 | 0 | 0 | inf | nan | 0 | 0
12 | Eastern Mechanical Division | NADIA | Karimpur - I | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Karimpur-I & II Blocks in Nadia District under Eastern Mechanical Division PHE Dte. | SM/16846 | TSM/017586 |  | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 13/03/2023 | 02/11/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
13 | Eastern Mechanical Division | NADIA | Ranaghat - I | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Ranaghat-I & II Blocks in Nadia District under Eastern Mechanical Division PHE Dte. | SM/16847 | TSM/017632 |  | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 13/03/2023 | 05/10/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
14 | Eastern Mechanical Division | NADIA | Krishnagar - I | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Krishnagar - I Block in Nadia District under Eastern Mechanical Division, PHE, Directorate. | SM/16848 | TSM/017683 |  |  |  |  | 13/03/2023 | 05/10/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
15 | Eastern Mechanical Division | NADIA | Tehatta - I | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Tehatta - I and Tehatta - II Blocks in Nadia District under Eastern Mechanical Division, PHE, Directorate. | SM/16849 | TSM/017684 |  | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 13/03/2023 | 05/10/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
16 | Eastern Mechanical Division | NADIA | Chapra | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Chapra and Krishnaganj Blocks in Nadia District under Eastern Mechanical Division, PHE, Directorate. | SM/16850 | TSM/017686 |  | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 13/03/2023 | 05/10/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
17 | Eastern Mechanical Division | NADIA | Santipur | Solarizations of WBSEDCL Energized Electrical Installations including Net Metering at Different piped water supply schemes at Santipur & Nabadwip Blocks in Nadia District under Eastern Mechanical Division PHE Dte | SM/16851 | TSM/018064 |  | Eastern Mechanical Sub Division-II | Assistant Engineer | Junior Engineer | 13/03/2023 | 05/10/2023 | 13/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
18 | Eastern Mechanical Division | NORTH 24 PARAGANAS | Barrackpur - II | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Barrackpur-II and Sandeshkhali-I Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. | SM/17172 | TSM/020024 |  |  |  |  | 16/03/2023 | 05/10/2023 | 16/09/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
19 | Eastern Mechanical Division | NADIA | Hanskhali | Solarisation of WBSEDCL Energised Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Hanskhali Block in Nadia District under Eastern Mechanical Division PHE, Dte. | SM/17183 | TSM/017202 |  |  |  |  | 15/03/2023 | 02/11/2023 | 15/12/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 18 | 0 | 0 | 0 |  | NAN