## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Malda Mechanical Division | MALDAH | English Bazar | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. | SM/13237 | TSM/014262 | Augmentation | Malda Mechanical Division | Assistant Engineer - II | Junior Engineer-04 | 14/10/2022 | 15/12/2022 | 31/03/2024 | 10/08/2023 | 2 | 0 | inf | inf | 84 | 75
2 | Malda Mechanical Division | DAKSHIN DINAJPUR | Balurghat | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 | TSM/015913 |  | Malda Mechanical Division | Assistant Engineer - I | Junior Engineer-01 | 15/03/2023 | 12/07/2023 | 31/03/2024 | 19/01/2024 | 5 | 0 | inf | inf | 10 | 8
3 | Malda Mechanical Division | MALDAH | Gazole | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Adhna Water Supply Schemes at Gazole Block of Malda District under Malda Mechanical Division, PHE | SM/17657 | TSM/019692 | IOT |  |  |  | 22/03/2023 | 27/06/2023 | 31/03/2024 | 28/06/2023 | 0 | 0 | inf | nan | 5 | 0
4 | Malda Mechanical Division | MALDAH | Habibpur | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Dakshin Brindabanbati Water Supply Schemes at Habibpur Block of Malda District under Malda Mechan | SM/17659 | TSM/019695 | IOT |  |  |  | 22/03/2023 | 09/06/2023 | 31/03/2024 | 28/06/2023 | 0 | 0 | inf | nan | 5 | 0
5 | Malda Mechanical Division | MALDAH | English Bazar | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Sailpur Water Supply Schemes at Englishbazar Block of Malda District under Malda Mechanical Divis | SM/17661 | TSM/019700 | IOT |  |  |  | 22/03/2023 | 28/06/2023 | 31/03/2024 | 07/07/2023 | 0 | 0 | inf | nan | 10 | 0
6 | Malda Mechanical Division | DAKSHIN DINAJPUR | Tapan | Design, Supply and Installation of different capacity Solar Power Plant at various water work station of Tapan Sub Surface Water Based Piped Water Supply Scheme with Net Metering Arrangement, Monitoring System in the district of Dakshin Dinajpur under Mal | SM/17675 | TSM/020299 | IOT | Malda Mechanical Division | Assistant Engineer - I | Junior Engineer-01 | 22/03/2023 |  | 22/09/2023 | 12/06/2023 | 0 | 0 | inf | nan | 0 | 0
7 | Malda Mechanical Division | DAKSHIN DINAJPUR | Gangarampur | Design, Supply and Installation of different capacity Solar Power Plant at various water work station of Gangarampur Sub Surface Water Based Piped Water Supply Scheme with Net Metering Arrangement, Monitoring System in the district of Dakshin Dinajpur un | SM/17676 | TSM/020300 | IOT | Malda Mechanical Division | Assistant Engineer - I | Junior Engineer-01 | 22/03/2023 | 21/06/2024 | 22/09/2023 | 12/06/2023 | 1 | 0 | inf | nan | 0 | 0
8 | Malda Mechanical Division | UTTAR DINAJPUR | Raiganj | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | TSM/016626 |  | Malda Mechanical Division | Assistant Engineer - I | Junior Engineer-02,Junior Engineer-06,Junior Engineer-07 | 29/03/2023 | 07/07/2023 | 29/09/2023 | 12/06/2023 | 7 | 0 | inf | nan | 0 | 0
9 | Malda Mechanical Division | MALDAH | Habibpur | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | TSM/016528 |  |  |  |  | 29/03/2023 | 03/07/2023 | 31/03/2024 | 21/12/2023 | 8 | 0 | inf | inf | 12 | 16
Total | [14 empty] | 23 | 0 | 0 | 0 |  | NAN