## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Buita W/S Scheme for Booth No:197 to 198 and Adjoining Areas under Budge Budge-I Block | SM/07014 | TSM/006124 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 23/11/2020 | 31/07/2022 | 12/06/2023 | 0 | 696 | inf | nan | 97 | 0
2 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Buita W/S Scheme for Booth No:137 to 140 and Adjoining Areas under Budge Budge-I Block | SM/07016 | TSM/006121 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 18/12/2020 | 31/03/2024 | 12/02/2024 | 0 | 2227 | inf | nan | 85 | 0
3 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Buita W/S Scheme for Booth No:141 to 144 and Adjoining Areas under Budge Budge-I Block | SM/07017 | TSM/006119 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 18/12/2020 | 31/12/2023 | 09/12/2023 | 0 | 2088 | inf | nan | 90 | 0
4 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Nischintipur W/S Scheme for Nischintipur Mouza near Head Work Site and Adjoining Areas under Budge Budge-I Block | SM/07018 | TSM/006129 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 1500 | inf | nan | 97 | 0
5 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Nandarampur W/S Scheme for Chak Nabashan Mouza and adjoining areas under Budge Budge-I Block | SM/07019 | TSM/006139 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 640 | inf | nan | 97 | 0
6 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Nandarampur W/S Scheme for Booth No:170 and Adjoining Areas under Budge Budge-I Block | SM/07020 | TSM/006127 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 18/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 1800 | inf | nan | 100 | 0
7 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works | SM/07050 | TSM/006136 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 2183 | inf | nan | 86 | 0
8 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Providing Functional Household Tap Connection for Atmarampur W/S Scheme for Atmarampur,Chingripota and Santoshpur Mouza under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur. | SM/07051 | TSM/006114 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 1627 | inf | nan | 95 | 0
9 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:153 to 169 under Budge Budge-I Block with allied works | SM/07053 | TSM/006134 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 07/11/2023 | 0 | 1637 | inf | nan | 90 | 0
10 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works | SM/07054 | TSM/006133 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 1910 | inf | nan | 95 | 0
11 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works | SM/07055 | TSM/006131 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 12/06/2023 | 0 | 1550 | inf | nan | 95 | 0
12 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of distribution System For Jamalpur W/S Scheme for habitations of Jamalpur Mouza and adjoining areas under Budge Budge-I Block with allied works | SM/07056 | TSM/006138 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 25/11/2020 | 18/12/2020 | 31/12/2023 | 26/08/2023 | 0 | 1286 | inf | nan | 98 | 0
13 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Baruipur | Improvement of W/S by interconnection from existing big dia TW and laying distribution system with CIDF, UPVC pipes including providing FHTC by retrofitting of scheme Improvement of WS [Phase-III] in Baruipur and Mograhat-II Block of Sankarpur-II GP withi | SM/08182 | TSM/006926 | Retrofitting | Baruipur Sub-Division | AE BSD |  | 09/02/2021 | 07/07/2021 | 31/12/2023 | 16/10/2023 | 0 | 1497 | inf | nan | 95 | 0
14 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Uttar Roypur, Balarampur (Part) and Chak Nabasan (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09946 | TSM/008302 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/12/2021 | 25/01/2022 | 31/12/2023 | 07/11/2023 | 0 | 50 | inf | nan | 85 | 0
15 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of pipeline for supporting FHTC drive for under Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza including Balarampur Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas | SM/09947 | TSM/008298 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/12/2021 | 25/01/2022 | 31/03/2024 | 31/01/2024 | 0 | 1526 | inf | nan | 90 | 0
16 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09950 | TSM/008295 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/12/2021 | 25/01/2022 | 31/12/2023 | 16/08/2023 | 0 | 394 | inf | nan | 85 | 0
17 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09954 | TSM/008291 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/12/2021 | 25/01/2022 | 31/12/2023 | 07/11/2023 | 0 | 118 | inf | nan | 91 | 0
18 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Budge Budge - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144 ) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09956 | TSM/008293 | Retrofitting | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/12/2021 | 25/01/2022 | 31/12/2023 | 12/06/2023 | 0 | 80 | inf | nan | 90 | 0
19 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | TSM/009340 | School | Sub-Division - II under South 24pgs W/s Division - I | AE SWSD-II |  | 08/02/2022 | 15/02/2022 | 31/12/2023 | 13/10/2023 | 0 | 0 | inf | nan | 85 | 0
20 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | TSM/009341 | School | Baruipur Sub-Division | AE BSD,AE SWSD-I |  | 08/02/2022 | 15/02/2022 | 31/12/2023 | 17/10/2023 | 0 | 0 | inf | nan | 95 | 0
21 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | TSM/009342 | School | South 24 Pgs. W/S Division - I | AE BSD,AE HQ-I |  | 08/02/2022 | 15/02/2022 | 31/12/2023 | 23/11/2023 | 0 | 0 | inf | nan | 87 | 0
22 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | TSM/009339 | School | South 24 Pgs. W/S Division - I | AE HQ-I |  | 08/02/2022 | 15/02/2022 | 31/12/2023 | 17/10/2023 | 0 | 0 | inf | nan | 93 | 0
23 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | TSM/009338 | School | South 24 Pgs. W/S Division - I | AE HQ-I |  | 08/02/2022 | 15/02/2022 | 31/12/2024 | 05/06/2024 | 0 | 0 | inf | nan | 94 | 0
24 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS |  | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | TSM/005807 | Support | Sub-Division - I under South 24 W/s Division - I | AE SWSD-I |  | 14/01/2022 | 31/07/2023 | 31/03/2024 | 13/12/2023 | 0 | 0 | inf | nan | 90 | 0
25 | South 24 Pgs. W/S Division - I | SOUTH 24 PARAGANAS | Bishnupur - I | Proposed ground water based CHAK BALAIBAG piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTE | SM/13783 | TSM/016350 | Augmentation | Sub-Division - II under South 24pgs W/s Division - I | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | 18/11/2022 | 09/02/2023 |  | 12/06/2023 | 0 | 2793 | inf | nan | 100 | 0
Total | [14 empty] | 0 | 25602 | 0 | 0 |  | NAN