## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte | SM/09039 | TSM/008791 | Anganwadi |  |  |  | 30/10/2021 | 03/03/2022 | 12/07/2023 | 28/06/2023 | 0 | 0 | inf | nan | 90 | 0
2 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | SM/09934 | TSM/009214 | Retrofitting | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 13/12/2021 | 03/03/2022 | 31/12/2023 | 31/08/2024 | 0 | 1435 | inf | nan | 75 | 0
3 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | TSM/010570 | Augmentation | Barasat Arsenic Division | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | 18/04/2022 | 31/05/2023 | 31/03/2024 | 19/01/2024 | 0 | 1845 | inf | nan | 87 | 0
4 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Baduria | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | SM/10559 | TSM/009206 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 18/04/2022 | 11/11/2022 | 31/03/2024 | 19/01/2024 | 0 | 180 | inf | nan | 72 | 0
5 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | TSM/010751 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 22/07/2022 | 31/05/2023 | 30/04/2024 | 07/03/2024 | 0 | 248 | inf | nan | 64 | 0
6 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | TSM/009609 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | 22/07/2022 | 31/05/2023 | 30/06/2024 | 09/11/2023 | 0 | 2441 | inf | nan | 94 | 0
7 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | TSM/009584 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | 22/07/2022 | 31/05/2023 | 30/06/2024 | 13/05/2024 | 0 | 2875 | inf | nan | 81 | 0
8 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | TSM/010753 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 22/07/2022 | 31/05/2023 | 31/03/2024 | 19/01/2024 | 0 | 128 | inf | nan | 70 | 0
9 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Baduria | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | TSM/010996 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 28/07/2022 | 31/05/2023 | 31/07/2024 | 19/01/2024 | 0 | 1405 | inf | nan | 34 | 0
10 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Hasnabad | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | TSM/011147 | Augmentation | Barasat Arsenic Sub-Division | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | 28/07/2022 | 31/05/2023 | 31/03/2024 | 19/01/2024 | 0 | 1024 | inf | nan | 23 | 0
11 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Sandeshkhali - II | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | TSM/011234 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | 28/07/2022 | 31/05/2023 | 30/06/2024 | 08/11/2023 | 0 | 391 | inf | nan | 61 | 0
12 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Baduria | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11663 | TSM/010997 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 28/07/2022 | 31/05/2023 | 30/06/2024 | 19/01/2024 | 0 | 150 | inf | nan | 52 | 0
13 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Sandeshkhali - II | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | TSM/011252 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 29/07/2022 | 31/05/2023 | 31/03/2024 | 19/01/2024 | 0 | 573 | inf | nan | 52 | 0
14 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Hasnabad | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | TSM/010982 | Augmentation |  |  |  | 29/07/2022 | 31/05/2023 | 31/03/2024 | 19/01/2024 | 0 | 174 | inf | nan | 37 | 0
15 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Baduria | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | TSM/010998 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 29/07/2022 | 30/08/2022 | 31/03/2024 | 19/01/2024 | 0 | 1360 | inf | nan | 50 | 0
16 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13420 | TSM/015209 | Augmentation | Barasat Arsenic Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | 02/11/2022 | 18/01/2023 | 31/03/2024 | 19/01/2024 | 0 | 567 | inf | nan | 27 | 0
17 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Hasnabad | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | TSM/011116 | Augmentation | Barasat Arsenic Sub-Division |  | Junior Engineer | 18/11/2022 | 31/05/2023 | 31/03/2024 | 08/11/2023 | 0 | 279 | inf | nan | 26 | 0
18 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Rajarhat | SULANGGARI Piped Water Supply Scheme | SM/14634 | TSM/016291 | New |  |  |  | 31/01/2023 | 20/04/2023 | 31/03/2024 | 08/11/2023 | 0 | 3786 | inf | nan | 5 | 0
19 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Rajarhat | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | TSM/017800 | Augmentation |  |  |  | 16/02/2023 | 17/02/2023 | 31/03/2024 | 05/07/2023 | 0 | 750 | inf | nan | 5 | 0
20 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | TEGHARIA Piped Water Supply Scheme | SM/16457 | TSM/016121 | New |  |  |  | 03/03/2023 | 04/08/2023 | 03/09/2024 | 08/11/2023 | 0 | 1445 | inf | nan | 5 | 0
21 | Barasat Arsenic Division | NORTH 24 PARAGANAS | Barasat - II | BARDASIA Piped Water Supply Scheme | SM/16626 | TSM/016108 | New |  |  |  | 14/03/2023 | 04/08/2023 | 14/09/2024 | 08/11/2023 | 0 | 1968 | inf | nan | 5 | 0
Total | [14 empty] | 0 | 23024 | 0 | 0 |  | NAN