## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | TSM/008784 | Disaster |  |  |  | 29/10/2021 |  |  | 31/10/2021 | 31 | 0 | inf | inf | 0 | 92
2 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha | SM/09030 | TSM/008133 | Disaster |  |  |  | 30/10/2021 |  |  | 02/11/2021 | 3 | 0 | inf | inf | 0 | 82
3 | Barasat Arsenic Division | ALIPURDUAR |  | Maintenance & modification of Jal swapna applications & dashboard through the up-gradation of backend database, identification of gaps and providing support through various communication media for technical skill enhancement of the users at all levels for | SM/10735 | TSM/010548 | Support |  |  |  | 19/05/2022 |  |  | 19/05/2022 | 3 | 0 | inf | inf | 0 | 88
4 | Barasat Arsenic Division | ALIPURDUAR |  | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | TSM/010550 | Support |  |  |  | 19/05/2022 |  |  | 19/05/2022 | 3 | 0 | inf | inf | 0 | 78
5 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Development of custom Document Archival System (DAS) software and selection of Service Provider for scanning / digitalization of documents for the Office of The Superintending Engineer, Eastern Circle, P.H.E. Dte. at Janasswasthya Karigari Bhawan, Public | SM/16510 | TSM/019274 | Support |  |  |  | 03/03/2023 |  |  | 06/03/2023 | 1 | 0 | inf | inf | 0 | 24
6 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Improvement of IT Infrastructure by providing Desktop computers, printers, copiers and its peripherals for Barasat Arsenic Division & Barasat Arsenic Sub Division Offices, PHE Dte. | SM/17634 | TSM/016177 | Support |  |  |  | 22/03/2023 |  |  | 24/03/2023 | 2 | 0 | inf | inf | 0 | 28
7 | Barasat Arsenic Division | NORTH 24 PARAGANAS |  | Project Management Services and Engineering Consultancy Job for 1. Integrated Surface Water Based Piped Water Supply Scheme for arsenic affected block of Baduria, Basirhat-I & II, Deganga & Swarupnagar in North 24 Parganas District & 2. Surface Water Bas | SM/18477 | TSM/015207 | Support |  |  |  | 24/07/2023 |  |  | 26/07/2023 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 43 | 0 | 0 | 0 |  | NAN