## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Nadia Arsenic Civil Division II | NADIA | Chapra | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08305 | TSM/007299 | Retrofitting |  |  |  | 26/02/2021 |  | 30/11/2021 | 12/06/2023 | 3 | 835 | inf | inf | 98 | 46
2 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | Retrofitting of Bagakhali Zone-I water supply scheme underTehatta-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08307 | TSM/007296 | Retrofitting |  |  |  | 26/02/2021 |  | 31/12/2021 | 12/06/2023 | 1 | 1176 | inf | inf | 75 | 78
3 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | TSM/008763 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 07/12/2021 | 31/03/2024 | 05/09/2023 | 16 | 1593 | inf | inf | 73 | 47
4 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09245 | TSM/008762 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 07/12/2021 | 31/03/2024 | 05/09/2023 | 7 | 430 | inf | inf | 74 | 43
5 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | TSM/008761 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 20/01/2022 | 31/12/2023 | 12/06/2023 | 16 | 660 | inf | inf | 80 | 49
6 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | TSM/008760 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/12/2023 | 12/06/2023 | 10 | 739 | inf | inf | 70 | 27
7 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09248 | TSM/008758 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/12/2023 | 12/06/2023 | 15 | 2269 | inf | inf | 72 | 51
8 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09249 | TSM/008759 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 30/12/2022 | 12/06/2023 | 16 | 234 | inf | inf | 75 | 60
9 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | TSM/008757 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/03/2024 | 05/09/2023 | 13 | 671 | inf | inf | 63 | 55
10 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | TSM/008756 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/03/2024 | 05/09/2023 | 5 | 962 | inf | inf | 69 | 40
11 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09252 | TSM/008733 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 16/11/2021 | 31/12/2023 | 12/06/2023 | 21 | 1337 | inf | inf | 70 | 35
12 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | TSM/008730 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 17/11/2021 | 31/12/2023 | 12/06/2023 | 17 | 226 | inf | inf | 73 | 34
13 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09255 | TSM/008736 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 17/11/2021 | 31/12/2023 | 12/06/2023 | 9 | 1308 | inf | inf | 75 | 17
14 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | TSM/008734 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 18/11/2021 | 31/03/2024 | 05/09/2023 | 11 | 1556 | inf | inf | 68 | 33
15 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | TSM/008732 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 16/11/2021 | 31/03/2024 | 05/09/2023 | 18 | 266 | inf | inf | 69 | 7
16 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | TSM/008728 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/12/2023 | 12/06/2023 | 15 | 1595 | inf | inf | 72 | 57
17 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09259 | TSM/008725 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/12/2023 | 12/06/2023 | 13 | 2353 | inf | inf | 79 | 67
18 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | TSM/008729 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/03/2024 | 05/09/2023 | 9 | 1106 | inf | inf | 76 | 60
19 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | TSM/008727 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/03/2024 | 05/09/2023 | 20 | 138 | inf | inf | 70 | 82
20 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09262 | TSM/008726 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/12/2023 | 12/06/2023 | 13 | 833 | inf | inf | 70 | 44
21 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09263 | TSM/008724 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/12/2023 | 12/06/2023 | 7 | 89 | inf | inf | 72 | 10
22 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09264 | TSM/008723 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 09/12/2021 | 31/12/2023 | 12/06/2023 | 17 | 9 | inf | inf | 75 | 40
23 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09265 | TSM/008722 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 14/01/2022 | 31/03/2024 | 05/09/2023 | 8 | 982 | inf | inf | 70 | 37
24 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09266 | TSM/008721 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 12/11/2021 | 31/03/2024 | 05/09/2023 | 11 | 372 | inf | inf | 71 | 28
25 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09267 | TSM/008720 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/12/2023 | 12/06/2023 | 16 | 3580 | inf | inf | 70 | 39
26 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | TSM/008719 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 14/07/2022 | 31/12/2023 | 12/06/2023 | 15 | 1411 | inf | inf | 72 | 61
27 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | TSM/008718 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 09/11/2021 | 31/12/2023 | 12/06/2023 | 14 | 570 | inf | inf | 78 | 53
28 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09270 | TSM/008717 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 08/11/2021 | 31/03/2024 | 05/09/2023 | 12 | 2595 | inf | inf | 72 | 29
29 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09271 | TSM/008671 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 09/11/2021 | 31/12/2023 | 12/06/2023 | 16 | 1269 | inf | inf | 75 | 35
30 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09866 | TSM/009127 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/12/2023 | 12/06/2023 | 14 | 550 | inf | inf | 74 | 33
31 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | TSM/009120 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/12/2023 | 12/06/2023 | 25 | 3052 | inf | inf | 75 | 73
32 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | TSM/009118 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/03/2024 | 05/09/2023 | 11 | 1059 | inf | inf | 72 | 8
33 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | TSM/009107 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/12/2023 | 12/06/2023 | 14 | 2255 | inf | inf | 75 | 30
34 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09870 | TSM/009095 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/03/2024 | 05/09/2023 | 15 | 2623 | inf | inf | 78 | 35
35 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | TSM/009098 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/12/2023 | 12/06/2023 | 19 | 2653 | inf | inf | 70 | 50
36 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09872 | TSM/009113 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 28/01/2022 | 31/12/2023 | 12/06/2023 | 18 | 2266 | inf | inf | 80 | 59
37 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10093 | TSM/009109 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 01/02/2022 | 04/03/2022 | 31/12/2023 | 12/06/2023 | 32 | 3734 | inf | inf | 75 | 12
38 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | TSM/009114 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 01/02/2022 | 04/03/2022 | 31/12/2023 | 12/06/2023 | 24 | 5978 | inf | inf | 80 | 25
39 | Nadia Arsenic Civil Division II | NADIA | Chapra | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | TSM/009068 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 05/08/2022 | 31/03/2024 | 28/07/2023 | 30 | 1582 | inf | inf | 37 | 32
40 | Nadia Arsenic Civil Division II | NADIA | Chapra | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | TSM/009069 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 08/06/2022 | 31/03/2024 | 30/06/2023 | 23 | 1261 | inf | inf | 37 | 30
41 | Nadia Arsenic Civil Division II | NADIA | Chapra | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | TSM/009022 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 13/05/2022 | 31/07/2024 | 16/04/2024 | 28 | 1374 | inf | inf | 48 | 31
42 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | TSM/009105 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 22/02/2022 | 04/03/2022 | 31/12/2023 | 12/06/2023 | 24 | 3798 | inf | inf | 75 | 25
43 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | TSM/009215 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 18/05/2022 | 31/03/2024 | 02/08/2023 | 25 | 1235 | inf | inf | 36 | 36
44 | Nadia Arsenic Civil Division II | NADIA | Chapra | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | TSM/008804 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 08/04/2022 | 19/05/2022 | 31/03/2024 | 12/06/2023 | 23 | 1665 | inf | inf | 43 | 41
45 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | TSM/008994 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 12/05/2022 | 31/05/2024 | 20/03/2024 | 26 | 1218 | inf | inf | 47 | 42
46 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | TSM/008951 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 19/04/2022 | 30/04/2024 | 01/03/2024 | 20 | 1975 | inf | inf | 43 | 44
47 | Nadia Arsenic Civil Division II | NADIA | Santipur | Manik Nagar Piped W/S Scheme | SM/10407 | TSM/008673 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 08/04/2022 | 13/05/2022 | 31/03/2024 | 12/06/2023 | 23 | 1182 | inf | inf | 43 | 39
48 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | TSM/008996 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 19/05/2022 | 31/03/2024 | 12/06/2023 | 30 | 1387 | inf | inf | 45 | 32
49 | Nadia Arsenic Civil Division II | NADIA | Hanskhali | SANATANPUR PIPED WATER SUPPLY SCHEME | SM/10409 | TSM/008959 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 08/04/2022 | 05/05/2022 | 31/03/2024 | 12/06/2023 | 21 | 1283 | inf | inf | 45 | 28
50 | Nadia Arsenic Civil Division II | NADIA | Chapra | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | TSM/008800 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 08/04/2022 | 19/04/2022 | 31/03/2024 | 12/06/2023 | 23 | 1651 | inf | inf | 42 | 33
51 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | TSM/008998 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 13/05/2022 | 31/03/2024 | 12/06/2023 | 25 | 797 | inf | inf | 41 | 24
52 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | TSM/008657 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 20/04/2022 | 18/07/2022 | 31/03/2024 | 12/06/2023 | 30 | 4138 | inf | inf | 45 | 36
53 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16100 | TSM/015457 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 17/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 98 | inf | nan | 0 | 0
54 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Dharammpur (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16101 | TSM/015464 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 17/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 95 | inf | nan | 0 | 0
55 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Shatikhali (Part-A) village, Block- Tehatta-II, Nadia District, Under Nadia Arsenic Civil Division-II. | SM/16102 | TSM/015466 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 97 | inf | nan | 0 | 0
56 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Shatikhali (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16103 | TSM/015467 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 92 | inf | nan | 0 | 0
57 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Chak Rudranagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II | SM/16104 | TSM/015477 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 76 | inf | nan | 0 | 0
58 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16105 | TSM/015521 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 3 | 79 | inf | nan | 0 | 0
59 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Mini Piped Water Supply Scheme at Chak Ramnagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II, | SM/16106 | TSM/015522 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 82 | inf | nan | 0 | 0
60 | Nadia Arsenic Civil Division II | NADIA | Karimpur - II | Mini Piped Water Supply Scheme at Jayghata village, Block- Karimpur-II, Nadia District , under Nadia Arsenic Civil Division-II. | SM/16109 | TSM/015525 | New | Eastern Mechanical Sub Division-III | Assistant Engineer | Junior Engineer | 22/02/2023 | 11/05/2023 | 22/08/2024 | 12/06/2023 | 2 | 99 | inf | inf | 0 | 28
Total | [14 empty] | 904 | 80598 | 0 | 0 |  | NAN