## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Kurseong Division | DARJEELING | Kurseong | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] | SM/10262 | TSM/007006 | Retrofitting | Neorakhola W/S Mnt. Division | Assistant Engineer | Sub-Assistant Engineer | 08/02/2021 |  | 08/05/2021 | 30/04/2022 | 12 | 817 | inf | inf | 0 | 48
2 | Kurseong Division | DARJEELING | Jorebunglow Sukiapokhri | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | TSM/007005 | Retrofitting |  |  |  | 08/02/2021 |  | 08/05/2021 | 30/04/2022 | 6 | 312 | inf | inf | 0 | 50
3 | Kurseong Division | DARJEELING | Kurseong | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | TSM/007004 | Retrofitting |  |  |  | 08/02/2021 |  | 08/05/2021 | 30/04/2022 | 6 | 1124 | inf | inf | 0 | 67
4 | Kurseong Division | DARJEELING | Kurseong | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 | TSM/013419 | New | Kurseong Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | 17/02/2023 | 28/02/2023 | 17/08/2024 | 28/05/2024 | 2 | 229 | inf | nan | 46 | 0
5 | Kurseong Division | DARJEELING | Kurseong | PWS Scheme for Selim Hill Tea Garden | SM/15652 | TSM/013284 | New | Kurseong Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | 17/02/2023 | 09/03/2023 | 17/08/2024 | 30/11/2023 | 2 | 384 | inf | inf | 48 | 20
6 | Kurseong Division | DARJEELING | Kurseong | PWS scheme for St. Mary's & Goethals | SM/15661 | TSM/013415 | New | Kurseong Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | 17/02/2023 | 01/03/2023 | 17/08/2024 | 16/10/2023 | 3 | 675 | inf | nan | 9 | 0
7 | Kurseong Division | DARJEELING | Mirik | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | TSM/017734 | New | Kurseong Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | 20/02/2023 | 03/08/2023 | 20/08/2024 | 11/01/2024 | 2 | 172 | inf | inf | 47 | 15
8 | Kurseong Division | DARJEELING | Kurseong | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18878 | TSM/020480 | Augmentation |  |  |  | 05/10/2023 |  | 05/04/2024 | 06/10/2023 | 0 | 161 | inf | nan | 0 | 0
9 | Kurseong Division | DARJEELING | Kurseong | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME | SM/18879 | TSM/020479 | Augmentation |  |  |  | 05/10/2023 |  | 05/04/2024 | 06/10/2023 | 0 | 80 | inf | nan | 0 | 0
10 | Kurseong Division | DARJEELING | Kurseong | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18880 | TSM/020477 | Augmentation |  |  |  | 05/10/2023 |  | 05/04/2024 | 06/10/2023 | 0 | 190 | inf | nan | 0 | 0
11 | Kurseong Division | DARJEELING | Naxalbari | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | TSM/020476 | Augmentation |  |  |  | 05/10/2023 |  | 05/04/2024 | 06/10/2023 | 0 | 159 | inf | nan | 0 | 0
Total | [14 empty] | 33 | 4303 | 0 | 0 |  | NAN