## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Northern Mechanical Division II | ALIPURDUAR | Madarihat | Implementation of Affordable IOT System at Dalmore-Ramjhora TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16906 | TSM/020214 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
2 | Northern Mechanical Division II | ALIPURDUAR | Alipurduar - II | Implementation of Affordable IOT System at Dhaolajhora TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16907 | TSM/020210 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
3 | Northern Mechanical Division II | ALIPURDUAR | Madarihat | Implementation of Affordable IOT System at Dheklapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16908 | TSM/020216 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
4 | Northern Mechanical Division II | ALIPURDUAR | Kalchini | Implementation of Affordable IOT System at Dima TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16909 | TSM/020212 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
5 | Northern Mechanical Division II | ALIPURDUAR | Madarihat | Implementation of Affordable IOT System at Dimdima TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16910 | TSM/020217 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
6 | Northern Mechanical Division II | ALIPURDUAR | Kumargram | Implementation of Affordable IOT System at Jayanti TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16911 | TSM/020208 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
7 | Northern Mechanical Division II | ALIPURDUAR | Madarihat | Implementation of Affordable IOT System at Makrapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16912 | TSM/020213 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
8 | Northern Mechanical Division II | ALIPURDUAR | Madarihat | Implementation of Affordable IOT System at Mujnai TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16913 | TSM/020215 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
9 | Northern Mechanical Division II | ALIPURDUAR | Alipurduar - I | Implementation of Affordable IOT System at Paitkapara TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16914 | TSM/020209 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
10 | Northern Mechanical Division II | ALIPURDUAR | Kalchini | Implementation of Affordable IOT System at Radharani Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16915 | TSM/020211 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
11 | Northern Mechanical Division II | ALIPURDUAR | Kumargram | Implementation of Affordable IoT System at Rahimabad TG Water Supply Scheme in the district of Alipurduar under NMD-II, PHE Dte. | SM/16916 | TSM/020207 | IOT | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 13/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
12 | Northern Mechanical Division II | ALIPURDUAR |  | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. | SM/17189 | TSM/018531 | Support |  |  |  | 15/03/2023 |  |  | 22/03/2023 | 5 | 0 | inf | inf | 0 | 47
13 | Northern Mechanical Division II | COOCHBEHAR | Dinhata - I | Implementation of Affordable IOT System at Bara Pholimari Water Supply Scheme in Dinhata-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17933 | TSM/020078 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Sanjeeb Tigga) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
14 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - II | Implementation of Affordable IOT System at Baraibari Water Supply Scheme in Coochbehar-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17934 | TSM/020074 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
15 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - I | Implementation of Affordable IOT System at Bogdabari Keshaibari Water Supply Scheme in Coochbehar-I Block of Coochbehar districtunder Northern Mechanical Division-II, P.H.E. Dte. | SM/17935 | TSM/020069 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
16 | Northern Mechanical Division II | COOCHBEHAR | Sitai | Implementation of Affordable IOT System at Chamta Water Supply Scheme in Sitai Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17936 | TSM/020081 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Sanjeeb Tigga) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
17 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - I | Implementation of Affordable IOT System at Ekmukha Water Supply Scheme in Coochbehar-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17937 | TSM/020067 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
18 | Northern Mechanical Division II | COOCHBEHAR | Dinhata - II | Implementation of Affordable IOT System at Kishmatdasgram Water Supply Scheme in Dinhata-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17938 | TSM/020080 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Sanjeeb Tigga) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
19 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - II | Implementation of Affordable IOT System at Maranadirkuthi Water Supply Scheme in Coochbehar-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17939 | TSM/020073 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
20 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - I | Implementation of Affordable IOT System at Panisala Water Supply Scheme in Coochbehar-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17940 | TSM/020070 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
21 | Northern Mechanical Division II | COOCHBEHAR | Dinhata - I | Implementation of Affordable IOT System at Petla Water Supply Scheme in Dinhata-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17941 | TSM/020079 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Sanjeeb Tigga) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
22 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - I | Implementation of Affordable IOT System at Putimari Fuleswari Water Supply Scheme in Coochbehar-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17942 | TSM/020072 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
23 | Northern Mechanical Division II | COOCHBEHAR | Cooch Behar - I | Implementation of Affordable IOT System at Rajpur Water Supply Scheme in Coochbehar-I Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17944 | TSM/020071 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
24 | Northern Mechanical Division II | COOCHBEHAR | Tufanganj - II | Implementation of Affordable IOT System at Rampur (Zone-I) Water Supply Scheme in Tufanganj-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17951 | TSM/020077 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
25 | Northern Mechanical Division II | COOCHBEHAR | Tufanganj - II | Implementation of Affordable IOT System at Rampur (Zone-II) Water Supply Scheme in Tufanganj-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17954 | TSM/020076 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
26 | Northern Mechanical Division II | COOCHBEHAR | Sitai | Implementation of Affordable IOT System at Satbhandari Water Supply Scheme in Sitai Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17958 | TSM/020082 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Sanjeeb Tigga) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
27 | Northern Mechanical Division II | COOCHBEHAR | Tufanganj - II | Implementation of Affordable IOT System at Takoamari Water Supply Scheme in Tufanganj-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17989 | TSM/020075 | IOT | Coochbehar Mechanical Sub Division | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,PHE Dte. | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 5 | 0 | 0 | 0 |  | NAN