## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Jhargram Division | JHARGRAM | Gopiballavpur - I | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | SM/08736 | TSM/007489 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | 09/09/2021 | 09/12/2022 | 09/12/2021 | 26/09/2023 | 4 | 804 | inf | inf | 81 | 86
2 | Jhargram Division | JHARGRAM |  | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Jhargram District. | SM/08978 | TSM/008141 | Support |  |  |  | 29/10/2021 | 19/08/2022 | 18/08/2023 | 25/02/2023 | 0 | 0 | inf | inf | 33 | 70
3 | Jhargram Division | JHARGRAM | Gopiballavpur - II | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | TSM/008605 | Augmentation | Jhargram Sub-Division | Assistant Engineer | JE (M),Junior Engineer-III | 12/11/2021 | 15/03/2022 | 30/06/2023 | 11/04/2024 | 9 | 89 | inf | inf | 81 | 52
4 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | TSM/010157 | Anganwadi | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer Nayagram block | 16/03/2022 | 16/02/2023 | 30/11/2023 | 30/06/2023 | 37 | 0 | inf | inf | 20 | 73
5 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(174 nos.) within Sankrail Block under Jhargram District. | SM/10350 | TSM/010159 | Anganwadi | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer-II | 16/03/2022 | 11/02/2023 | 08/02/2024 | 24/11/2023 | 1 | 0 | inf | inf | 10 | 26
6 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(220 nos.) within Gopiballavpur-I Block under Jhargram District. | SM/10351 | TSM/010152 | Anganwadi | Gopiballavpur Sub Division | Assistant Engineer |  | 16/03/2022 | 03/05/2023 | 31/12/2023 | 04/09/2023 | 1 | 0 | inf | inf | 11 | 24
7 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers (137 nos.) within Gopiballavpur-II Block under Jhargram District. | SM/10352 | TSM/010153 | Anganwadi | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer Gopiballavpur-II block | 16/03/2022 | 20/01/2023 | 31/12/2023 | 17/10/2023 | 1 | 0 | inf | inf | 10 | 87
8 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | TSM/010156 | Anganwadi | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | 16/03/2022 | 01/12/2022 | 30/06/2023 | 05/05/2023 | 31 | 0 | inf | inf | 0 | 51
9 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(176 nos.) within Jhargram Block under Jhargram District. | SM/10354 | TSM/010158 | Anganwadi | Jhargram Division | Assistant Engineer Headquarter |  | 16/03/2022 | 24/10/2022 | 31/12/2023 | 07/09/2023 | 1 | 0 | inf | inf | 70 | 61
10 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | TSM/010154 | Anganwadi | Jhargram Sub-Division | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | 16/03/2022 | 01/03/2023 | 31/12/2023 | 27/07/2023 | 20 | 0 | inf | inf | 50 | 42
11 | Jhargram Division | JHARGRAM |  | Water Supply System at Anganwadi Centers(306 nos) within Binpur-II Block under Jhargram District. | SM/10356 | TSM/010155 | Anganwadi | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 16/03/2022 | 01/06/2023 | 31/12/2023 | 08/09/2023 | 2 | 0 | inf | inf | 10 | 64
12 | Jhargram Division | JHARGRAM |  | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | TSM/008809 | School | Jhargram Sub-Division | Assistant Engineer | Junior Engineer Binpur-I block | 16/03/2022 | 10/05/2023 | 31/12/2023 | 22/08/2023 | 14 | 0 | inf | inf | 10 | 41
13 | Jhargram Division | JHARGRAM | Sankrail | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10489 | TSM/008545 | Augmentation | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer Sankrail block | 13/04/2022 | 03/09/2024 | 13/10/2022 | 12/06/2023 | 3 | 45 | inf | inf | 0 | 14
14 | Jhargram Division | JHARGRAM | Jhargram | PINDRAKULI AND ADJOINING MOUJAS PWSS | SM/12450 | TSM/014117 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 13/09/2022 | 26/05/2023 | 13/03/2024 | 12/06/2023 | 3 | 871 | inf | nan | 0 | 0
15 | Jhargram Division | JHARGRAM | Jhargram | RAJBAND AND ADJOINING MOUJAS PWSS | SM/12842 | TSM/013139 | New | Jhargram Division | Assistant Engineer Headquarter | Junior Engineer-II | 22/09/2022 | 30/09/2023 | 22/03/2024 | 12/06/2023 | 3 | 786 | inf | nan | 0 | 0
16 | Jhargram Division | JHARGRAM | Binpur - II | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS | SM/16675 | TSM/017880 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 14/03/2023 | 02/08/2023 | 14/09/2024 | 12/06/2023 | 2 | 1017 | inf | nan | 0 | 0
17 | Jhargram Division | JHARGRAM | Binpur - II | KHARIYARATA AND ADJOINING MOUJAS PWSS | SM/17592 | TSM/014387 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 18/03/2023 | 20/09/2023 | 31/10/2024 | 11/04/2024 | 6 | 713 | inf | inf | 19 | 8
18 | Jhargram Division | JHARGRAM | Binpur - II | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | TSM/015911 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 17/03/2023 | 09/02/2024 | 01/11/2024 | 11/04/2024 | 9 | 727 | inf | inf | 21 | 1
19 | Jhargram Division | JHARGRAM | Binpur - II | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | TSM/015888 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 17/03/2023 | 09/02/2024 | 31/10/2024 | 11/04/2024 | 12 | 681 | inf | inf | 9 | 0
20 | Jhargram Division | JHARGRAM | Binpur - II | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | TSM/015763 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 | 20/03/2023 | 17/09/2024 | 12/06/2023 | 5 | 1639 | inf | inf | 0 | 7
21 | Jhargram Division | JHARGRAM | Jamboni | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. | SM/17945 | TSM/017857 | Augmentation | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 17/03/2023 | 05/06/2023 | 31/12/2023 | 11/04/2024 | 3 | 0 | inf | inf | 77 | 41
22 | Jhargram Division | JHARGRAM | Binpur - II | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | TSM/017859 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | 17/03/2023 | 14/08/2023 | 17/09/2023 | 08/09/2023 | 11 | 0 | inf | inf | 88 | 6
23 | Jhargram Division | JHARGRAM | Sankrail | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17956 | TSM/017855 | Augmentation | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer Sankrail block | 17/03/2023 | 17/05/2023 | 17/02/2024 | 26/01/2024 | 2 | 0 | inf | nan | 51 | 0
24 | Jhargram Division | JHARGRAM | Gopiballavpur - II | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | TSM/017850 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 17/03/2023 | 04/07/2023 | 31/10/2024 | 11/04/2024 | 4 | 150 | inf | inf | 32 | 5
25 | Jhargram Division | JHARGRAM | Nayagram | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17966 | TSM/017853 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | 17/03/2023 | 01/09/2023 | 31/10/2024 | 11/04/2024 | 2 | 25 | inf | inf | 48 | 10
26 | Jhargram Division | JHARGRAM | Binpur - I | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18012 | TSM/017847 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 17/03/2023 | 01/06/2023 | 31/10/2023 | 08/09/2023 | 2 | 10 | inf | inf | 99 | 46
27 | Jhargram Division | JHARGRAM | Gopiballavpur - II | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | SM/18190 | TSM/017852 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | 31/03/2023 | 01/09/2023 | 31/07/2024 | 11/04/2024 | 4 | 294 | inf | inf | 48 | 17
Total | [14 empty] | 192 | 7851 | 0 | 0 |  | NAN