## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | TSM/005582 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 06/10/2020 | 26/11/2020 |  | 27/06/2023 | 0 | 1989 | inf | nan | 100 | 0
2 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | TSM/005669 | Retrofitting | Jhargram Sub-Division |  | Junior Engineer-III | 06/10/2020 | 28/12/2021 |  | 27/06/2023 | 0 | 1720 | inf | nan | 100 | 0
3 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | TSM/005670 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 06/10/2020 | 10/05/2022 |  | 27/06/2023 | 0 | 2031 | inf | nan | 100 | 0
4 | Jhargram Division | JHARGRAM | Gopiballavpur - I | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | TSM/005671 | Retrofitting | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer-II | 06/10/2020 | 11/12/2020 |  | 27/06/2023 | 0 | 1771 | inf | nan | 100 | 0
5 | Jhargram Division | JHARGRAM | Jamboni | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram | SM/06832 | TSM/005673 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 06/10/2020 | 26/11/2020 |  | 27/06/2023 | 0 | 1635 | inf | nan | 100 | 0
6 | Jhargram Division | JHARGRAM | Binpur - II | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. | SM/06834 | TSM/005583 | Retrofitting |  |  |  | 06/10/2020 |  |  | 12/06/2023 | 0 | 2218 | inf | nan | 100 | 0
7 | Jhargram Division | JHARGRAM | Binpur - II | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. | SM/06835 | TSM/005584 | Retrofitting |  |  |  | 06/10/2020 |  |  | 12/06/2023 | 0 | 1641 | inf | nan | 100 | 0
8 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to accommodate FHTC under JJM in Bahadurpur P.W.S.S. (Phase-II) within Binpur-I Block | SM/08173 | TSM/007031 | Retrofitting |  |  |  | 08/02/2021 |  |  | 12/06/2023 | 0 | 69 | inf | nan | 100 | 0
9 | Jhargram Division | JHARGRAM | Gopiballavpur - II | Retrofitting to accommodate FHTC under JJM in Junsola P.W.S.S. (Phase-II) within Gopiballavpur-II Block | SM/08174 | TSM/007032 | Retrofitting |  |  |  | 08/02/2021 |  |  | 12/06/2023 | 0 | 100 | inf | nan | 100 | 0
10 | Jhargram Division | JHARGRAM | Jhargram | Retrofitting to accommodate FHTC under JJM in Lohamelya P.W.S.S. (Phase-II) within Jhargram Block | SM/08175 | TSM/007033 | Retrofitting |  |  |  | 08/02/2021 |  |  | 12/06/2023 | 0 | 155 | inf | nan | 100 | 0
11 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | TSM/007486 | Retrofitting | Jhargram Sub-Division |  | Junior Engineer-III | 09/09/2021 | 30/09/2021 |  | 12/06/2023 | 0 | 559 | inf | nan | 100 | 0
12 | Jhargram Division | JHARGRAM | Sankrail | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | TSM/007488 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer Sankrail block | 09/09/2021 | 22/03/2022 |  | 27/06/2023 | 0 | 1849 | inf | nan | 100 | 0
13 | Jhargram Division | JHARGRAM | Binpur - I | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) | SM/09102 | TSM/008213 | Retrofitting | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-I | 28/10/2021 | 22/10/2024 |  | 12/06/2023 | 0 | 52 | inf | nan | 100 | 0
14 | Jhargram Division | JHARGRAM | Gopiballavpur - II | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | TSM/008527 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-III | 12/11/2021 | 27/01/2022 |  | 27/06/2023 | 0 | 2232 | inf | nan | 100 | 0
15 | Jhargram Division | JHARGRAM | Jamboni | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. | SM/09385 | TSM/008669 | Retrofitting | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 12/11/2021 | 15/02/2022 |  | 08/09/2023 | 0 | 150 | inf | nan | 100 | 0
16 | Jhargram Division | JHARGRAM | Binpur - I | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | TSM/007452 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-III | 18/11/2021 | 04/04/2022 |  | 27/06/2023 | 0 | 0 | inf | nan | 100 | 0
17 | Jhargram Division | JHARGRAM | Nayagram | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. | SM/10439 | TSM/010186 | Retrofitting |  |  |  | 12/04/2022 |  |  | 12/06/2023 | 0 | 90 | inf | nan | 100 | 0
18 | Jhargram Division | JHARGRAM | Binpur - I | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10485 | TSM/008541 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-I | 13/04/2022 | 05/08/2022 |  | 27/06/2023 | 0 | 303 | inf | nan | 100 | 0
19 | Jhargram Division | JHARGRAM | Binpur - I | Rejuvenation of Ground Water Based Netai PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10488 | TSM/008544 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 13/04/2022 | 13/05/2022 |  | 16/01/2024 | 0 | 22 | inf | nan | 100 | 0
20 | Jhargram Division | JHARGRAM |  | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. | SM/16630 | TSM/016472 | Support |  |  |  | 14/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
21 | Jhargram Division | JHARGRAM |  | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM | SM/16656 | TSM/012061 | Support |  |  |  | 14/03/2023 |  |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
22 | Jhargram Division | JHARGRAM |  | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | TSM/013411 | Support | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 14/03/2023 | 31/10/2023 |  | 20/03/2023 | 0 | 0 | inf | nan | 0 | 0
23 | Jhargram Division | JHARGRAM |  | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission | SM/18228 | TSM/017804 | Support | Jhargram Division | Assistant Engineer Headquarter |  | 15/03/2023 | 27/09/2024 |  | 17/05/2023 | 0 | 0 | inf | nan | 0 | 0
24 | Jhargram Division | JHARGRAM |  | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under JHARGRAM Division, PHE Dte. | SM/19267 | TSM/022404 | Support |  |  |  | 10/09/2024 |  |  | 11/09/2024 | 0 | 0 | inf | nan | 0 | 0
Total | [14 empty] | 0 | 18586 | 0 | 0 |  | NAN